## Read me
ERCOT Queue Brief: September 2026 report
From ERCOT's September 2026 Generator Interconnection Status report, compared with August 2026. Built 2026-10-24.
Every row is from ERCOT's report or the document linked on the issue page; names, developers and points of interconnection are as ERCOT lists them.
A request is a study position, not a project. ERCOT prepares the report for planning purposes from developer-entered data; it may contain errors.
Issue page: https://parcelandgrid.com/brief/2026-09/ Method: https://parcelandgrid.com/methodology.html
27 new requests (11,125 MW) · 48 withdrawn (8,680 MW) · net +2,445 MW · 38 moved forward · 21 past target date

## New requests
INR | Request | County | Type | MW | POI (as listed)
28INR0456 | Brazos Energy Security | Fisher | Gas combined cycle | 3000 | Tap 345 kV (Bus #1048) Tonkawa Switch – (Bus #11050) Dusty Road
33INR0007 | Blue Energy Center - Phase 3 – Steam Stage 2 | Victoria | Nuclear | 1320 | Tap 345kV 80286 DULCE7A - 8676 STATIC7A
29INR0354 | Wolf Bone North Energy Center | Reeves | Gas combined cycle | 1174.4 | TNMP Cowpen 345kV Substation POIB 38044 (4 mile transmission line will connect POI at customer substation to POIB in the Cowpen substation)
30INR0150 | Blue Energy Center- Phase 1a - Gas | Victoria | Gas turbine | 780 | Tap 345kV 80286 DULCE7A - 8676 STATIC7A
26INR0230 | Titus Sienta Solar | Pecos | Solar | 501.93 | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub
29INR0397 | Black Mountain Briscoe Gas | Briscoe | Gas combined cycle | 495.32 | ‎23914, Tule Canyon Substation, 345 kV
30INR0128 | Horizon Ridge Wind | Winkler | Wind | 406.55 | POIB is 131853 NOTSW_1_8 - the Notrees SW Substation - Project includes property in Ector, Andrews, and Winkler counties.
26INR0530 | Longview Wind | Dawson | Wind | 352.6 | Venturi (Bus #59923)
27INR0636 | Myrtle Solar Repower | Brazoria | Solar | 314.27 | 42110 Angleton 138kV
28INR0520 | SunRustler Solar | Culberson | Solar | 301.49 | 11082 MAVRKDRW_8 138kV
29INR0399 | Rugged Prairie Wind | Fisher | Wind | 294.14 | Tap 345kV BUS #11305 Dermott- BUS #60706 Kirchhef
29INR0224 | Mandolin Solar III SLF | Starr | Solar | 250 | Tap 345kV 80355 Del Sol - 80227 Rapido
29INR0393 | Lone Tiger Solar | Jones | Solar | 242.8 | Tap 345 kV Claytonville (#68001) to phantom hill (#68004)
29INR0394 | Buzzer Butte Solar | Kent | Solar | 242.8 | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911)
30INR0164 | Buzzer Butte 2 Solar | Kent | Solar | 242.8 | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911)
30INR0123 | Sideoats Solar 1 | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345 kV
30INR0124 | Sideoats Solar 2 | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV
30INR0125 | Sideoats Solar 3 | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV
29INR0263 | Whitethorn Solar Project | Pecos | Solar | 163.1 | 345KV 860 GIRVINSW
29INR0272 | Trail Ranch Solar 2 | Concho | Solar | 132.85 | Tap 345 kV 6444 Red Creek -7077 Amos Creek
30INR0133 | Starfield Energy Storage | Wharton | Battery storage | 122.2 | Tap 138kV 44150 Hungerford - 44190 East Bernard
27INR0202 | Shallow Valley Storage | Ward | Battery storage | 103.39 | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub
26INR0341 | Megamouth Energy Storage | Harris | Battery storage | 101.3 | 42750 Mykawa 138 kV
27INR0655 | Lynx Energy Storage_Full | Nueces | MWH | 50 | PRIMAVERA 138kV Substation
28INR0495 | Old Alma Road Solar | Ellis | Solar | 20.06 | 2326 ENNS_SE_8 138kV
25INR0602 | Hockley BESS | Harris | Battery storage | 9.99 | 30.021619, -95.846315 Station Name (Station Code): Hockley (HK) LONG CODE: HOCKLY Short Code: HK TR5 ERCOT Bus Name: Hockley Feeder: HK-91 ERCOT Load Name: TR5 CNP XFMR #: HK TR5 ERCOT Bus #: 45880 Node: 0101
27INR0611 | Bodkin BESS SLF | Brazoria | Battery storage | 0 | The 138kV Danbury Dab DANBUR_POI_8 (BUS#42875) Station

## Withdrawn
INR | Request | County | Type | MW
29INR0162 | Wolf Bone North Energy Center (OLD) | Reeves | Gas combined cycle | 1204
28INR0113 | Axis Ridge Wind | Sutton | Wind | 392
25INR0057 | Sombrero Solar | Schleicher | Solar | 351.85
25INR0195 | Photo Solar 2 | Uvalde | Solar | 300
27INR0118 | Grapefruit Solar | Hidalgo | Solar | 291.4
21INR0380 | Charolais Solar | Matagorda | Solar | 261.63
29INR0026 | Skeeter Solar | Jones | Solar | 251
20INR0029 | Lutum Wind | Clay | Wind | 241.5
22INR0244 | Razorbill Solar | Matagorda | Solar | 240
28INR0101 | Vazlon Solar SLF | La Salle | Solar | 211.41
21INR0349 | Pearl Crescent Solar | Colorado | Solar | 208.35
27INR0228 | Sunlit Pines BESS SLF | Nacogdoches | Battery storage | 208.12
26INR0333 | VERTUS ENERGY STORAGE | Galveston | Battery storage | 207.3
24INR0302 | Pintail Pass BESS | San Patricio | Battery storage | 207.25
27INR0226 | Sunlit Pines Solar SLF | Nacogdoches | Solar | 206.71
23INR0501 | Soda Lake BESS 1 | Crane | Battery storage | 203.87
21INR0413 | Big Star Solar | Bastrop | Solar | 203.1
24INR0381 | Alexandrite Storage | Cameron | Battery storage | 203
24INR0459 | Exodus BESS | Caldwell | Battery storage | 201.36
27INR0350 | Saddle Horn Station BESS SLF | Comanche | Battery storage | 177.41
27INR0351 | Saddle Horn Station Solar SLF | Comanche | Solar | 174.64
25INR0672 | Fagus Solar Park 2 SLF | Childress | Solar | 166.57
20INR0091 | Fagus Solar Park 1 SLF | Childress | Solar | 166.42
25INR0555 | Stargazer Solar | Brazoria | Solar | 157.7
26INR0196 | Realitos Solar SLF | Duval | Solar | 150.49
25INR0706 | Bocanova Power II | Brazoria | Battery storage | 150.46
23INR0206 | PEREGRINE BESS | Goliad | Battery storage | 150
25INR0078 | Peregrine BESS 2 | Goliad | Battery storage | 150
23INR0168 | Charolais Storage | Matagorda | Battery storage | 150
24INR0122 | PHOTO BESS 2 | Uvalde | Battery storage | 150
25INR0194 | Photo Solar 1 | Uvalde | Solar | 150
27INR0272 | EMPower Odessa (TEF - Due Diligence) | Ector | Gas engines | 122.8
26INR0544 | Signal Hill BESS I | Wichita | Battery storage | 122.78
22INR0382 | Razorbill Storage | Matagorda | Battery storage | 120
25INR0055 | Three W Solar | Hill | Solar | 110.89
25INR0556 | Stargazer BESS | Brazoria | Battery storage | 104.5
23INR0204 | GALVANIC BESS | Kinney | Battery storage | 100
24INR0380 | Photo BESS 3 | Uvalde | Battery storage | 100
23INR0205 | SUNSETTER BESS | Uvalde | Battery storage | 100
21INR0469 | Big Star Storage | Bastrop | Battery storage | 80
24INR0121 | PHOTO BESS 1 | Uvalde | Battery storage | 75
23INR0181 | Starling Storage | Gonzales | Battery storage | 63.6
21INR0470 | Pearl Crescent Storage | Colorado | Battery storage | 50.26
22INR0363 | Hayhurst Texas Solar | Culberson | Solar | 24.76
25INR0766 | Mesquite BESS2 | Cameron | Battery storage | 9.99
26INR0736 | Hovey Solar 2 | Pecos | Solar | 8.05
26INR0195 | Realitos Storage SLF | Duval | Battery storage | 0
28INR0104 | Vazlon BESS SLF | La Salle | Battery storage | 0

## Moved forward
INR | Request | County | Type | MW | From | To
28INR0114 | Elk Ridge Solar | Pecos | Solar | 503 | In study | Signed; security posted
30INR0053 | MRR Solar | Pecos | Solar | 500 | In study | Signed; security posted
29INR0068 | Gregory Power Development SLF | San Patricio | Gas combined cycle | 469.9 | In study | Signed
27INR0108 | Paint Rock Wind | Concho | Wind | 379.18 | In study | Signed
27INR0091 | Oak Tree Energy Storage | Lavaca | Battery storage | 310.2 | In study | Signed
27INR0355 | Gardner Draw Solar | Glasscock | Solar | 309.5 | Signed | Signed; security posted
29INR0219 | Cenizo Solar | Webb | Solar | 301.39 | In study | Signed
27INR0438 | Wisdom Solar SLF | Pecos | Solar | 299.37 | In study | Signed
20INR0236 | New Hickory Solar | Jackson | Solar | 209.15 | Energized | Approved to connect
29INR0132 | Caesar Storage | Borden | Battery storage | 205.5 | In study | Signed; security posted
24INR0383 | Soda Lake BESS 2 SLF | Crane | Battery storage | 205.35 | In study | Signed
28INR0389 | Tri-X BESS 1 SLF | Crane | Battery storage | 205.3 | In study | Signed
23INR0249 | Limewood Solar | Bell | Solar | 204.6 | Energized | Approved to connect
25INR0231 | Apache Hill BESS | Hood | Battery storage | 201.15 | Signed; security posted | Energized
25INR0144 | Jasper BESS | Midland | Battery storage | 201.13 | Signed | Signed; security posted
25INR0146 | Blue Heron BESS | Reeves | Battery storage | 201.13 | Signed | Signed; security posted
21INR0362 | Oystercatcher Solar | Ellis | Solar | 198.43 | Signed | Energized
29INR0131 | Caesar Solar | Borden | Solar | 181.6 | In study | Signed; security posted
21INR0334 | Nightfall Solar | Uvalde | Solar | 180.87 | Signed; security posted | Energized
25INR0579 | Albatross BESS 2 | McLennan | Battery storage | 159.6 | In study | Signed; security posted
24INR0491 | Gunnar BESS | Hidalgo | Battery storage | 154.75 | Energized | Approved to connect
21INR0253 | Ulysses Solar | Coke | Solar | 151.2 | Signed; security posted | Energized
27INR0288 | Rain Lily Solar 1 | Hood | Solar | 147.76 | In study | Signed; security posted
28INR0305 | Iron Cowboy Solar | San Patricio | Solar | 144.59 | Signed | Signed; security posted
24INR0160 | Huisache Solar | Wilson | Solar | 125.59 | Signed | Signed; security posted
24INR0313 | Backbone Creek BESS | Burnet | Battery storage | 124.1 | Signed; security posted | Approved to connect
26INR0470 | Roxton Solar | Lamar | Solar | 116.8 | In study | Signed; security posted
27INR0285 | Rain Lily Storage 1 | Hood | Battery storage | 105.6 | In study | Signed; security posted
27INR0440 | Wisdom BESS SLF | Pecos | Battery storage | 102.88 | In study | Signed
26INR0469 | Roxton Storage | Lamar | Battery storage | 102 | In study | Signed; security posted
27INR0234 | Lima Solar Project | Grayson | Solar | 101.3 | In study | Signed
24INR0376 | Huisache BESS | Wilson | Battery storage | 100.67 | Signed | Signed; security posted
25INR0227 | SERENGETI SOLAR | Delta | Solar | 76.18 | Signed | Signed; security posted
25INR0246 | VALDIVIAN SOLAR | Hunt | Solar | 74.9 | In study | Signed; security posted
28INR0306 | Iron Cowboy Storage | San Patricio | Battery storage | 63.27 | Signed | Signed; security posted
25INR0071 | Albatross BESS | McLennan | Battery storage | 50.4 | In study | Signed; security posted
26INR0698 | Staghorn Gas | Ward | Gas engines | 9.99 | Signed; security posted | Approved to connect
26INR0702 | Bexar Martinez BESS | Bexar | Battery storage | 9.99 | Signed; security posted | Energized

## Crowded POIs
Substation (PSS/E bus) | Counties | Requests | Direct | MW
Solstice (60404) 345 kV | Pecos, Reeves | 23 | 8 | 13000
RILEY7A (6101) 345 kV | Baylor, Foard, Hardeman, Wichita, Wilbarger | 22 | 8 | 9936
Navarro (68091) 345 kV | Ellis, Freestone, Hill, Navarro | 22 | 1 | 5873
Tnp One (39950) 345 kV | Bell, Milam, Robertson | 22 | 4 | 3995
Cruce (80079) 345 kV | Duval, Jim Hogg, Starr, Webb | 21 | 1 | 6554
San Miguel (5901) 345 kV | Atascosa, Duval, McMullen, Wilson | 20 | 0 | 5476
Elm Creek (5133) 345 kV | DeWitt, Gonzales, Guadalupe, Wilson | 19 | 0 | 4695
Brown (1444) 345 kV | Brown, Coleman, Mills, Runnels | 19 | 2 | 4694
STP (5915) 345 kV | DeWitt, Gonzales, Guadalupe, Lavaca, Matagorda, Refugio, Victoria | 17 | 1 | 5264
CENIZO7C (80225) 345 kV | Jim Hogg, Zapata | 16 | 0 | 4321
Cottonwood (59904) 345 kV | Cottle, Crosby, Dickens, Kent, King, Motley | 16 | 3 | 3924
Del Sol (80355) 345 kV | Jim Hogg, Starr | 16 | 2 | 3856
Riley (6111) 345 kV | Clay, Montague, Wichita, Wilbarger, Wise | 15 | 0 | 4272
Tule Canyon (23914) 345 kV | Armstrong, Briscoe, Castro, Swisher | 14 | 2 | 7289
Zorn (7042) 345 kV | Bastrop, Caldwell, Guadalupe | 14 | 6 | 4993
Del Sol (80307) 345 kV | Jim Hogg, Zapata | 14 | 0 | 3930
Twin Oak (3400) 345 kV | Robertson | 14 | 2 | 2397
EDITHCLA7B (60505) 345 kV | Foard, Hardeman, Wilbarger | 13 | 0 | 6946
Krum West (1730) 345 kV | Clay, Cooke, Jack, Montague, Wichita, Wilbarger, Wise | 13 | 0 | 3688
TRICRN1_5 (2432) 345 kV | Dallas, Kaufman | 13 | 0 | 1520
Limestone (46020) 345 kV | Freestone, Leon, Madison, Navarro | 12 | 4 | 5105
Graham (1430) 345 kV | Fisher, Haskell, Jack, Throckmorton, Young | 12 | 0 | 4716
Fowlerton (5709) 345 kV | Atascosa, La Salle, McMullen, Webb | 12 | 0 | 2773
Phantom Hill (68004) 345 kV | Fisher, Jones | 12 | 3 | 1998
COLETO7A (8164) 345 kV | Goliad, Karnes | 12 | 0 | 1545
Bottlebrush (38441) 345 kV | Pecos | 11 | 1 | 7037
Clear Crossing (60515) 345 kV | Haskell, Jack, Jones, Shackelford, Stonewall | 11 | 1 | 5068
North Mccamey (76000) 345 kV | Crane, Reagan, Upton | 11 | 2 | 3386
Edith Clarke (60500) 345 kV | Cottle, Dickens, Foard, King, Motley | 11 | 3 | 3229
Lobo (80219) 345 kV | La Salle, Webb | 11 | 3 | 2827
Twin Buttes (76009) 345 kV | Coke, Concho, Schleicher, Tom Green | 11 | 0 | 2620
Claytonville (68001) 345 kV | Fisher, Jones | 11 | 1 | 1840
PAWNEESW5 (5725) 345 kV | Bee, Goliad, Karnes | 11 | 2 | 1752
Willow Creek (1421) 345 kV | Jack, Wise | 10 | 1 | 5843
Venus (1907) 345 kV | Ellis, Hill | 10 | 0 | 3998
Angstrom (8249) 345 kV | Refugio, San Patricio | 10 | 1 | 3749
Bluff Creek (60040) 345 kV | Coleman, Runnels, Taylor | 10 | 0 | 3121
Wolf (11010) 345 kV | Ector, Ward | 10 | 0 | 2931
Singleton (44645) 345 kV | Grimes, Leon, Madison | 10 | 3 | 2817
Austrop (7040) 345 kV | Bastrop, Caldwell, Milam, Travis | 10 | 0 | 2624
Sand Bluff (59902) 345 kV | Glasscock, Sterling | 10 | 7 | 2197
Alibates (23900) 345 kV | Armstrong, Briscoe, Carson, Swisher | 9 | 1 | 5267
Jacksboro (1429) 345 kV | Jack, Wise | 9 | 2 | 4324
Moses Ckts (1695) 345 kV | Franklin, Hopkins, Lamar | 9 | 0 | 3642
Ogallala (23912) 345 kV | Castro, Swisher | 9 | 3 | 3007
SAM (68090) 345 kV | Hill, McLennan | 9 | 3 | 2751
Amos Creek (7077) 345 kV | Concho, Tom Green | 9 | 2 | 2636
Hillje (44200) 345 kV | Matagorda, Wharton | 9 | 5 | 2307
WATMLL_W5 (2427) 345 kV | Dallas, Ellis | 9 | 0 | 968
Tonkawa (1048) 345 kV | Fisher, Haskell, Nolan | 8 | 2 | 5745
Deaf Smith (23908) 345 kV | Deaf Smith | 8 | 6 | 5238
Paris (1692) 345 kV | Lamar | 8 | 2 | 2667
Venus (1906) 345 kV | Ellis, Navarro | 8 | 2 | 2408
Wallis (44740) 138 kV | Austin, Wharton | 8 | 0 | 2039
Big Hill (76003) 345 kV | Schleicher, Tom Green | 8 | 2 | 1880
Central Bluff (11406) 345 kV | Coleman, Nolan, Runnels, Taylor | 8 | 3 | 1873
Angleton (42110) 138 kV | Brazoria | 8 | 2 | 1406
Bell County (3687) 345 kV | Bell, Milam | 8 | 1 | 1400
Longshore (1058) 345 kV | Glasscock, Howard, Mitchell | 8 | 4 | 1351
BUS2 (11050) 345 kV | Fisher, Throckmorton, Young | 7 | 0 | 4833
Sweetwater East (11420) 345 kV | Nolan | 7 | 5 | 3122
Gasconades Creek (76030) 345 kV | Mitchell, Sterling | 7 | 3 | 2798
Valley South (1729) 345 kV | Fannin, Grayson, Lamar | 7 | 1 | 2365
GEBHRT_X65B8 (44700) 138 kV | Austin | 7 | 0 | 1936
Divide (76090) 345 kV | Coke, Sterling, Tom Green | 7 | 1 | 1866
Jewett (3390) 345 kV | Falls, Freestone, Grimes, Leon, Madison | 7 | 0 | 1862
Cenizo (80220) 345 kV | Jim Hogg, Webb | 7 | 2 | 1807
Rapido (80227) 345 kV | Starr, Zapata | 7 | 2 | 1752
Bearkat (59903) 345 kV | Glasscock, Reagan, Upton | 7 | 1 | 1721
Tesla (60501) 345 kV | Childress, Hardeman | 7 | 3 | 1277
STATIC7A (8676) 345 kV | Refugio, Victoria | 6 | 0 | 4217
Bakerfield (76002) 345 kV | Pecos | 6 | 0 | 3740
Woodard (11699) 345 kV | Franklin, Lamar | 6 | 0 | 2707
Muleshoe (59922) 345 kV | Borden | 6 | 6 | 2047
Comanche (1440) 345 kV | Comanche, Erath | 6 | 3 | 2043
Tesla (60504) 345 kV | Hardeman, Wilbarger | 6 | 0 | 1936
Tnmp Fm (39703) 138 kV | Brazoria | 6 | 4 | 1747
Lon Hill (8455) 345 kV | Brooks, Nueces, San Patricio, Zapata | 6 | 0 | 1573
Big Onion (2466) 345 kV | Ellis, Navarro | 6 | 0 | 1545
Novaprime (59908) 345 kV | Dickens, Kent | 6 | 4 | 1500
Grissom (8624) 345 kV | San Patricio | 6 | 0 | 1492
Shaula (5380) 345 kV | DeWitt, Gonzales, Lavaca, Wilson | 6 | 1 | 1439
Goddard (8606) 345 kV | Bee, San Patricio | 6 | 4 | 1284
Buckhorn (3424) 345 kV | Brown, Lampasas, Mills | 6 | 0 | 1219
Longdraw (59900) 345 kV | Borden, Dawson | 6 | 2 | 1087
North Edinburg (8383) 345 kV | Cameron, Hidalgo, Willacy | 6 | 0 | 1032
Garvey Road (17002) 345 kV | Archer, Young | 6 | 2 | 1014
Brackettville (8252) 138 kV | Kinney, Maverick | 6 | 1 | 906
Cash (2464) 345 kV | Hopkins, Hunt | 6 | 0 | 866
Bates (8392) 138 kV | Hidalgo, Starr | 6 | 0 | 749
Liston (8394) 138 kV | Hidalgo, Starr | 6 | 0 | 749
Elkton (3105) 345 kV | Kaufman, Rusk | 6 | 0 | 703
Lockhart (7216) 138 kV | Caldwell | 6 | 1 | 479
White Baker (38435) 345 kV | Pecos | 5 | 0 | 4024
Prong Moss (10057) 345 kV | Howard, Mitchell | 5 | 0 | 3406
Little Pond (3377) 345 kV | Milam | 5 | 3 | 2702
Kingfisher (79501) 345 kV | Cameron | 5 | 2 | 2334
Mhos (59911) 345 kV | Kent, Scurry | 5 | 3 | 2143
Windmill (23910) 345 kV | Castro, Deaf Smith | 5 | 0 | 2066
Railhead (79005) 345 kV | Carson, Hutchinson | 5 | 4 | 1982
SANDLAKE_5 (11098) 345 kV | Pecos, Reeves, Ward | 5 | 1 | 1842
Foxtail (6076) 345 kV | Baylor, Knox | 5 | 0 | 1658
Faraday (59905) 345 kV | Borden | 5 | 4 | 1611
Wshack (68000) 345 kV | Fisher, Jones, Shackelford | 5 | 0 | 1588
Red Creek (6444) 345 kV | Concho, Tom Green | 5 | 2 | 1390
Comanche Peak (1900) 345 kV | Comanche, Erath, Parker, Somervell | 5 | 0 | 1382
Tiempo (80224) 345 kV | Webb, Zapata | 5 | 1 | 1352
BIGBRNW_5 (3381) 345 kV | Freestone, Navarro | 5 | 0 | 1285
JIM_ENG_8 (3351) 138 kV | Houston | 5 | 0 | 1273
FLATBRA_8 (3345) 138 kV | Houston | 5 | 0 | 1273
Wa Parish (44000) 345 kV | Fort Bend, Matagorda | 5 | 3 | 1258
Lytton Springs (9074) 345 kV | Caldwell, Fayette | 5 | 0 | 1231
Reforzar (80078) 345 kV | Brooks, Nueces | 5 | 3 | 1199
Tn West (39500) 138 kV | Brazoria | 5 | 1 | 1181
Savana (43180) 345 kV | Brazoria | 5 | 1 | 1137
Anna (2373) 345 kV | Collin, Cooke, Fannin, Grayson | 5 | 1 | 1131
Reata (68051) 345 kV | Callahan, Eastland | 5 | 3 | 1033
Palmito (79500) 345 kV | Cameron | 5 | 3 | 1031
Tradinghouse (3405) 345 kV | Falls, McLennan | 5 | 0 | 974
Stewart Road (80137) 345 kV | Cameron, Hidalgo | 5 | 0 | 942
Dermott (11305) 345 kV | Fisher, Kent, Scurry | 5 | 3 | 941
Martin Lake (3100) 345 kV | Rusk | 5 | 0 | 940
Victoria (8172) 138 kV | Goliad, Victoria | 5 | 0 | 871
Mustang Bayou (42960) 138 kV | Brazoria | 5 | 0 | 856
Hudson (42100) 138 kV | Brazoria | 5 | 0 | 856
South Lane (43190) 138 kV | Wharton | 5 | 2 | 778
WATERH_POI_5 (44880) 345 kV | Wharton | 5 | 5 | 757
Big Wells (8613) 138 kV | Dimmit, Frio | 5 | 0 | 638
Rock Island (57640) 138 kV | Colorado | 5 | 1 | 626
Hays Energy (7043) 345 kV | Comal, Hays | 5 | 4 | 588
Revolution (3387) 138 kV | Hill, Navarro | 5 | 3 | 566
Prairie Hill (107) 69 kV | Limestone, Navarro | 5 | 4 | 306
Parker (1436) 345 kV | Jack, Parker | 4 | 0 | 2605
Fort Smith (3389) 345 kV | Ellis, Hill | 4 | 1 | 2487
Blackwater (23920) 345 kV | Hale | 4 | 4 | 2104
Abilene Mulberry (6235) 345 kV | Taylor | 4 | 2 | 1989
Liberty (68092) 345 kV | Hill, Limestone | 4 | 4 | 1810
Stryker (3109) 345 kV | Cherokee, Nacogdoches, Rusk | 4 | 0 | 1696
Big Brown (3380) 345 kV | Freestone | 4 | 0 | 1647
Galvani (59912) 345 kV | Scurry | 4 | 4 | 1581
Spruce (5400) 345 kV | Bexar | 4 | 0 | 1453
Tempss (3414) 345 kV | Bell, Falls | 4 | 0 | 1388
Buck Canyon (59916) 345 kV | Borden | 4 | 4 | 1387
AJO (80076) 345 kV | Kenedy | 4 | 2 | 1311
Hog Creek (3704) 345 kV | Milam | 4 | 0 | 1292
Jim Treece (61001) 345 kV | Hardeman, Wilbarger | 4 | 2 | 1280
Fisher Road (1425) 345 kV | Wichita | 4 | 0 | 1243
Cattleman (10053) 345 kV | Mitchell | 4 | 0 | 1238
Reiter (18544) 345 kV | Ector | 4 | 0 | 1202
Killeen (3422) 345 kV | Lampasas, Mills | 4 | 0 | 1126
Odysseus (60072) 345 kV | Coke, Runnels | 4 | 1 | 1067
LEON_CRK (38355) 138 kV | Pecos | 4 | 2 | 1054
Seabreeze (43020) 345 kV | Brazoria | 4 | 1 | 960
Bailey (44040) 345 kV | Wharton | 4 | 4 | 959
Bowman (1422) 345 kV | Archer, Wilbarger | 4 | 0 | 949
Braunig (5475) 345 kV | Bexar | 4 | 2 | 911
Tango (8689) 345 kV | Bee | 4 | 0 | 904
Bus 76026 (76026) 138 kV | Crane | 4 | 4 | 814
Sulphur Springs (1697) 345 kV | Hopkins | 4 | 0 | 767
Cobb (1458) 345 kV | Archer, Clay, Jack | 4 | 2 | 766
Rio Hondo (8319) 138 kV | Cameron, Willacy | 4 | 2 | 766
Black Cat (80124) 138 kV | Matagorda | 4 | 1 | 715
Escondido (8260) 138 kV | Kinney, Maverick | 4 | 0 | 704
Goldthwaite (7070) 138 kV | Mills | 4 | 1 | 697
White River (23922) 345 kV | Dickens, Motley | 4 | 0 | 650
Glidden (7258) 138 kV | Colorado | 4 | 2 | 642
Bruni (8297) 138 kV | Duval, Webb | 4 | 0 | 638
Kopperl (68040) 345 kV | Bosque, Hill, Navarro | 4 | 1 | 632
Parish (44010) 138 kV | Brazoria, Fort Bend | 4 | 0 | 628
Nash (42980) 138 kV | Brazoria, Fort Bend | 4 | 0 | 628
Gulftie (43340) 138 kV | Matagorda, Wharton | 4 | 2 | 623
Ttrsw (11688) 345 kV | Franklin, Lamar | 4 | 4 | 621
Bitter Creek (71050) 345 kV | Nolan | 4 | 4 | 614
Bus 2217 (2217) 345 kV | Ellis | 4 | 0 | 603
Bluff Creek (6216) 138 kV | Nolan, Taylor | 4 | 4 | 564
Zapata (8299) 138 kV | Zapata | 4 | 1 | 557
Pearson (5813) 138 kV | Medina | 4 | 1 | 512
Poetry (2485) 345 kV | Kaufman, Van Zandt | 4 | 0 | 510
LOPENO4A (8957) 138 kV | Starr, Zapata | 4 | 0 | 489
Crandall (2727) 138 kV | Kaufman | 4 | 0 | 467
Kaufman Northwest (2724) 138 kV | Kaufman | 4 | 0 | 467
Lampasas (7064) 138 kV | Lampasas | 4 | 2 | 462
Hondo (5225) 138 kV | Medina | 4 | 0 | 411
Blessing (8121) 138 kV | Matagorda, Wharton | 4 | 1 | 406
Lolita (8125) 138 kV | Jackson, Matagorda, Victoria | 4 | 1 | 405
RAPTOR7A (8673) 345 kV | Goliad | 4 | 0 | 402
Aspermont (6158) 138 kV | Haskell, Stonewall | 4 | 0 | 385
Lynx (60400) 138 kV | Crane, Pecos | 4 | 4 | 363
Hawk Hollow (1768) 138 kV | Lamar, Red River | 4 | 0 | 355
Luling (7224) 138 kV | Caldwell | 4 | 0 | 329
Paint Creek (6161) 138 kV | Haskell | 4 | 0 | 290
Pin Oak (3308) 345 kV | Anderson | 3 | 3 | 3789
Ranger Camp (10049) 345 kV | Mitchell | 3 | 0 | 2891
Yellow Wolf (79007) 345 kV | Leon | 3 | 2 | 2438
DULCE7A (80286) 345 kV | Victoria | 3 | 0 | 2430
Gray (79000) 345 kV | Gray | 3 | 3 | 2121
Naismith (8659) 345 kV | San Patricio | 3 | 1 | 1594
Rock Draw (18668) 345 kV | Crane, Upton | 3 | 0 | 1338
HOWARD_5 (5231) 345 kV | Bexar | 3 | 1 | 1194
Aj Swope (23906) 345 kV | Deaf Smith | 3 | 0 | 1149
Thomas Price (11523) 345 kV | Jack | 3 | 0 | 1129
Bus 170174 (170174) 345 kV | Bastrop | 3 | 3 | 1106
Quarry Field (11188) 345 kV | Ward | 3 | 0 | 1087
Coleto Creek (8162) 138 kV | Goliad | 3 | 1 | 1041
Zoisite (8754) 345 kV | Matagorda | 3 | 3 | 1006
Oklaunion (6100) | Baylor | 3 | 0 | 1004
Bow Wood (76006) 345 kV | Concho, McCulloch | 3 | 2 | 979
King Mountain (76635) 138 kV | Crane, Upton | 3 | 1 | 971
Russell Gap (3348) 345 kV | Brown, Lampasas | 3 | 0 | 919
Bus 3412 (3412) 345 kV | Bell, Falls | 3 | 0 | 908
LAKE_HALL_5 (3403) 345 kV | McLennan | 3 | 1 | 898
Pendulo (60507) 345 kV | Haskell | 3 | 1 | 882
Bernoulli (59907) 345 kV | Glasscock | 3 | 2 | 844
Schneeman Draw (76005) 345 kV | Crockett, Schleicher | 3 | 1 | 841
Bus 11736 (11736) 345 kV | Wise | 3 | 0 | 840
Gauss (60703) 345 kV | Haskell, Knox | 3 | 0 | 838
Moss (1018) 345 kV | Ector | 3 | 0 | 837
Thorndale North (3659) 138 kV | Milam, Williamson | 3 | 0 | 835
Dokmai (80090) 138 kV | Calhoun, Victoria | 3 | 3 | 831
Old Hickory (5323) 345 kV | Jackson, Wilson | 3 | 1 | 811
TNCENTRY1_1 (38431) 138 kV | Pecos | 3 | 3 | 808
PIGCREEK4A (60393) 138 kV | Pecos | 3 | 1 | 808
Garden Villas (42680) 138 kV | Harris | 3 | 0 | 807
Clear Fork (23876) 345 kV | Andrews | 3 | 0 | 805
Gardenale (11157) 345 kV | Andrews | 3 | 0 | 805
Farmersvl (1685) 345 kV | Lamar | 3 | 0 | 800
Corn Trail (11441) 345 kV | Brown, Comanche | 3 | 1 | 786
Holman (9073) 345 kV | Fayette, Wharton | 3 | 1 | 785
Smoky Hill (6104) 345 kV | Haskell | 3 | 2 | 730
Gibson (3706) 345 kV | Milam | 3 | 1 | 701
Meteor (10012) 345 kV | Ector | 3 | 2 | 693
Zenith (44900) 345 kV | Grimes | 3 | 0 | 672
Deely (5110) 138 kV | Bexar | 3 | 0 | 662
Sunglow (78016) 138 kV | Maverick | 3 | 3 | 608
Oasis (43035) 345 kV | Brazoria | 3 | 1 | 607
Mt Enterprise (3116) 345 kV | Nacogdoches, Rusk | 3 | 0 | 604
Chalybe (88337) 345 kV | Cameron | 3 | 3 | 602
Outlaw (3386) 345 kV | Freestone, Navarro | 3 | 1 | 601
Sandow (13429) 345 kV | Milam | 3 | 0 | 591
REDCREEK4A (6442) 138 kV | Tom Green | 3 | 1 | 583
Voss Lake (3751) 345 kV | Milam | 3 | 0 | 569
ELM_MOTT_5 (3406) 345 kV | McLennan | 3 | 1 | 556
Martinez (5294) 138 kV | Bexar | 3 | 1 | 550
Eagle Creek (5132) 138 kV | Wilson | 3 | 1 | 532
Moore (5827) 138 kV | Frio | 3 | 0 | 522
Conoco (8138) 138 kV | Matagorda | 3 | 0 | 515
Graham Ses (1431) 138 kV | Young | 3 | 1 | 514
Rookie (3701) 138 kV | Milam | 3 | 1 | 492
Rio Hondo (8318) 345 kV | Cameron, Willacy | 3 | 0 | 483
Comstock (8683) 138 kV | Val Verde | 3 | 1 | 475
Adamsville (7066) 138 kV | Lampasas | 3 | 2 | 460
Riwood (43150) 138 kV | Brazoria | 3 | 0 | 460
East Bernard (44190) 138 kV | Wharton | 3 | 0 | 459
Hood (363) 138 kV | Hood | 3 | 1 | 455
Friends Ranch (6562) 138 kV | Crockett | 3 | 3 | 451
Groesbeck Main (3634) 138 kV | Limestone | 3 | 0 | 447
La Grulla (8798) 138 kV | Hidalgo, Starr | 3 | 0 | 443
Bus 3159 (3159) | Ellis | 3 | 0 | 432
Paris (1693) 138 kV | Lamar | 3 | 0 | 428
Mcdonald (1333) 138 kV | Glasscock | 3 | 2 | 427
Windsor (165) 138 kV | McLennan | 3 | 1 | 411
Dilley (8212) 138 kV | Dimmit, Frio | 3 | 0 | 411
Allens Creek (1835) 138 kV | Fannin, Lamar | 3 | 0 | 411
Canton (3174) 138 kV | Kaufman, Van Zandt | 3 | 0 | 404
LA PRYOR4A (8008) 138 kV | Zavala | 3 | 1 | 385
Royse (2478) 345 kV | Kaufman, Rockwall | 3 | 1 | 384
TNCENTRY2_1 (38432) 138 kV | Pecos | 3 | 3 | 368
Temple Pecan (3420) 138 kV | Bell, Falls | 3 | 2 | 360
Farmland (79641) 345 kV | Dawson | 3 | 0 | 360
Rosharon (44600) 138 kV | Brazoria | 3 | 0 | 358
Winmil (44531) 138 kV | Brazoria | 3 | 0 | 358
Mustang Prairie (6733) 138 kV | Houston | 3 | 0 | 356
Latexo (6732) 138 kV | Houston | 3 | 0 | 356
Sandy Ranch (2621) 345 kV | Hopkins | 3 | 0 | 351
WEIMAR8 (7254) 138 kV | Colorado | 3 | 1 | 351
Oaks (5713) 138 kV | Atascosa | 3 | 1 | 348
Fayette (7055) 345 kV | Caldwell, Fayette | 3 | 0 | 332
Girvinsw (860) 345 kV | Pecos | 3 | 3 | 317
Austrop (9328) 138 kV | Travis | 3 | 3 | 306
Munday East (6110) 138 kV | Knox | 3 | 3 | 303
Hawk Hollow (11768) 138 kV | Lamar | 3 | 0 | 302
CARBON_8 (3378) 138 kV | Comal, Eastland | 3 | 0 | 300
Long Lake (3280) 138 kV | Freestone | 3 | 0 | 286
Long Lake (3279) 138 kV | Freestone | 3 | 0 | 286
Live Oak (6500) 138 kV | Schleicher | 3 | 1 | 284
Asherton (8283) 138 kV | Dimmit | 3 | 1 | 279
Ash Creek (3473) 138 kV | Hill | 3 | 1 | 262
Talty (6902) 138 kV | Kaufman | 3 | 1 | 238
Pinto Creek (78255) 138 kV | Kinney | 3 | 2 | 226
Hubbard (3515) 138 kV | Hill, Navarro | 3 | 3 | 209
Bus 43110 (43110) 138 kV | Brazoria, Wharton | 3 | 0 | 207
Pruitt (971) 138 kV | Hunt | 3 | 2 | 203
OZARKTRAIL_5 (23901) 345 kV | Swisher | 3 | 3 | 201
Tributary (10119) 138 kV | Howard | 3 | 3 | 200
Bus 31875 (31875) | Wise | 2 | 2 | 2000
Trinidad (3123) 345 kV | Cherokee, Kaufman | 2 | 0 | 1576
Bus 1873 (1873) 345 kV | Parker | 2 | 0 | 1500
Jewett (3391) 345 kV | Freestone | 2 | 0 | 1496
Morgan Creek (1030) 345 kV | Mitchell | 2 | 0 | 1434
TNCOWPEN__3 (38044) 345 kV | Reeves | 2 | 2 | 1233
Kirchhoff (60707) 345 kV | Jones, Stonewall | 2 | 0 | 1207
Redland (3321) 345 kV | Angelina | 2 | 2 | 1200
Hungerford (44150) 138 kV | Wharton | 2 | 0 | 1158
Bus 7310 (7310) 138 kV | Bastrop | 2 | 2 | 1106
Bus 44920 (44920) 345 kV | Grimes | 2 | 2 | 996
Triada (8718) 345 kV | Webb | 2 | 2 | 986
King Mountain (842) 345 kV | Upton | 2 | 2 | 983
DRYLAKE_5 (18723) 345 kV | Reeves | 2 | 0 | 983
TNFAULKNER3 (38125) 345 kV | Reeves | 2 | 0 | 983
Bus 2249 (2249) 345 kV | Ellis | 2 | 0 | 919
Mw Pun (1800) 345 kV | Deaf Smith | 2 | 0 | 891
Crane (76615) 138 kV | Crane | 2 | 0 | 821
Twelvemile (76008) 345 kV | Upton | 2 | 2 | 798
Quasar (60712) 345 kV | Haskell, Knox | 2 | 0 | 705
NEBULA7A (60011) 345 kV | Scurry | 2 | 2 | 677
Bus 12677 (12677) 138 kV | Grayson | 2 | 0 | 671
Roans Prairie (40600) 345 kV | Grimes | 2 | 2 | 667
Peters (46220) 138 kV | Austin, Harris | 2 | 1 | 662
Marion (7044) 345 kV | Guadalupe | 2 | 2 | 660
SOLSTICE4A (60385) 138 kV | Pecos | 2 | 0 | 657
Perigee (60791) 345 kV | Knox | 2 | 0 | 654
Woodhouse (38308) 138 kV | Pecos | 2 | 0 | 653
Kilby (60089) 345 kV | Haskell | 2 | 2 | 643
Bus 68005 (68005) 345 kV | Callahan | 2 | 0 | 608
Coyanosa (1239) 138 kV | Pecos, Ward | 2 | 0 | 605
Blair Lake (11238) 138 kV | Pecos, Ward | 2 | 0 | 605
Edinb (8905) 345 kV | Brooks, Zapata | 2 | 0 | 603
POSSUMTROT_5 (3791) | McLennan | 2 | 0 | 601
Bus 11048 (11048) 345 kV | Scurry | 2 | 0 | 568
Bus 11318 (11318) 345 kV | Scurry | 2 | 0 | 568
Tiger Creek (3379) 345 kV | McLennan | 2 | 2 | 559
Bus 8579 (8579) | San Patricio | 2 | 2 | 558
Saragosa (60716) 138 kV | Reeves | 2 | 2 | 545
Cebolla (8601) 345 kV | Kenedy | 2 | 0 | 536
Rockhound (10062) 345 kV | Howard | 2 | 0 | 515
FULSHR_S25_8 (44750) 138 kV | Waller | 2 | 0 | 512
TWINWD_S25_8 (44860) 138 kV | Waller | 2 | 0 | 512
Midland County (1185) 345 kV | Ector, Midland | 2 | 0 | 511
Spring (684) 138 kV | Cooke, Denton | 2 | 1 | 511
Ratsnake (3399) 345 kV | Falls | 2 | 0 | 508
Bellville North (7287) 138 kV | Austin | 2 | 1 | 508
Champion Creek (1414) 345 kV | Mitchell, Nolan | 2 | 1 | 507
BKR (4920) 345 kV | Ellis | 2 | 0 | 504
Commerce (1816) 138 kV | Hunt | 2 | 1 | 482
Hickory Forest (7225) 138 kV | Guadalupe | 2 | 2 | 472
Beecher (8721) 138 kV | Victoria | 2 | 1 | 469
Lcra Bremen (7271) 138 kV | Austin | 2 | 2 | 461
Cisco (6317) 138 kV | Eastland | 2 | 0 | 459
MTNBRANCH_8 (3545) 138 kV | Eastland | 2 | 0 | 459
Sweeny Co (110505) 138 kV | Brazoria | 2 | 0 | 459
Rising Star (33285) 138 kV | Eastland | 2 | 2 | 457
MCKENZIE4A (8858) 138 kV | Nueces | 2 | 2 | 455
RICHLND2_5 (3133) 345 kV | Freestone | 2 | 0 | 452
Atascocita (40130) 138 kV | Harris | 2 | 0 | 452
Cowpen (38043) 138 kV | Reeves | 2 | 0 | 449
Bus 8695 (8695) 138 kV | Duval | 2 | 0 | 437
Noelke (7053) 345 kV | Crockett | 2 | 1 | 415
Short Grass (11525) 138 kV | Young | 2 | 0 | 409
Tradinghouse Ses (13405) 345 kV | McLennan | 2 | 0 | 405
BENJ4A (6088) 138 kV | King, Knox | 2 | 1 | 405
Pleasant Valley (1450) 138 kV | Wichita | 2 | 0 | 404
Bus 78118 (78118) 138 kV | Colorado | 2 | 0 | 403
Dyemound (741) 138 kV | Montague | 2 | 2 | 403
Holiday Tnp (38455) 138 kV | Pecos | 2 | 0 | 402
Soaptree Tnp (38450) 138 kV | Pecos | 2 | 0 | 402
Pearsall (5895) 138 kV | Frio | 2 | 0 | 402
TRIBUTE4A (60008) 138 kV | Tom Green | 2 | 0 | 402
Lytton (9075) 138 kV | Caldwell | 2 | 2 | 402
MUSTANG_8 (1167) 138 kV | Dawson | 2 | 0 | 402
DILLION_P8 (11206) 138 kV | Dawson | 2 | 0 | 402
Fowlerton (5705) 138 kV | La Salle | 2 | 2 | 400
Bus 5506 (5506) 138 kV | Victoria | 2 | 0 | 391
Bus 5584 (5584) 138 kV | Victoria | 2 | 0 | 391
Bus 23833 (23833) 138 kV | Howard, Mitchell | 2 | 0 | 386
Vosslake (3750) 138 kV | Milam | 2 | 0 | 382
Buckholts (3749) 138 kV | Milam | 2 | 0 | 382
Bus 5155 (5155) 138 kV | Wilson | 2 | 0 | 376
Corral (60389) 138 kV | Val Verde | 2 | 0 | 372
Old Monticello (1794) | Franklin | 2 | 2 | 367
Dyann (42985) 138 kV | Wharton | 2 | 0 | 366
Hastings (39010) 138 kV | Brazoria | 2 | 1 | 361
Leon Creek (5260) 138 kV | Bexar | 2 | 1 | 360
Grelton (59901) 345 kV | Martin, Midland | 2 | 1 | 357
Heights (38740) 138 kV | Galveston | 2 | 2 | 355
JAVELINA4A (8475) 138 kV | Nueces | 2 | 2 | 351
San Saba (77074) 138 kV | Mills | 2 | 0 | 340
Cavazos (80229) 138 kV | Cameron | 2 | 1 | 334
Bus 8118 (8118) 138 kV | Victoria | 2 | 0 | 332
MONTFTSS__8 (3454) 138 kV | Navarro | 2 | 2 | 326
Wichita Falls (1464) 138 kV | Wichita | 2 | 0 | 317
TNCOYOTSPG1 (38113) 138 kV | Reeves | 2 | 2 | 314
CHOCBAYU4A (80064) 138 kV | Victoria | 2 | 2 | 309
Haney (40790) 138 kV | Harris | 2 | 0 | 309
Tuleta (8590) 138 kV | Bee, Goliad | 2 | 1 | 308
Bus 8186 (8186) | Karnes | 2 | 0 | 308
Bus 8153 (8153) | Karnes | 2 | 0 | 308
Badger (3761) 345 kV | Milam | 2 | 0 | 307
Danevang (5546) 138 kV | Wharton | 2 | 1 | 306
Cangrejo (8723) 138 kV | Calhoun, Victoria | 2 | 1 | 306
Ho Clarke (47150) 138 kV | Harris | 2 | 2 | 305
NEDIN4A (8380) 138 kV | Hidalgo | 2 | 0 | 302
Nacogdoches (3119) 345 kV | Nacogdoches | 2 | 0 | 302
Roma (8796) 138 kV | Starr | 2 | 1 | 300
Hendrick (60387) 138 kV | Jones | 2 | 2 | 300
L_GILLES8_1Y (7132) 138 kV | Gillespie | 2 | 0 | 300
L_FERGUS8_1Y (7126) 138 kV | Gillespie | 2 | 0 | 300
Odessa (11028) 345 kV | Midland, Upton | 2 | 0 | 292
Yucca (1009) 138 kV | Ward | 2 | 0 | 291
Sand Tank (11197) 138 kV | Ward | 2 | 0 | 291
La Palma (8317) 345 kV | Cameron | 2 | 0 | 284
ENLOE T8 (11806) 138 kV | Delta, Lamar | 2 | 0 | 281
Yates (445) 138 kV | Hill | 2 | 0 | 276
Covington (444) 138 kV | Hill | 2 | 0 | 276
Bus 285 (285) 138 kV | Eastland | 2 | 0 | 275
Bus 289 (289) 138 kV | Eastland | 2 | 0 | 275
Tennessee Colony (3281) 138 kV | Anderson | 2 | 0 | 270
Blackfoot (3499) 138 kV | Anderson | 2 | 0 | 270
Chalmers (8750) 138 kV | Wharton | 2 | 0 | 267
Lane City (8127) 138 kV | Wharton | 2 | 0 | 267
ROSE HILL_RC (6894) 138 kV | Kaufman | 2 | 1 | 261
BALE_S5 (3711) 345 kV | Falls | 2 | 1 | 259
Luna (8656) 138 kV | Cameron, Hidalgo | 2 | 1 | 257
Rivercrest Ses (1780) 138 kV | Red River | 2 | 0 | 255
Closner (8029) 138 kV | Hidalgo | 2 | 1 | 255
Abbybend (350) 138 kV | Hood | 2 | 0 | 253
Zenaida (80043) 138 kV | Duval | 2 | 2 | 248
Sheridan (57639) 138 kV | Colorado | 2 | 0 | 247
Miracle Lake (5700) 138 kV | Atascosa | 2 | 2 | 245
Edna (5522) 69 kV | Jackson | 2 | 0 | 245
El Toro (5518) 69 kV | Jackson | 2 | 0 | 245
MEXIA_2_1_8 (3632) 138 kV | Limestone | 2 | 0 | 243
Goodwin (8355) 138 kV | Hidalgo | 2 | 0 | 243
Heartland (60386) 69 kV | McCulloch, Menard | 2 | 1 | 242
Dimmit (78281) 138 kV | Dimmit | 2 | 0 | 230
Conoco Chittam (8274) 138 kV | Dimmit | 2 | 0 | 230
Alamitto Creek (6680) 138 kV | Brewster | 2 | 0 | 229
Hayter Ranch (60444) 138 kV | Brewster | 2 | 0 | 229
Explorer (6833) 138 kV | Van Zandt | 2 | 1 | 223
Bus 1700 (1700) 138 kV | Lamar | 2 | 0 | 223
BIGSPRIG_8 (1322) 138 kV | Howard | 2 | 0 | 223
Nelson Sharpe (85000) 345 kV | Nueces | 2 | 2 | 220
Bus 1833 (1833) 138 kV | Lamar | 2 | 0 | 219
Blue (44060) 345 kV | Wharton | 2 | 2 | 219
Voltage (78520) 138 kV | Colorado | 2 | 1 | 212
Mcgregor (161) 138 kV | McLennan | 2 | 0 | 210
Rwmiller (331) 138 kV | Palo Pinto | 2 | 0 | 209
Jaybird (320) 138 kV | Palo Pinto | 2 | 0 | 209
Haisley (8920) 138 kV | San Patricio | 2 | 2 | 208
Union (18555) 138 kV | Scurry | 2 | 1 | 205
Holmes (47210) 138 kV | Harris | 2 | 0 | 204
Bus 3181 (3181) 138 kV | Van Zandt | 2 | 0 | 204
Buffalo (23837) 138 kV | Howard, Martin | 2 | 2 | 204
Revilla (8004) 138 kV | Zapata | 2 | 2 | 204
Mykawa (42750) 138 kV | Brazoria, Harris | 2 | 1 | 203
WOLFSS_8 (1013) 138 kV | Ector | 2 | 0 | 203
SANDHLTA_8 (1103) 138 kV | Ector | 2 | 0 | 203
Laquinta (80439) 138 kV | Webb | 2 | 0 | 201
Shawpd (18664) 138 kV | Glasscock, Midland | 2 | 1 | 201
Blackburn (3325) 138 kV | Anderson | 2 | 0 | 201
Palestine (3272) 138 kV | Anderson | 2 | 0 | 201
Bus 7252 (7252) 138 kV | Colorado | 2 | 0 | 200
Castillo (76040) 138 kV | Upton | 2 | 2 | 190
Bus 8009 (8009) 138 kV | Zavala | 2 | 0 | 185
Odlasw (7425) 138 kV | Kinney | 2 | 2 | 181
Charter (8156) 138 kV | Live Oak | 2 | 2 | 181
TNSTAGHORN1 (37990) 138 kV | Ward | 2 | 2 | 180
Baez (8629) 69 kV | Bee | 2 | 2 | 178
North Mercedes (8358) 138 kV | Hidalgo | 2 | 1 | 175
Burnet (7100) 138 kV | Burnet | 2 | 0 | 167
Pruitt (977) 138 kV | Hunt | 2 | 1 | 155
ILLN4A (6564) 138 kV | Crockett | 2 | 2 | 154
Bus 1660 (1660) 138 kV | Stephens | 2 | 0 | 153
Bus 1613 (1613) 138 kV | Stephens | 2 | 0 | 153
Putnam (6310) 138 kV | Eastland | 2 | 0 | 150
LAKECR1 (3409) 345 kV | Falls | 2 | 0 | 145
Roma (8795) 138 kV | Starr | 2 | 2 | 137
Santiago (6490) 138 kV | Schleicher | 2 | 0 | 134
Hornsby (7047) 138 kV | Travis | 2 | 2 | 133
Schroeder (5678) 69 kV | Goliad | 2 | 0 | 133
Big Oak (5675) 69 kV | Goliad | 2 | 0 | 133
Deer Creek (7595) 138 kV | Gonzales | 2 | 0 | 128
Nixon (7621) 138 kV | Gonzales | 2 | 0 | 128
BRIAR_CRK_8 (3472) 138 kV | Navarro | 2 | 0 | 126
POWELL1_8 (3467) 138 kV | Navarro | 2 | 0 | 126
Ben Bolt (5653) 69 kV | Jim Wells | 2 | 2 | 123
Holt (1141) 138 kV | Ector | 2 | 2 | 112
Bus 6835 (6835) 138 kV | Delta | 2 | 0 | 111
Bus 6834 (6834) 138 kV | Delta | 2 | 0 | 111
Charlotte (8206) 69 kV | Atascosa | 2 | 0 | 102
Jourdanton (8607) 69 kV | Atascosa | 2 | 0 | 102
Bus 5718 (5718) 138 kV | Atascosa | 2 | 0 | 101
Pin Oak (3510) 138 kV | Freestone | 2 | 2 | 100
Bus 43380 (43380) 138 kV | Brazoria | 2 | 0 | 100
San Diego (5654) 69 kV | Jim Wells | 2 | 0 | 92
Orange Grove (5658) 69 kV | Jim Wells | 2 | 0 | 92
Nbatesville (5836) 69 kV | Zavala | 2 | 0 | 82
Leona (5822) 69 kV | Zavala | 2 | 0 | 82
West George (5690) 69 kV | Live Oak | 2 | 2 | 82
Tn White (38430) 138 kV | Pecos | 2 | 2 | 77
Bus 1785 (1785) 69 kV | Red River | 2 | 0 | 75
Bus 11784 (11784) 69 kV | Red River | 2 | 0 | 75
Vernon (6060) 138 kV | Wilbarger | 2 | 2 | 75
Brundage (5870) 69 kV | Dimmit | 2 | 0 | 72
Big Wells (5868) 69 kV | Dimmit | 2 | 0 | 72
Bus 8107 (8107) 69 kV | Bee | 2 | 2 | 61
Groesbeck (3588) 69 kV | Falls | 2 | 0 | 61
Otto Junction (3637) 69 kV | Falls | 2 | 0 | 61
Uvalde (5823) 69 kV | Uvalde | 2 | 0 | 42
Uvalde (5820) 69 kV | Uvalde | 2 | 0 | 42
Midlothian Anp (1940) 345 kV | Ellis | 2 | 2 | 36
Rionog (5362) 345 kV | Guadalupe | 2 | 2 | 6
BYNUM_5 (3383) 345 kV | Ellis | 2 | 0 | 3
Clute (42050) 138 kV | Brazoria | 2 | 0 | 0

## Slipping schedules
INR | Request | County | Type | MW | Target COD
18INR0073 | Sweetwater 1 repower | Nolan | Wind | 3 | 2024-11-30
23INR0015 | Scarlet Solar | Castro | Solar | 180 | 2025-08-26
24INR0003 | Stem Solar | Swisher | Solar | 200 | 2025-08-26
23INR0104 | BRP Kamet BESS | Andrews | Battery storage | 202.46 | 2025-12-01
19INR0189 | SP TX-12B Phase III | Upton | Solar | 40 | 2025-12-02
25INR0688 | Giga Texas Data Center | Travis | Battery storage | 133 | 2025-12-15
23INR0009 | Shaula III Solar | DeWitt | Solar | 205.2 | 2025-12-24
21INR0509 | McClure Solar | Palo Pinto | Solar | 105.73 | 2025-12-31
25INR0378 | Second Division Storage | Brazoria | Battery storage | 0 | 2025-12-31
26INR0297 | Buzzi Maryneal Wind Project | Nolan | Wind | 18 | 2026-01-02
22INR0215 | TEXAS SOLAR NOVA 3 | Kent | Solar | 200.2 | 2026-01-31
26INR0004 | GRIMES SOLAR | Grimes | Solar | 153.45 | 2026-02-15
22INR0546 | Enchanted Rock NEWPP | Harris | Gas engines | 30 | 2026-02-28
23INR0464 | Sloan Storage | Henderson | Battery storage | 200.9 | 2026-03-27
24INR0645 | COYOTE SPRINGS AGR1 | Reeves | Oil | 9.95 | 2026-06-23
24INR0646 | SADDLEBACK AGR1 | Reeves | Oil | 9.95 | 2026-06-23
22INR0301 | Fortuna Wind | Jack | Wind | 295.3 | 2026-07-01
26INR0630 | Betel Storage I | Milam | Battery storage | 500 | 2026-08-12
23INR0487 | Brightside Solar Alt POI | Live Oak | Solar | 50 | 2026-08-14
24INR0238 | Appaloosa Run BESS | Upton | Battery storage | 103 | 2026-08-30
25INR0515 | Fagus Storage SLF | Childress | Battery storage | 0 | 2026-09-01

## All active requests
inr | name | developer_as_listed | county | tech | mw | poi | target_cod | ia_signed | security_and_ntp | energized | synchronized | stage | change_this_month
22INR0541 | ALWEST BESS | Castleman Power | Anderson | Battery storage | 208.63 | 3114 Paltalco 138kV | 2028-04-19 |  |  |  |  | In study
25INR0432 | Brotherton Storage | BT Brotherton Storage, LLC | Anderson | Battery storage | 176.13 | 6937 Tucker Sub 138kV | 2027-05-01 | 2024-08-06 | True |  |  | Signed; security posted
24INR0450 | Lumen Farm BESS SLF | Neches Solar, LLC | Anderson | Battery storage | 0 | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | 2028-09-30 |  |  |  |  | In study
23INR0439 | Lumen Farm Solar SLF | Neches Solar, LLC | Anderson | Solar | 201.04 | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | 2028-09-30 |  |  |  |  | In study
32INR0003 | Mule Deer Run Gas | Anderson Energy Center, LLC | Anderson | Gas combined cycle | 1263 | #3308 Pin Oak 345KV | 2031-07-01 |  |  |  |  | In study
31INR0021 | Mule Deer Run Gas II | Anderson Energy Center, LLC | Anderson | Gas combined cycle | 1263 | #3308 Pin Oak 345KV | 2032-07-01 |  |  |  |  | In study
31INR0022 | Mule Deer Run Gas III | Anderson Energy Center, LLC | Anderson | Gas combined cycle | 1263 | #3308 Pin Oak 345KV | 2032-07-01 |  |  |  |  | In study
28INR0094 | Pham BESS | ASB1, LLC | Anderson | Battery storage | 132.98 | Tap 138kV 3281 TENNCLNY_8 - 3499 BLACKFTAP_8 | 2028-09-18 | 2026-07-31 | True |  |  | Signed; security posted
23INR0289 | Skull Creek Solar | Skull Creek Solar, LLC | Anderson | Solar | 136.98 | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot Massey Lake Switch in TSP’s Pin Oak Switch - Long Lake Substation | 2027-06-30 | 2024-05-20 |  |  |  | Signed
22INR0427 | BRP Kabru BESS | BRP Kabru BESS LLC | Andrews | Battery storage | 202.45 | 1159 Andrew North - 11284 Blackbird 138kV | 2028-12-01 |  |  |  |  | In study
23INR0104 | BRP Kamet BESS | BRP Kamet BESS LLC | Andrews | Battery storage | 202.46 | Andrews North – McKenzie Draw Switch 138 kV | 2025-12-01 |  |  |  |  | In study
30INR0135 | Blue Sage Wind | CPV Blue Sage Wind, LLC | Andrews | Wind | 394.54 | BUS #11270 - DOGHOUSE_5 - THE DOGHOUSE 345kV SUBSTATION | 2030-04-23 |  |  |  |  | In study
19INR0103 | Rodeo Solar | Core Solar SPV I, LLC | Andrews | Solar | 200 | 138kV 11273 NELSON SWITCH | 2026-11-30 | 2019-08-20 | True |  |  | Signed; security posted
27INR0385 | Straight Spur Solar | ENGIE IR Holdings LLC | Andrews | Solar | 251.8 | Tap 345 kV ClearFork (Bus #23876) to Gardenale Switch (Bus #11157) | 2029-04-01 |  |  |  |  | In study
27INR0386 | Straight Spur Storage | ENGIE IR Holdings LLC | Andrews | Battery storage | 306.2 | Tap 345kV ClearFork( Bus # 23876) to Gardenale Switch (Bus # 11157) | 2029-04-01 |  |  |  |  | In study
27INR0384 | Straight Spur Wind | ENGIE IR Holdings LLC | Andrews | Wind | 247.4 | Tap 345 kV 23876 Clear Fork -11157 Gardenale Switch | 2029-04-01 |  |  |  |  | In study
23INR0279 | Trivor BESS | BRP Trivor BESS LLC | Andrews | Battery storage | 205.46 | 1272 Fullerton 138kV | 2028-03-01 |  |  |  |  | In study
23INR0278 | Tucana BESS | BRP Tucana BESS LLC | Andrews | Battery storage | 201.3 | 1157 Andrews County South 138kV | 2028-03-01 |  |  |  |  | In study
19INR0110 | Azalea Springs Solar | AZALEA SPRINGS SOLAR PARK LLC | Angelina | Solar | 181 | tap 138kV Jim English – Lufkin Chipper Mill | 2026-11-01 | 2023-09-14 | True | 2025-01-29 | 2025-02-11 | Approved for synchronization
30INR0114 | Longleaf II Power Station | WattBridge Texas Holdings, LLC | Angelina | Gas turbine | 600 | 3321 Redland 345 kV | 2030-07-01 |  |  |  |  | In study
26INR0294 | Longleaf Power Station | WattBridge Texas Holdings, LLC | Angelina | Gas turbine | 600 | Redland Substation (# 3321) | 2029-03-31 |  |  |  |  | In study
24INR0174 | Solar Star North Herty Storage | Solar Star North Herty Storage, LLC | Angelina | Battery storage | 125.9 | 3307 Redland Switch 138 kV | 2027-08-25 |  |  |  |  | In study
27INR0247 | Sun Angel ESS | Sun Angel ESS LLC | Angelina | Battery storage | 201.54 | Tap 138kV LUFKINE East (#3326) - HERTY TAP (#3318) | 2028-09-21 |  |  |  |  | In study
25INR0616 | Bobcat Bluff Storage SLF | Cub Storage LLC | Archer | Battery storage | 0 | 1475 Windthorst 138 kV | 2027-04-15 | 2026-01-12 |  |  |  | Signed
27INR0279 | Red Hollow Renewable Energy BESS SLF | Red Hollow Renewable Energy LLC | Archer | Battery storage | 0 | Tap 345kV 1422 Bowman - 17002 Garvey Road | 2029-04-19 |  |  |  |  | In study
28INR0088 | Red Hollow Renewable Energy Solar SLF | Red Hollow Renewable Energy LLC | Archer | Solar | 308.61 | Tap 345kV (Bus# 1422) Bowman - (Bus# 17002) Garvey Road | 2029-04-19 |  |  |  |  | In study
28INR0348 | Ringtail Energy Storage | PowerPulse LLC | Archer | Battery storage | 203.8 | Bus # 1446, Lake Wichita, 138 kV | 2028-12-15 |  |  |  |  | In study
25INR0583 | Shannon Wind Repower | Shannon Wind, LLC | Archer | Wind | 18.52 | 1458 Cobb Switching Station 345 kV | 2027-09-15 |  |  |  |  | In study
26INR0295 | Trinity Hills BESS SLF | Phoenix Battery Storage, LLC | Archer | Battery storage | 94 | To the 345 kV Garvey Road Switch (#17002) | 2028-01-24 |  |  |  |  | In study
25INR0628 | Wichita Falls Energy Storage | Wichita Falls Energy Storage LLC | Archer | Battery storage | 202 | Tap 345kV 1422 Bowman - 1458 Cobb Switch | 2028-08-01 |  |  |  |  | In study
28INR0215 | Complex Serenity Wind | Serenity Wind, LLC | Armstrong | Wind | 971 | Double tap 345 kV Alibates (bus# 23900) to Tule Canyon (bus# 23914) and Tule Canyon (bus# 23914) to Midpoint Switch (bus# 23931) | 2029-04-16 |  |  |  |  | In study
23INR0637 | Goodnight Wind II | FGE Goodnight II, LLC | Armstrong | Wind | 261.1 | tap 345kV 23900 Alibates - 23914 Tule Canyon CKT2 | 2027-06-06 | 2019-08-18 | True |  |  | Signed; security posted
27INR0443 | Serenity Wind | Serenity Wind, LLC | Armstrong | Wind | 473 | 23931 MIDPOINT SWITCH 345 kV | 2028-09-18 |  |  |  |  | In study
25INR0587 | Zeus Armstrong BESS | Armstrong BESS, LLC | Armstrong | Battery storage | 1043.08 | Tap 345KV 23900 ALIBATES - 23914 TULECNYN CKT1 & CKT2 | 2028-04-17 |  |  |  |  | In study
25INR0586 | Zeus Armstrong Solar | Armstrong Solar, LLC | Armstrong | Solar | 503.56 | Tap 345KV 23900 AlLIBATES -23914 TULECNYN | 2028-04-17 |  |  |  |  | In study
29INR0050 | Amphion Solar Phase 1 | Amphion Solar, LLC | Atascosa | Solar | 180.6 | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt FOWRTN_SMIGL2 | 2028-09-01 |  |  |  |  | In study
28INR0343 | Amphion Solar Phase 2 | Amphion Solar, LLC | Atascosa | Solar | 205.9 | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | 2029-05-15 |  |  |  |  | In study
28INR0344 | Amphion Solar Phase 3 | Amphion Solar, LLC | Atascosa | Solar | 115.4 | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | 2029-11-15 |  |  |  |  | In study
29INR0214 | Amphion Storage | Amphion Solar, LLC | Atascosa | Battery storage | 200 | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | 2029-05-15 |  |  |  |  | In study
27INR0396 | Bluewind BESS | Bluewind Energy Center, LLC | Atascosa | Battery storage | 246.5 | 5713 Oaks Substation 138kV | 2029-07-02 |  |  |  |  | In study
21INR0391 | Grandslam Solar | Grandslam Solar, L.L.C. | Atascosa | Solar | 121.89 | 5700 Miracle Lake 138kV | 2027-10-01 | 2021-01-29 |  |  |  | Signed
26INR0654 | Great Hambino BESS | Atascosa BESS, LLC | Atascosa | Battery storage | 122.98 | #5700 Miracle Lake Substation 138kV | 2028-10-01 |  |  |  |  | In study
27INR0305 | Kurtz Solar SLF | Kurtz Solar, LLC | Atascosa | Solar | 101.9 | Tap 69kV #8206 Charlotte - #8607 Jourdanton | 2029-05-31 |  |  |  |  | In study
27INR0306 | Kurtz Storage SLF | Kurtz Storage, LLC | Atascosa | Battery storage | 0 | Tap 69kV #8206 Charlotte - #8607 Jourdanton | 2029-05-31 |  |  |  |  | In study
28INR0463 | Mutz Solar | AETS Development Holdings LLC | Atascosa | Solar | 72.82 | Tap 69 kV 5693 San Miguel Tap - 5698 North Calliham Sub | 2028-06-30 |  |  |  |  | In study
23INR0200 | Paradiso BESS | VESI 13 | Atascosa | Battery storage | 102.3 | 8203 Pleasanton 138kV | 2028-03-15 | 2025-04-18 | True |  |  | Signed; security posted
25INR0082 | Reis Solar | Greenalia Solar Power Reis LLC | Atascosa | Solar | 105.48 | Tapping into 138 kV line (5689) Choke Canyon AEP to (5902) San Miguel Gen | 2027-08-03 |  |  |  |  | In study
28INR0209 | Strawberry Dunes BESS SLF | Strawberry Dunes LLC | Atascosa | Battery storage | 0 | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | 2028-06-30 |  |  |  |  | In study
28INR0208 | Strawberry Dunes Solar SLF | Strawberry Dunes LLC | Atascosa | Solar | 101.1 | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | 2028-06-30 |  |  |  |  | In study
28INR0265 | Agricola BESS | Agricola BESS LLC | Austin | Battery storage | 205.2 | Tap 138kV GEBHARDT (#44700) - Wallis (#44740) | 2029-05-31 |  |  |  |  | In study
26INR0427 | BremRaek BESS | BremRaek BESS | Austin | Battery storage | 200.6 | 7271 LCRA New Bremen 138 kV | 2027-11-14 |  |  |  |  | In study
28INR0089 | EmberYork | EmberYork Energy Center | Austin | Gas turbine | 900 | TAP 138kV WALLIS 44740 - GERBHRT 44700 | 2028-01-01 | 2025-12-12 |  |  |  | Signed
29INR0041 | Homestead Power (TEF-Due Diligence) | Homestead Power LLC | Austin | Gas turbine | 260.3 | 138 kV New Bremen #7271 | 2029-12-15 |  |  |  |  | In study
26INR0229 | Pamplona Solar | Karol Solar III | Austin | Solar | 42.38 | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | 2028-10-17 |  |  |  |  | In study
28INR0226 | Pamplona Storage | Karol Solar V | Austin | Battery storage | 153.88 | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | 2028-10-17 |  |  |  |  | In study
27INR0252 | Parula Energy Center | Parula Energy Center | Austin | Battery storage | 250.95 | 7287 Bellville North 138kV | 2029-06-18 |  |  |  |  | In study
26INR0410 | Prost ESS | Prost ESS LLC | Austin | Battery storage | 202.7 | Tap 138kV L_PISEK_8_1Y (#7296) - L_WELCOM8_1Y(#7577) | 2028-09-08 |  |  |  |  | In study
28INR0186 | Saddlehorn Energy Storage | Saddlehorn Energy Storage, LLC | Austin | Battery storage | 256.8 | Tap 138kV 7287 Bellville North - 7291 Highway 36 | 2028-11-01 |  |  |  |  | In study
26INR0519 | Sky Global West Houston | Sky Global Power Two, LLC | Austin | Gas engines | 324.58 | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | 2028-06-01 | 2025-03-25 |  |  |  | Signed
28INR0061 | Sunrose Renewable Energy Solar SLF | Sunrose Renewable Energy LLC | Austin | Solar | 309.88 | Tap 138kV #44740 WALLIS - #44700 GEBHRT | 2029-07-04 |  |  |  |  | In study
28INR0066 | Sunrose Renewable Energy Storage SLF | Sunrose Renewable Energy LLC | Austin | Battery storage | 0 | Tap 138kV 44740 WALLIS - 44700 GEBHRT | 2029-07-04 |  |  |  |  | In study
26INR0466 | Symphony BESS | Symphony BESS, LLC | Austin | Battery storage | 612 | 46220 PETERS | 2028-07-01 |  |  |  |  | In study
26INR0774 | Wallis BESS2 | Denali Energy Storage LLC | Austin | Battery storage | 9.9 | TSP Substation Name - Wallis TSP Substation Code - WA Load Name/Load Transformer Name - TR4 Bus # / PTI Bus Number: 44740 Voltage (Transmission level kV) - 138 kV Node (associated w/ load/load XFMR in NMMS) - TR4 | 2027-02-22 | 2024-12-11 | True |  |  | Signed; security posted
24INR0502 | Medina City BESS | Regis Medina, LLC | Bandera | Battery storage | 9.99 | Station Name (TDSP Station Code): MEDINA; Load/Load Transformer Name: L_MEDICI9_1Y; PTI BUS number: 7430; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 12.47kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | 2026-11-26 | 2023-01-18 | True | 2026-07-16 | 2026-07-29 | Approved for synchronization
26INR0194 | Motif BESS II | Motif Storage, LLC | Bandera | Battery storage | 201.13 | 7440 Tarpley 138kV | 2029-02-19 |  |  |  |  | In study
23INR0078 | Shaw Solar | Rio Lago Solar, LLC | Bandera | Solar | 124.65 | Tap 138kV 7146 Verde Creek - 7438 Bandera | 2026-10-16 | 2023-02-17 | True | 2026-06-04 | 2026-07-31 | Approved for synchronization
26INR0261 | Bastrop Peaking Generators (TEF-Due Diligence) | MPH Bastrop Peakers, LLC | Bastrop | Gas turbine | 1104 | 7048 L_GARFIE5_1Y 345kV | 2027-12-07 | 2025-12-19 |  |  |  | Signed
26INR0560 | Fort Worth Power Core Bastrop Gas Plant | Fort Worth Power Core LLC | Bastrop | Gas combined cycle | 506.38 | Tap 345kV 7042 ZORN - 7040 AUSTROP | 2029-09-28 |  |  |  |  | In study
29INR0166 | LOST PINES GAS RECIP | LCRA | Bastrop | Gas engines | 113.02 | (#170174) LOST PINES 345 kV | 2033-06-01 | 2025-12-26 |  |  |  | Signed
31INR0010 | LOST PINES GAS RECIP PHASE 2 | LCRA | Bastrop | Gas engines | 113.02 | (#170174) LOST PINES 345 kV | 2033-06-01 | 2025-12-26 |  |  |  | Signed
26INR0045 | LUND STORAGE CENTER 1 | Lund Storage Center 1, LLC | Bastrop | Battery storage | 407.55 | TAP 138 KV LINE AND CREATE NEW BUS BETWEEN KIMBRO (7337) AND ELGIN SWITCH (3650) | 2029-10-31 |  |  |  |  | In study
26INR0511 | Little Star Solar | RWE Clean Energy Development, LLC | Bastrop | Solar | 61.6 | #9043 CISTERN 345kV | 2027-12-31 |  |  |  |  | In study
30INR0052 | Lost Pines Power Park | LCRA | Bastrop | Gas combined cycle | 880 | (#170174) LOST PINES 345 kV | 2033-06-01 | 2025-12-26 |  |  |  | Signed
31INR0011 | SIM GIDEON GAS RICE | LCRA | Bastrop | Gas engines | 226.03 | (#7310) SIM GIDEON 138 kV | 2031-05-10 | 2025-12-19 |  |  |  | Signed
30INR0051 | Sim Gideon Combined Cycle | LCRA | Bastrop | Gas combined cycle | 880 | (#7310) SIM GIDEON 138 kV | 2030-12-15 | 2025-12-19 |  |  |  | Signed
26INR0514 | Techne BESS | Techne BESS, LLC | Bastrop | Battery storage | 202.7 | 7560 RED ROCK 138kV | 2028-12-31 |  |  |  |  | In study
25INR0447 | Waterloo BESS 1 | Waterloo BESS, LLC | Bastrop | Battery storage | 120 | Tap 345-kV 7040 Austrop to 7042 Zorn | 2028-12-15 | 2024-09-04 |  |  |  | Signed
25INR0422 | Waterloo Solar 1 | Waterloo Solar 1, LLC | Bastrop | Solar | 200.64 | Tap 345-kV 7040 Austrop to 7042 Zorn | 2027-12-01 | 2024-09-04 |  |  |  | Signed
27INR0005 | Dundee East A Wind | Felix 2, LLC | Baylor | Wind | 524 | 345 kV Riley Substation (#6101); AEP | 2027-12-31 | 2025-02-21 | True |  |  | Signed; security posted
27INR0011 | Dundee East B Wind | Felix 2, LLC | Baylor | Wind | 261.45 | 345 kV Riley Substation (#6101); AEP | 2027-12-31 | 2025-02-21 | True |  |  | Signed; security posted
29INR0198 | Velveteen Solar I | Velveteen Solar, LLC | Baylor | Solar | 502.2 | Tap into 6076 FOXTAIL- 6100 OKLAUNION | 2029-10-15 |  |  |  |  | In study
29INR0225 | Velveteen Solar II | Velveteen Solar II, LLC | Baylor | Solar | 300.9 | Tap into 6076 FOXTAIL- 6100 OKLAUNION | 2029-12-15 |  |  |  |  | In study
29INR0226 | Velveteen Solar III | Velveteen Solar III, LLC | Baylor | Solar | 200.7 | Tap into 6076 FOXTAIL- 6100 OKLAUNION | 2029-12-15 |  |  |  |  | In study
28INR0514 | Young Road Solar | reNRG TX 5 LLC | Baylor | Solar | 101.7 | The POI B is TAP 69 KV LINE AND CREATE NEW BUS BETWEENWESTOVER (784) AND LAKE KEMP SWITCH (782) 69 KV SUB STATIONS. | 2028-04-30 |  |  |  |  | In study
27INR0372 | Abeja Solar Farm | Abeja Solar Farm LLC | Bee | Solar | 200.84 | Tap 345kV 8012 PALADIO7A - 8689 TANGO7A | 2029-06-07 | 2025-12-16 |  |  |  | Signed
25INR0060 | Argenta Solar | Charter Oak Solar, LLC | Bee | Solar | 310 | Tap 345kV 8689 Tango - 8606 Goddard | 2028-06-30 | 2024-04-05 | True |  |  | Signed; security posted
25INR0061 | Argenta Storage | Charter Oak Storage, LLC | Bee | Battery storage | 192 | Tap 345kV 8689 Tango - 8606 Goddard | 2028-06-30 | 2024-04-05 | True |  |  | Signed; security posted
26INR0412 | BumbleBee Solar | BumbleBee Solar Farm LLC | Bee | Solar | 200.86 | Tap 345kV 5725 PawneeSW5 - 8689 Tango | 2031-03-01 |  |  |  |  | In study
20INR0129 | Foxtrot Wind | Lincoln Clean | Bee | Wind | 268.2 | AEP 88689 Tango 345kV station | 2026-12-31 | 2020-05-05 | True | 2022-02-23 | 2022-03-09 | Approved for synchronization
22INR0559 | Honeycomb Solar SLF | Honeycomb Solar, LLC | Bee | Solar | 61.4 | 69 kV Tynan Substation (#8107) | 2027-02-27 | 2023-05-01 | True |  |  | Signed; security posted
23INR0392 | Honeycomb Storage SLF | Honeycomb BESS, LLC | Bee | Battery storage | 0 | 69 kV Tynan Substation (#8107) | 2027-05-11 | 2023-05-01 | True |  |  | Signed; security posted
26INR0134 | Myers Solar | BT Myers Solar, LLC | Bee | Solar | 101.59 | 8629 Baez 69 kV | 2028-05-22 |  |  |  |  | In study
26INR0135 | Myers Storage | BT Myers Solar, LLC | Bee | Battery storage | 75.96 | 8629 Baez 69 kV | 2028-05-22 |  |  |  |  | In study
25INR0394 | Orchard Ray BESS | Pettus BESS | Bee | Battery storage | 51.85 | 8590 Tuleta 138kV | 2027-05-01 |  |  |  |  | In study
28INR0485 | Sparta BESS | Sparta Storage Center | Bee | Battery storage | 250.95 | 88690 SPTPOI7A 345kV | 2029-12-31 |  |  |  |  | In study
27INR0083 | Spinner Energy Storage | GCI Wolf Energy Storage, LLC | Bee | Battery storage | 125.63 | 8196 Poesta Substation 138kV | 2029-07-10 |  |  |  |  | In study
26INR0614 | Bell County Leifester Storage | DM-BCRCML, LLC | Bell | Battery storage | 204.82 | Tap 138kV 3428 Killeen South – 13628 Founders Trail Sub | 2029-09-17 |  |  |  |  | In study
26INR0615 | Bell County Morgan Storage | DM-BCTRM, LLC | Bell | Battery storage | 256.27 | To Tap 138 kV Trimmier Substation (Bus# 136) | 2029-12-30 |  |  |  |  | In study
23INR0469 | Big Elm Storage | Big Elm Storage, LLC | Bell | Battery storage | 120 | 3404 Belfalls 345kV | 2028-12-15 | 2024-05-10 | True |  |  | Signed; security posted
25INR0337 | Butcherbird Solar | Butcherbird Solar, LLC | Bell | Solar | 116 | Tap 138 kV - Bell County #133 to Bartlett Switch #114 | 2029-01-31 |  |  |  |  | In study
23INR0070 | Chillingham Solar | Chillingham Solar LLC | Bell | Solar | 352.39 | 3687 Bell County East 345kV | 2026-10-31 | 2022-02-04 | True | 2024-08-19 | 2024-09-04 | Approved for synchronization
25INR0281 | Cosper Solar | Gransolar Texas Twenty LLC | Bell | Solar | 148.16 | Tap 138kV 115 Ding Dong - 3630 Copperas Cove Tu | 2027-11-12 | 2025-07-31 | True |  |  | Signed; security posted
25INR0100 | Goldeneye BESS | Black Mountain Energy Storage II | Bell | Battery storage | 201.6 | 3423 KILLEEN Switch 138 KV | 2028-05-15 | 2024-02-26 |  |  |  | Signed
23INR0344 | Hermes Solar | Bell 1 Solar, LLC | Bell | Solar | 100.36 | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | 2026-06-12 | 2023-11-08 | True | 2026-02-23 | 2026-04-17 | Approved for synchronization
24INR0365 | Hermes Storage | Bell 1 Storage LLC | Bell | Battery storage | 100.42 | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | 2026-08-18 | 2023-11-08 | True | 2026-03-03 | 2026-04-17 | Approved for synchronization
26INR0465 | Lavita BESS | Lavita BESS, LLC | Bell | Battery storage | 606 | Tap 345kV Temple Pecan Creek (3412) - Temple Switch (3414) 345kV ckt 2 | 2028-07-01 |  |  |  |  | In study
23INR0249 | Limewood Solar | Limewood Bell Renewables, LLC | Bell | Solar | 204.6 | 3420 Temple Pecan Creek 138kV | 2026-12-29 | 2023-02-22 | True | 2026-08-10 | 2026-09-15 | Approved for synchronization | Energized -> Approved to connect
23INR0248 | Limewood Storage | Limewood Bell Renewables LLC | Bell | Battery storage | 50 | 3420 Temple Pecan Creek 138kV | 2028-12-29 | 2023-02-22 | True |  |  | Signed; security posted
29INR0206 | Riviera Gas | BKV-BPP Power | Bell | Gas combined cycle | 636.9 | Tap #3414 Temple Switch - #3780 Tower Switch 345kV DCKT Line | 2030-06-14 |  |  |  |  | In study
26INR0330 | Alamo City BESS | ALAMO CITY ESS LLC | Bexar | Battery storage | 128.2 | Tap 138kV 5294 Martinez - 5110 JT Deely | 2027-09-21 | 2025-05-22 |  |  |  | Signed
27INR0294 | Bernice Energy Storage | Bernice Energy Storage LLC | Bexar | Battery storage | 402.8 | 5135 ELMENDORF 138kV | 2029-02-15 |  |  |  |  | In study
26INR0702 | Bexar Martinez BESS | Bexar Martinez LLC | Bexar | Battery storage | 9.99 | TSP Station Name: Martinez TSP Station Code: C5 Load Name / Load Transformer Name: T3 Bus #: PTI Bus Number: 5294 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 0120 | 2027-01-23 | 2026-02-03 | True | 2026-09-15 |  | Approved for energization | Signed; security posted -> Energized
24INR0427 | CPS AvR CT1 Rotor Replacement | CPS Energy | Bexar | Gas combined cycle | 11.3 | 5475 Braunig 345kV | 2026-08-14 |  |  |  | 2023-12-04 | Approved for synchronization
25INR0531 | CPS Energy AvR1CT2 Rotor Replacement | CPS Energy | Bexar | Gas combined cycle | 23.2 | 5475 Braunig 345kV | 2026-08-14 |  |  |  | 2024-11-22 | Approved for synchronization
25INR0346 | Cado Storage | Cado Storage, LLC | Bexar | Battery storage | 205.51 | Tap 138 kV Line from Braunig East (#5030) to Highland Hills (#5205) Ckt. 1 | 2030-06-08 |  |  |  |  | In study
28INR0020 | Caracara Energy Storage Center | FRESH AIR ENERGY II, LLC | Bexar | Battery storage | 203 | Tap 138kV 5055 Cagnon - 5346 Potranco | 2028-08-01 |  |  |  |  | In study
27INR0342 | Dorsey Road BESS | Horizon Energy Storage Greenfield Project Holdings LLC | Bexar | Battery storage | 150.39 | Tap 138 kV Chavanea (5085) - Palo Alto (5330). | 2029-08-31 |  |  |  |  | In study
23INR0207 | El Patrimonio Solar | Heritage Solar, LLC | Bexar | Solar | 152.32 | tap 138kV 5429 Trumbo - 5260 Leon Creek | 2027-04-29 | 2023-12-11 | True |  |  | Signed; security posted
27INR0393 | Ferdinand Grid BESS II | Coval Infrastructure DevCo LLC | Bexar | Battery storage | 208.12 | 5260 Leon Creek 138kV | 2027-12-01 |  |  |  |  | In study
28INR0390 | Horsepower BESS | Horsepower BESS, LLC | Bexar | Battery storage | 257.5 | POI is 138 kV Howard Substation (Bus# 5230) (SSWG bus name: HOWARD), NMMS station code: S1 | 2028-01-31 |  |  |  |  | In study
29INR0173 | Howard Road BESS | Project Fast Flow LLC | Bexar | Battery storage | 617.63 | 5231 HOWARD RD 345 kV | 2028-04-01 |  |  |  |  | In study
23INR0467 | Lavender Storage Project | Lavender Storage Project LLC | Bexar | Battery storage | 231.9 | Tap 138kV Deely (bus 5110) - Laredo (bus 5255) | 2029-09-13 | 2025-06-23 |  |  |  | Signed
24INR0108 | Louisa Energy Storage | VESI 49 LLC | Bexar | Battery storage | 102.77 | 138 kV Helotes (#5200) | 2029-03-12 | 2025-02-27 | True |  |  | Signed; security posted
28INR0474 | Mission Station Energy Storage I | Mission Station LLC | Bexar | Battery storage | 375 | Tap 345kV (Bus #5400) SPRUCE – (Bus #5475) VON_ROSE Ckt 1; | 2030-05-31 |  |  |  |  | In study
28INR0475 | Mission Station Energy Storage II | Mission Station LLC | Bexar | Battery storage | 375 | Tap 345kV (Bus #5400) SPRUCE – (Bus #5231) HOWARD_5 Ckt 1 | 2030-05-31 |  |  |  |  | In study
27INR0082 | Orbit Energy Storage | GCI Orbit Energy Storage, LLC | Bexar | Battery storage | 501.94 | Tap 345 kV Calaveras Power Station (BUS #5400) to VON_ROSE (BUS #5475) | 2027-06-01 |  |  |  |  | In study
27INR0180 | Otter BESS | GRS BESS TEXAS TEN, LLC | Bexar | Battery storage | 157.12 | 5378 SHEPHERD RD 138kV | 2029-09-15 |  |  |  |  | In study
28INR0024 | Padua Grid BESS Unit 3 | Padua Grid 3, LLC | Bexar | Battery storage | 201.35 | Tap #5395 O.W Sommer 138kV | 2026-05-15 | 2025-03-07 | True | 2026-06-12 | 2026-06-22 | Approved for synchronization
22INR0423 | Quela BESS | BRP Quela BESS LLC | Bexar | Battery storage | 301.41 | Tap 138kV 5110 J.T. Deely - 5294 Martinez | 2027-12-01 |  |  |  |  | In study
26INR0331 | RUSH ESS | OCI Solar Power LLC | Bexar | Battery storage | 201.27 | Tap 345 kV 5231 HOWARD_5 – 5400 SPRUCE | 2031-02-08 |  |  |  |  | In study
24INR0392 | Riverwalk BESS | RWE Solar Developement, LLC | Bexar | Battery storage | 120 | 5294 Martinez Substation 138kV | 2027-10-01 | 2026-08-18 |  |  |  | Signed
23INR0479 | Taormina Storage | Taormina Storage Project LLC | Bexar | Battery storage | 231.86 | Tap 138kV VH Braunig (5025) to Valley Road 138kV (5465) | 2029-05-26 | 2025-04-14 | True |  |  | Signed; security posted
26INR0616 | Blanco County Behrends Storage | DM-BCB, LLC | Blanco | Battery storage | 153.62 | #70482 Blanco Substation 138 kV - currently being upgraded | 2029-12-30 |  |  |  |  | In study
27INR0500 | Antila Solar | Antila Solar LLC | Borden | Solar | 500 | #59916 Buck Canyon 345kV | 2027-11-30 | 2025-08-13 | True |  |  | Signed; security posted
27INR0481 | Borden Dino BESS | Borden Dino Solar, LLC | Borden | Battery storage | 60.26 | 59905 FARADAY 345KV | 2028-07-01 |  |  |  |  | In study
27INR0480 | Borden Dino Solar | Borden Dino Solar, LLC | Borden | Solar | 120.47 | 59905 FARADAY 345KV | 2028-07-01 |  |  |  |  | In study
29INR0131 | Caesar Solar | Caesar Solar, LLC | Borden | Solar | 181.6 | 59916 Buck Canyon 345 kV | 2029-11-26 | 2026-09-15 | True |  |  | Signed; security posted | In study -> Signed; security posted
29INR0132 | Caesar Storage | Caesar Solar, LLC | Borden | Battery storage | 205.5 | 59916 Buck Canyon 345 kV | 2029-11-26 | 2026-09-15 | True |  |  | Signed; security posted | In study -> Signed; security posted
27INR0499 | Draco Solar | Draco Solar LLC | Borden | Solar | 500 | Tap Long Draw (59900) – Faraday (59905) CKT 1 and LONGDRAW (59900) - GALVANI(59912) CKT 2 | 2027-08-19 |  |  |  |  | In study
29INR0291 | Enfinity Post Oak Solar SLF | EG White Oak LLC | Borden | Solar | 500 | 345kV Muleshoe (59922) | 2029-12-18 |  |  |  |  | In study
29INR0292 | Enfinity Post Oak Storage SLF | EG White Oak LLC | Borden | Battery storage | 0 | 345kV Muleshoe (59922) Transmission line | 2029-12-18 |  |  |  |  | In study
29INR0267 | Enfinity White Oak BESS | EG White Oak LLC | Borden | Battery storage | 200 | Tap 138kV Key (1307) to 138kV Gail (1308) | 2029-09-17 |  |  |  |  | In study
28INR0176 | Gail Mountain Solar | Gail Mountain Solar, LLC | Borden | Solar | 244.4 | Muleshoe (Bus #59922) 345 kV | 2028-08-25 | 2025-12-30 | True |  |  | Signed; security posted
26INR0621 | Juno 3 Solar | Juno Solar 3 | Borden | Solar | 500 | #59916 Buck Canyon 345kV | 2027-11-30 | 2025-07-01 | True |  |  | Signed; security posted
27INR0434 | Lyra Solar | Juno Solar 4 | Borden | Solar | 500 | 345kV MULESHOE (#59922) | 2027-09-15 | 2025-07-01 | True |  |  | Signed; security posted
26INR0636 | Lyra Storage | JUNO BESS I | Borden | Battery storage | 500 | 345kV MULESHOE (#59922) | 2026-11-12 | 2025-08-13 |  |  |  | Signed
28INR0297 | Magnet Solar | HyFuels Big Spring Solar LLC | Borden | Solar | 503.09 | Faraday Substation 345kV - Bus #59905 | 2029-09-29 | 2025-12-11 | True |  |  | Signed; security posted
28INR0298 | Magnet Storage | HyFuels Big Spring LLC | Borden | Battery storage | 426.7 | Faraday 345 kV Substation (#59905) | 2029-09-29 |  |  |  |  | In study
25INR0439 | Stephens Ranch Wind Repower | Stephens Ranch Wind Energy, LLC | Borden | Wind | 12.4 | 59900 Long Draw 345 kV | 2027-11-01 |  | True |  |  | Signed; security posted
26INR0359 | Uva Creek Solar | Grape Creek Solar, LLC | Borden | Solar | 302.16 | Muleshoe #59922 345 KV | 2028-08-25 | 2024-10-30 | True |  |  | Signed; security posted
25INR0474 | Solheim Solar | Solheim Solar, LLC | Bosque | Solar | 108.68 | Meridian (Bus# 315) - Glen Rose (Bus #319) 69 kV | 2027-11-01 |  |  |  |  | In study
27INR0298 | Symank Solar | BT Symank Solar, LLC | Bosque | Solar | 66.55 | Tap 69 kV 37470 TNOLSEN - 37520 TNSYCAMORE | 2027-12-15 |  |  |  |  | In study
30INR0005 | Woodland Energy Storage | Woodland Energy Storage, LLC | Bosque | Battery storage | 207.6 | 68040 Kopperl Substation 345kV | 2030-10-01 |  |  |  |  | In study
25INR0421 | Aldrin 138 BESS | Aldrin Energy Storage LLC | Brazoria | Battery storage | 207 | (Bus: 39015) North Alvin TNMP 138kV | 2028-03-01 | 2024-04-18 | True |  |  | Signed; security posted
25INR0425 | Aldrin 345 BESS | Aldrin Energy Storage LLC | Brazoria | Battery storage | 362 | (Bus: 43030) Meadow 345kV substation | 2028-03-01 | 2024-06-15 | True |  |  | Signed; security posted
25INR0102 | Austin Bayou Solar | Austin Bayou Solar, LLC | Brazoria | Solar | 502.48 | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | 2027-06-01 | 2023-11-15 | True |  |  | Signed; security posted
25INR0235 | Austin Bayou Storage I | Austin Bayou Solar, LLC | Brazoria | Battery storage | 150.68 | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | 2027-06-01 | 2025-02-14 |  |  |  | Signed
25INR0236 | Austin Bayou Storage II | Austin Bayou Solar, LLC | Brazoria | Battery storage | 156.6 | Tap to CKT#27 from Savana (Bus# 43180) to Oasis (Bus# 43035) – 345 kV Line | 2027-06-01 | 2025-02-14 |  |  |  | Signed
25INR0237 | Austin Bayou Storage III | Austin Bayou Solar, LLC | Brazoria | Battery storage | 156.6 | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | 2027-06-01 | 2025-02-14 |  |  |  | Signed
25INR0480 | Bell Creek BESS | BELL CREEK BESS, LLC | Brazoria | Battery storage | 200.9 | Tap 138kV 39500 West Colombia - 39703 FM524 | 2027-10-30 | 2024-11-14 |  |  |  | Signed
27INR0611 | Bodkin BESS SLF | Bodkin BESS, LLC | Brazoria | Battery storage | 0 | The 138kV Danbury Dab DANBUR_POI_8 (BUS#42875) Station | 2027-12-01 |  |  |  |  | In study | new
26INR0314 | Brazos River BESS | Brazos River BESS LLC | Brazoria | Battery storage | 180.36 | Tap 138kV 39530 West Colombia LOCAL TNP - 39560 ANGLETON TNP | 2027-10-30 | 2025-05-24 |  |  |  | Signed
27INR0095 | Bulldog Power (TEF - Due Diligence) | Bulldog Power LLC | Brazoria | Gas turbine | 311 | 39703 TNMP FM524 Substation 138kV | 2027-12-18 |  |  |  |  | In study
30INR0073 | Bulldog Power II | Bulldog Power II LLC | Brazoria | Gas turbine | 311 | 39703 TNMP FM524 Substation 138kV | 2030-09-30 |  |  |  |  | In study
24INR0712 | Byrd Ranch Repower | Byrd Ranch Storage LLC | Brazoria | Battery storage | 5.5 | 39700 SWEENY 138kV | 2027-01-22 | 2020-12-14 |  |  |  | Signed
23INR0091 | Cascade Solar | Cascade Solar Energy, LLC | Brazoria | Solar | 171 | 43180 SAVANAH 345 kV | 2028-01-15 | 2023-04-17 | True |  |  | Signed; security posted
23INR0376 | Cascade Storage | Oyster Creek LLC | Brazoria | Battery storage | 250 | 345kV Oasis (43035) – Seabreeze circuit 27 | 2028-06-01 |  |  |  |  | In study
22INR0279 | Clutch City Solar Phase I | HZ Solar I, LLC | Brazoria | Solar | 200.75 | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT #04 | 2028-07-01 | 2022-09-30 |  |  |  | Signed
25INR0330 | Clutch City Solar Phase II | HZ SOLAR I, LLC | Brazoria | Solar | 251.27 | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT#04 | 2028-07-01 | 2025-02-11 |  |  |  | Signed
26INR0374 | Cobra Clean Energy Center | Cobra Clean Energy Center LLC | Brazoria | Battery storage | 100.4 | looped on circuit 04 between Mustang Bayou (#42960) and Hudson (#42100) | 2027-10-08 |  |  |  |  | In study
25INR0566 | Copano Bay Energy Storage | Copano Bay Energy Storage, LLC | Brazoria | Battery storage | 201.04 | Tap 138kV 42980 Nash - 44010 WA Parish Ckt 2 | 2027-12-31 |  |  |  |  | In study
19INR0134 | Cottonwood Bayou Solar | Cottonwood Bayou Solar, LLC | Brazoria | Solar | 351.4 | tap 138kV 42870 Liverpool - 43070 Petson | 2026-10-30 | 2019-11-13 | True | 2024-05-01 | 2024-05-29 | Approved for synchronization
23INR0150 | Cradle Solar | Cradle Solar LLC | Brazoria | Solar | 200.85 | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | 2027-09-17 | 2023-03-15 | True |  |  | Signed; security posted
20INR0248 | DAMAZO (Second Division) SOLAR | TX Gulf Solar 1 LLC | Brazoria | Solar | 100.2 | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | 2025-12-31 | 2020-10-14 | True | 2024-10-08 | 2024-10-17 | Approved for synchronization
23INR0790 | DAMON BESS3 | BarBar Storage LLC | Brazoria | Battery storage | 9.96 | Station Name: DAMON TSP Station Code: DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV Node (associated w/ load/load XFRM in NMMS): TR2 | 2025-12-01 | 2024-01-30 | True | 2025-09-29 | 2026-03-04 | Approved for synchronization
23INR0603 | Damon BESS 2 | PR DAMON, LLC | Brazoria | Battery storage | 9.99 | 9.99 MW 50 MWh battery energy storage project connecting at 12.47kV Damon (DA) substation. Station Name (TDSP Station Code): DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | 2027-08-21 | 2023-10-06 | True |  |  | Signed; security posted
25INR0554 | Dan Kearney BESS | Dan Kearney BESS LLC | Brazoria | Battery storage | 204.38 | 39703 TNFM524 138kV | 2029-02-28 | 2024-10-18 |  |  |  | Signed
25INR0103 | Elio BESS | Elio Energy LLC | Brazoria | Battery storage | 205.28 | 138 kV Weinbrenner Station (Bus #42990) | 2028-12-31 | 2024-09-15 | True |  |  | Signed; security posted
26INR0226 | First Capitol BESS | First Capitol BESS, LLC | Brazoria | Battery storage | 257.48 | Tap 138kV West Columbia Main (39500) - Sweeny Cogen (110505) | 2027-11-01 | 2025-05-15 | True |  |  | Signed; security posted
25INR0550 | Friendswood Energy Storage | Friendswood Energy Storage LLC | Brazoria | Battery storage | 105.08 | TAP 138kV 39010 HASTINGS - 38980 FRIENDSWOOD | 2028-03-30 |  |  |  |  | In study
26INR0417 | GAMAY ENERGY STORAGE | GAMAY ENERGY STORAGE LLC | Brazoria | Battery storage | 418.6 | Tap 138 kV Line from TNFM524 (39703) to West Columbia Main (39500), in Brazoria County. | 2028-01-01 | 2025-05-27 |  |  |  | Signed
27INR0209 | Goby Energy Center | Goby Energy Center | Brazoria | Battery storage | 200.65 | Tap 138kV line 44390 Karsten - 44721 Thompsons | 2029-09-07 |  |  |  |  | In study
28INR0448 | Gulf Prairie BESS | Gulf Prairie Energy LLC | Brazoria | Battery storage | 207.78 | (CEHESub) looped either 1) on 138 kV circuit 82 between RIWOOD (#43150) and Angleton (#42110), or 2) on 345 kV circuit 18 between DOW (#42500) and Huizache (#46640) | 2028-12-01 |  |  |  |  | In study
27INR0449 | Gulf Prairie Solar | Gulf Prairie Energy LLC | Brazoria | Solar | 202.17 | (CEHESub) looped either 1) on 138 kV circuit 82 between RIWOOD (#43150) and Angleton (#42110), or 2) on 345 kV circuit 18 between DOW (#42500) and Huizache (#46640) | 2028-12-01 |  |  |  |  | In study
26INR0551 | Hastings Park BESS | Brazos Roots BESS, LLC | Brazoria | Battery storage | 256.34 | 39010 138kV HASTINGS | 2028-02-27 | 2025-08-13 |  |  |  | Signed
27INR0061 | Hecate Energy Orem Wind | Hecate Energy LLC | Brazoria | Wind | 1542 | 42530 Jones Creek 345kV | 2030-06-01 |  |  |  |  | In study
26INR0408 | Liatris Flexible Gas | Stone Creek Peaker LLC | Brazoria | Gas turbine | 204.71 | Tap 138 kV (42980) Nash - (44010) WA Parish CKT02 | 2029-02-01 | 2025-11-01 | True |  |  | Signed; security posted
21INR0444 | Long Point Storage | Long Point Storage, LLC | Brazoria | Battery storage | 100.62 | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | 2027-12-30 | 2023-08-28 |  |  |  | Signed
24INR0570 | Marcus Energy Storage | Marcus Energy Storage, LLC | Brazoria | Battery storage | 201.04 | Tap 138kV 39500 West Columbia Main - 110505 Sweeny Co-Gen LP Ckt 1 | 2027-09-01 |  |  |  |  | In study
28INR0295 | Margay Energy Storage | PowerPulse LLC | Brazoria | Battery storage | 101.3 | Tap 138kV 42750 Mykawa - 48353 Telephone Ckt 06 | 2029-04-10 | 2025-12-26 |  |  |  | Signed
19INR0041 | Myrtle Solar | Myrtle Solar, LLC | Brazoria | Solar | 321.2 | 42110 Angleton 138kV | 2027-06-21 | 2019-11-13 | True | 2022-12-07 | 2022-12-20 | Approved for synchronization
27INR0636 | Myrtle Solar Repower | Myrtle Solar, LLC | Brazoria | Solar | 314.27 | 42110 Angleton 138kV | 2027-06-21 |  |  |  |  | In study | new
26INR0117 | Oyster Creek Solar I SLF | Oyster Creek Solar 1, LLC | Brazoria | Solar | 0 | Tap 138kV 42110 Angleton - 42050 Clute | 2029-04-01 |  |  |  |  | In study
26INR0118 | Oyster Creek Storage I SLF | Oyster Creek Solar 1, LLC | Brazoria | Battery storage | 0 | Tap 138kV 42110 Angleton - 42050 Clute | 2029-04-01 |  |  |  |  | In study
29INR0174 | Palisade BESS | Flexen USA LLC | Brazoria | Battery storage | 153.5 | Hoffman (42810) - Lake Jackson (42880) 138 kV line | 2029-10-01 |  |  |  |  | In study
23INR0194 | Pequin Energy Storage | Pequin Energy Storage, LLC | Brazoria | Battery storage | 103.4 | 39500 TN West Columbia 138kV | 2027-09-13 |  |  |  |  | In study
25INR0170 | Pinewood Solar | Brazoria Solar II, LLC | Brazoria | Solar | 150.68 | 43020 Seabreeze 345kV | 2028-02-29 | 2025-05-08 |  |  |  | Signed
24INR0041 | Rock N' Roll Solar SLF | Rock N’ Roll Solar, LLC | Brazoria | Solar | 151.97 | tap 138kV 44600 Rosharon - 44531 Winmil | 2027-08-30 |  |  |  |  | In study
24INR0234 | Rock N' Roll Storage SLF | Rock N’ Roll Solar, LLC | Brazoria | Battery storage | 0 | tap 138kV 44600 Rosharon - 44531 Winmil | 2028-08-01 |  |  |  |  | In study
24INR0235 | Rock N' Roll Storage Two | Rock N’ Roll Solar, LLC | Brazoria | Battery storage | 206 | tap 138kV 44600 Rosharon - 44531 Winmil | 2027-08-30 |  |  |  |  | In study
26INR0497 | Rosharon BESS | Rosharon BESS LLC | Brazoria | Battery storage | 120 | 138 kV 42570 Archer (ACH) | 2028-06-30 |  |  |  |  | In study
24INR0282 | Royal River BESS | Royal River LLC | Brazoria | Battery storage | 310.7 | Tap 138kV 42110 Angleton - 43381 West Columbia | 2028-06-30 | 2023-12-15 | True |  |  | Signed; security posted
27INR0096 | Rubicon Power BESS | Rubicon Power LLC | Brazoria | Battery storage | 301.38 | 39703 TNMP FM524 138kV | 2027-12-31 |  |  |  |  | In study
25INR0378 | Second Division Storage | Mound Creek Storage, LLC | Brazoria | Battery storage | 0 | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | 2025-12-31 |  |  |  |  | In study
26INR0189 | Skipjack Energy Storage | Skipper Energy Storage LLC | Brazoria | Battery storage | 150.6 | Tap 138 42980 Nash - 44010 W A Parish ckt #2 | 2028-02-28 | 2024-08-13 | True |  |  | Signed; security posted
24INR0530 | Southside Energy | Southside Energy, LLC | Brazoria | Battery storage | 101.2 | Tap 138kV 42960 Mustang Bayou - 42100 HUDSON ckt 4 | 2028-12-31 |  |  |  |  | In study
25INR0458 | Surfside Energy Storage | Rocky Mountain Energy Holdings, LLC | Brazoria | Battery storage | 50.34 | Tap 138kV 42110 Angleton – 43150 Riwood ckt 82 | 2028-12-31 |  |  |  |  | In study
23INR0054 | Tanglewood Solar | Brazoria Solar, LLC | Brazoria | Solar | 250.96 | 345kV Seabreeze Substation | 2026-09-30 | 2022-11-01 | True | 2025-08-05 | 2025-08-20 | Approved for synchronization
25INR0494 | Willow Beach Wind | Capital Wind, LLC | Brazoria | Wind | 202.33 | Tap 138 kV Bus# 42100 HUD_8 – Bus# 42960 MUSTNG_S04_8 138kV CKT# 4 | 2027-10-01 | 2025-06-16 |  |  |  | Signed
25INR0347 | Cadet Storage | TX BESS 5, LLC | Brazos | Battery storage | 104.42 | Tap 69kV 32864 BRYN_ATK69 to 32873 BRYN SHADY | 2029-07-28 |  |  |  |  | In study
28INR0530 | Wickson Creek Gas | Wickson Creek Center, LLC | Brazos | Gas turbine | 1022.08 | Jack Creek Station 345 kV (#975) | 2028-10-01 |  |  |  |  | In study
29INR0170 | Three Ranches BESS | Three Ranches Energy LLC | Brewster | Battery storage | 103.37 | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | 2029-12-01 |  |  |  |  | In study
28INR0271 | Three Ranches Solar | Three Ranches Energy LLC | Brewster | Solar | 125.53 | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | 2029-12-01 |  |  |  |  | In study
23INR0330 | BRP Snowdon BESS | BRP SNOWDON BESS LLC | Briscoe | Battery storage | 410.94 | 23914 Tule Canyon Substation 345kV | 2028-12-01 |  |  |  |  | In study
29INR0397 | Black Mountain Briscoe Gas | Black Mountain Power LLC | Briscoe | Gas combined cycle | 495.32 | ‎23914, Tule Canyon Substation, 345 kV | 2029-09-28 |  |  |  |  | In study | new
29INR0030 | Commodus Solar | IP Blackwell, LLC | Briscoe | Solar | 502.1 | Tap 345kV 23914 Tule Canyon - 23900 Alibates | 2029-07-30 |  |  |  |  | In study
29INR0031 | Commodus Wind | IP Blackwell, LLC | Briscoe | Wind | 641.4 | tap 345kV 23914 Tule Canyon - 23900 Alibates | 2029-07-30 |  |  |  |  | In study
28INR0023 | Silverton Solar | NextEra Energy Interconnection Holdings, LLC | Briscoe | Solar | 410 | Tap 345kV 23914 Tule Canyon - 79001 Cross_W1 | 2029-07-01 |  |  |  |  | In study
23INR0087 | Kinenos Solar | Encino del Sol Energy, LLC | Brooks | Solar | 203.17 | tap 345kV 8905 North Edinburg - 8455 Lon Hill | 2029-12-31 |  |  |  |  | In study
27INR0400 | Reforzar BESS 1 | Tempus Power management LLC | Brooks | Battery storage | 207.6 | 345 kV 80078 Reforzar | 2028-04-13 |  |  |  |  | In study
27INR0401 | Reforzar Bess 2 | Tempus Power management LLC | Brooks | Battery storage | 207.6 | 345 kV 80078 Reforzar | 2028-04-13 |  |  |  |  | In study
28INR0059 | Verily Solar (FKA Cuello De Cuero Solar) | Verily Solar, LLC | Brooks | Solar | 261 | 80078 Reforzar Switch Station 345kV | 2029-07-01 |  |  |  |  | In study
28INR0166 | Brookesmith Storage | Brookesmith Storage LLC | Brown | Battery storage | 351 | Tap Brown Switch #1444 – Russell Gap Switch #3348 | 2029-05-07 |  |  |  |  | In study
24INR0333 | Chisme Solar | Blue Heron Solar, LLC | Brown | Solar | 147 | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | 2027-04-13 |  | True |  |  | Signed; security posted
24INR0331 | Chisme Storage | Blue Heron Solar, LLC | Brown | Battery storage | 150.7 | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | 2027-04-13 |  | True |  |  | Signed; security posted
27INR0432 | Coyote Ridge BESS | Grenergy USA | Brown | Battery storage | 111.06 | 292 Holder 138 kV | 2027-10-06 |  |  |  |  | In study
19INR0075 | Horseshoe Bend Solar | Clenera | Brown | Solar | 301.1 | 1444 Brown 345kV | 2028-02-20 |  |  |  |  | In study
21INR0294 | Mountaineer Solar | Mustang Mountaineer Solar LLC | Brown | Solar | 329.26 | 1444 Brown 345 kV | 2029-09-01 |  |  |  |  | In study
27INR0291 | Nouveau BESS | RamZ BESS, LLC | Brown | Battery storage | 256.1 | 1444 Brown Switch - 3348 Russell Gap 345 kV Line | 2027-12-15 |  |  |  |  | In study
28INR0269 | Soluce Bravo Solar | BNPB1, LLC | Brown | Solar | 80.82 | tap 345kV 1444 BROWN - 11441 CORN TRAIL SW CKT2 | 2029-09-17 |  |  |  |  | In study
28INR0270 | Soluce Bravo Storage | BNPB1, LLC | Brown | Battery storage | 302.62 | tap 345kV 1444 BROWN - 11441 CORN TRAIL SW CKT2 | 2029-09-17 |  |  |  |  | In study
24INR0544 | Wetzel BESS | Brown ESS, LLC | Brown | Battery storage | 185.57 | Tap 138kV 1654 Zephyr – 1655 Brownwood Switch | 2028-09-09 |  |  |  |  | In study
30INR0111 | Tradition BESS | Horizon Energy Storage Greenfield Project Holdings LLC | Burleson | Battery storage | 150.36 | 32878 Greens Prairie 138kV | 2030-04-30 |  |  |  |  | In study
24INR0313 | Backbone Creek BESS | Backbone Creek BESS LLC | Burnet | Battery storage | 124.1 | 7351 STARCKE 138kV | 2026-12-01 | 2023-12-22 | True | 2026-09-04 | 2026-09-21 | Approved for synchronization | Signed; security posted -> Approved to connect
26INR0499 | Mineral Springs BESS | Burnet County LLC | Burnet | Battery storage | 104 | 7065 DOBVI 138kV | 2027-11-02 |  |  |  |  | In study
27INR0125 | RedSun BESS | Redsun Solar Project LLC | Burnet | Battery storage | 84.04 | Existing Line from Substation Name: Burnet (PSSE#7100) to Substation Name: Bertram (PSSE#7520) | 2028-08-28 |  |  |  |  | In study
27INR0124 | RedSun Solar | Redsun Solar Project LLC | Burnet | Solar | 82.55 | Tap 138kV 7100 Burnet - 7529 Bertram | 2028-08-28 | 2025-09-25 |  |  |  | Signed
23INR0503 | Ardesia Storage | Ardesia Storage Project LLC | Caldwell | Battery storage | 100 | Tap 138kV 7325 Mendoza - 7216 Lockhart | 2030-03-29 |  |  |  |  | In study
29INR0167 | Big Watt Power Austin-1 | Big Watt Power Austin-1 LLC | Caldwell | Gas combined cycle | 448.98 | Tapping the 345 kV Double circuit Line: Zorn (Bus# 7042) - Lytton Springs (Bus# 9074) and Zorn (Bus# 7042) - Austrop (Bus# 7040). | 2028-11-15 |  |  |  |  | In study
29INR0340 | Bobcat Generating Station | Critical Grid Solutions Bobcat, LLC | Caldwell | Gas engines | 450 | Between (7042) ZORN & (9074) LYTTON SPRINGS Substations on ONCOR 345kV. | 2029-11-01 |  |  |  |  | In study
30INR0031 | Caldwell County Energy Center | Caldwell County Energy Center, LLC | Caldwell | Gas combined cycle | 1500 | #7051 Misty Substation 345kV | 2030-04-30 |  |  |  |  | In study
25INR0129 | Demeter Solar | Demeter Solar, LLC | Caldwell | Solar | 88 | Tap 138kV 7224 LULING - 7216 LOCKHART | 2029-06-01 |  |  |  |  | In study
25INR0130 | Demeter Storage | Demeter Solar, LLC | Caldwell | Battery storage | 65 | Tap 138kV 7224 LULING - 7216 Lockhart | 2029-06-01 |  |  |  |  | In study
26INR0523 | Demeter Storage 2 | Demeter Solar, LLC | Caldwell | Battery storage | 138 | Tap 138kV 7224 LULING - 7216 Lockhart | 2029-06-01 |  |  |  |  | In study
23INR0135 | Elbus BESS | BRP Elbus BESS LLC | Caldwell | Battery storage | 200.99 | 9075 Lytton 138kV | 2028-06-01 |  |  |  |  | In study
27INR0585 | Lytton Springs BESS | SMT Lytton Springs LLC | Caldwell | Battery storage | 76.4 | Lytton Springs (#9074) – Fayette Plant (#7055) 345 kV Line | 2028-12-01 |  |  |  |  | In study
27INR0584 | Lytton Springs Solar | SMT Lytton Springs LLC | Caldwell | Solar | 55.3 | Lytton Springs (#9074) – Fayette Plant (#7055) 345 kV Line | 2028-12-01 |  |  |  |  | In study
27INR0478 | Metro BESS | Metro BESS LLC | Caldwell | Battery storage | 200.71 | 138 kV LYTTON8 (9075) | 2030-12-07 |  |  |  |  | In study
30INR0054 | SCHNEIDER COMBINED CYCLE | LCRA | Caldwell | Gas combined cycle | 880 | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | 2033-05-10 | 2025-12-19 |  |  |  | Signed
29INR0176 | SCHNEIDER GAS RICE | LCRA | Caldwell | Gas engines | 113.02 | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | 2032-12-14 | 2025-12-19 |  |  |  | Signed
31INR0013 | SCHNEIDER GAS RICE PHASE 2 | LCRA | Caldwell | Gas engines | 113.02 | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | 2032-12-14 | 2025-12-19 |  |  |  | Signed
22INR0473 | TAIN SOLAR | Abei Energy Green VII LLC | Caldwell | Solar | 37.54 | tap 138kV 7216 Lockhart - 7224 Luling City | 2027-10-27 |  |  |  |  | In study
20INR0245 | Volunteer Storage | Blackjack Storage LLC | Caldwell | Battery storage | 50.6 | 7216 Lockhart 138kV | 2028-02-29 |  |  |  |  | In study
26INR0019 | HyFuels Green Lake Solar | HyFuels Green Lake Solar LLC | Calhoun | Solar | 347 | Dokmai 138kV Substation (bus #80090) | 2027-12-01 |  |  |  |  | In study
20INR0266 | Tres Bahias Solar | Tres Bahias Solar Power LLC | Calhoun | Solar | 195 | 8140 Joslin 138kV | 2026-08-31 | 2020-08-07 | True | 2023-06-26 | 2023-09-12 | Approved for synchronization
23INR0123 | Vaca Storage | Long Mount Storage, LLC | Calhoun | Battery storage | 101 | 138kV 8723 Cangrejo | 2029-07-01 |  |  |  |  | In study
27INR0466 | Wolfram Storage | Nova Clean Energy, LLC | Calhoun | Battery storage | 206.6 | Dokmai 138kV Substation (bus #80090) | 2027-12-01 |  |  |  |  | In study
20INR0083 | Baird North Wind | BMP Wind, LLC | Callahan | Wind | 340 | 68008 Latimer 345kV | 2026-12-31 | 2019-05-31 | True | 2021-08-09 | 2021-08-20 | Approved for synchronization
25INR0446 | Guitar BESS | Guitar BESS LLC | Callahan | Battery storage | 204.79 | Tap 138kV 6275 ABEAST4A - 6670 PUTN4C | 2027-12-31 |  |  |  |  | In study
28INR0246 | Hittson Creek BESS | 174 Power Global Properties | Callahan | Battery storage | 205.38 | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | 2028-12-15 |  |  |  |  | In study
28INR0245 | Hittson Creek Solar | 174 Power Global Properties | Callahan | Solar | 402.93 | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | 2028-12-15 |  |  |  |  | In study
22INR0262 | Sequoia II Solar | ENBRIDGE SOLAR SEQUOIA II LLC | Callahan | Solar | 417.47 | 68051 Reata 345kV | 2027-01-28 | 2023-08-29 | True |  |  | Signed; security posted
23INR0066 | Accalia Point Solar | Accalia Point Solar LLC | Cameron | Solar | 190.5 | Tap 345kV 8383 North Edingburg – 79501 Kingfisher | 2029-05-31 |  |  |  |  | In study
27INR0084 | Aegle Power | Aegle Power LLC | Cameron | Gas combined cycle | 1536.4 | (#79501) Kingfisher 345 kV | 2027-07-30 |  |  |  |  | In study
26INR0640 | Amberjack2 BESS | Hunt Energy Network, LLC | Cameron | Battery storage | 180 | 79501 KINGFISHER 345KV | 2028-04-03 |  |  |  |  | In study
20INR0086 | Arroyo Solar | BT Cantwell Solar, LLC | Cameron | Solar | 100 | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | 2028-02-22 | 2021-09-28 | True |  |  | Signed; security posted
24INR0306 | Arroyo Storage | BT Cantwell Solar, LLC | Cameron | Battery storage | 183.76 | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | 2026-10-23 | 2022-08-10 | True | 2025-12-08 | 2026-06-25 | Approved for synchronization
25INR0385 | Bobcat Cameron BESS | Bobcat BESS, LLC | Cameron | Battery storage | 200.78 | 5764 East Rio Hondo Substation 138kV | 2027-12-31 |  |  |  |  | In study
24INR0319 | Burro Loco Energy Storage | VESI | Cameron | Battery storage | 25.14 | 8626 Resaca 69kV | 2028-09-15 |  |  |  |  | In study
22INR0401 | Eval Storage | Hecate Grid East Valley Storage LLC | Cameron | Battery storage | 251.85 | 80229 Cavazos 138kV | 2029-04-30 | 2022-02-03 | True |  |  | Signed; security posted
26INR0691 | Harlingen #1 BESS 1 | Harlingen ESS Assets LLC | Cameron | Battery storage | 9.99 | TSP Station Name: Harlingen #1 TSP Station Code: HARLIN_1 • Load Name / Load Transformer Name: 69_12_1 Bus #: PTI Bus Number:8321 Voltage (Transmission level kV):69kV Node (associated w/ load/load XFMR in NMMS): Transformer 1 | 2026-08-21 | 2025-06-18 | True | 2026-07-14 | 2026-08-10 | Approved for synchronization
22INR0469 | Harper Energy Storage | VESI 31 LLC | Cameron | Battery storage | 82.42 | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | 2028-09-15 |  |  |  |  | In study
25INR0270 | Harryoung Solar | Gransolar Texas Four LLC | Cameron | Solar | 190.01 | Tap 8319 Rio Hondo - SOUTH SANTA ROSA: 8359, 138kV | 2028-05-15 |  |  |  |  | In study
25INR0552 | HarryoungBESS | Gransolar Texas Four LLC | Cameron | Battery storage | 190.01 | 8319 Rio Hondo sub 138kV | 2028-05-15 |  |  |  |  | In study
24INR0572 | Megacharge BESS | SMT Harlingen III LLC | Cameron | Battery storage | 110 | 8320 WEST HARLINGEN 69kV | 2028-07-01 |  |  |  |  | In study
28INR0397 | Ouroboros Grid BESS 1 | Ouroboros Grid BESS Unit 1 | Cameron | Battery storage | 200.82 | POIB: #88337 Chalybe 345 kV (expansion of the #8735 Chalybe 138 kV – to be connected by double circuit line to #79500 Palmito 345 kV) | 2028-06-01 |  |  |  |  | In study
28INR0398 | Ouroboros Grid BESS 2 | Ouroboros Grid BESS Unit 2 | Cameron | Battery storage | 200.81 | 88337 Chalybe 345 kV | 2028-06-01 |  |  |  |  | In study
28INR0403 | Ouroboros Grid BESS 3 | Ouroboros Grid BESS Unit 3 | Cameron | Battery storage | 200.72 | 88337 Chalybe 345 kV | 2028-06-01 |  |  |  |  | In study
28INR0427 | Ouroboros Grid BESS 4 | Ouroboros Grid BESS Unit 4 | Cameron | Battery storage | 201.14 | 79500 Palmito 345kV | 2029-06-01 |  |  |  |  | In study
28INR0428 | Ouroboros Grid BESS 5 | Ouroboros Grid BESS Unit 5 | Cameron | Battery storage | 200.96 | 79500 Palmito 345KV | 2029-06-01 |  |  |  |  | In study
28INR0429 | Ouroboros Grid BESS 6 | Ouroboros Grid BESS Unit 6 | Cameron | Battery storage | 200.94 | 79500 Palmito 345KV | 2029-06-01 |  |  |  |  | In study
22INR0480 | Pachanga Wind | Pachanga Wind LLC | Cameron | Wind | 300 | tap 345kV 5966 Palmito - 80137 Stewart Rd | 2030-04-08 |  |  |  |  | In study
26INR0008 | Puerto Del Sol 1 | PUERTO DEL SOL, LLC | Cameron | Solar | 213.8 | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | 2026-12-31 |  |  |  |  | In study
27INR0002 | Puerto Del Sol 2 | PUERTO DEL SOL, LLC | Cameron | Solar | 213.8 | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | 2027-12-31 |  |  |  |  | In study
27INR0399 | Resaca Oasis Storage | Resaca Oasis Storage, LLC | Cameron | Battery storage | 200.7 | # 79601 Stillman Substation 138 kV | 2028-09-20 | 2025-05-22 | True |  |  | Signed; security posted
26INR0515 | Rio Grand Valley Element Fuels Power | Element H2Gen, LLC | Cameron | Hydro | 79.63 | Tap 138kV 59450 Waterport Substation - 5789 Southmost Sub | 2028-12-05 |  |  |  |  | In study
26INR0461 | Rio Hondo BESS | SBESS TX25 LLC | Cameron | Battery storage | 200.78 | Tap 138kV #80309 Las Pulgas - #8319 Rio Hondo | 2028-06-30 |  |  |  |  | In study
26INR0181 | Solar Star Frontier BESS | Solar Star Frontier BESS, LLC | Cameron | Battery storage | 101.02 | 8656 Luna 138kV | 2029-02-27 |  |  |  |  | In study
27INR0140 | Kingsmill Wind SLF | Kingsmill Wind, LLC | Carson | Wind | 606.3 | 79005 Railhead 345kV | 2029-09-01 | 2025-12-18 |  |  |  | Signed
23INR0283 | Kota Battery | Kota Storage, LLC | Carson | Battery storage | 200.8 | 23900 Alibates 345kV | 2028-10-31 |  |  |  |  | In study
27INR0022 | Panhandle Flagship Solar 1 | Panhandle Solar Group Operating Company LLC | Carson | Solar | 439.4 | 345 kV Railhead Substation (RAILHEAD #79005) | 2031-06-30 | 2025-08-28 |  |  |  | Signed
27INR0025 | Panhandle Flagship Storage | Panhandle Solar Group Operating Company LLC | Carson | Battery storage | 371.7 | 345 kV Railhead Substation (RAILHEAD #79005) | 2031-06-30 | 2025-08-28 |  |  |  | Signed
25INR0460 | Acker BESS | Ogallala BESS LLC | Castro | Battery storage | 301.04 | 23912 Ogallala 345 kV | 2029-04-17 | 2025-04-21 |  |  |  | Signed
20INR0050 | Castro Solar | Castro Solar One, LLC | Castro | Solar | 224.67 | 23912 Ogallala 345kV | 2029-04-18 | 2020-11-30 |  |  |  | Signed
29INR0034 | Cavell Solar | IP Cavell, LLC | Castro | Solar | 502.1 | Tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | 2029-07-30 |  |  |  |  | In study
29INR0035 | Cavell Wind | IP Cavell, LLC | Castro | Wind | 641.2 | tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | 2029-07-30 |  |  |  |  | In study
16INR0049 | Nazareth Solar | TX Nazareth Solar, LLC | Castro | Solar | 203 | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | 2027-08-31 | 2026-03-05 | True |  |  | Signed; security posted
27INR0143 | Ogalalla Storage | Hecate Energy Ogalalla Solar LLC | Castro | Battery storage | 251.6 | 23912 OGALLALA_5 345kV | 2028-04-15 |  |  |  |  | In study
23INR0015 | Scarlet Solar | Innovative Solar 416, LLC | Castro | Solar | 180 | tap 345kV 23912 Ogallala - 23910 Windmill | 2025-08-26 |  |  |  |  | In study
24INR0285 | APV Plumwood Storage | APV Lonestar Energy LLC | Chambers | Battery storage | 200.82 | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | 2029-10-01 | 2024-09-03 |  |  |  | Signed
23INR0029 | Cedar Bayou 5 (TEF - Due Diligence) | NRG Cedar Bayou 5 LLC | Chambers | Gas turbine | 697 | 40000 Cedar Bayou 345kV | 2028-03-31 | 2022-01-10 | True |  |  | Signed; security posted
23INR0425 | Coneflower Storage Project | Coneflower Storage Project LLC | Chambers | Battery storage | 170.85 | 40855 JORDON 138 kV | 2028-02-28 | 2024-03-25 | True |  |  | Signed; security posted
18INR0009 | Eagle Pines Gas | FGE Power | Cherokee | Gas combined cycle | 1173.5 | tap 345kV 3109 Stryker - 3123 Trinidad | 2028-10-30 |  |  |  |  | In study
23INR0324 | Lumberjack Storage | EDP Renewables North America LLC | Cherokee | Battery storage | 50.94 | 138 kV Tap 3110 Stryker Creek - 3147 Troup | 2029-11-01 | 2024-03-20 |  |  |  | Signed
25INR0414 | Rogers Creek BESS | Dialville BESS | Cherokee | Battery storage | 100.33 | Tap 138 KV DailVille (3160) - Neches Pump (3296) | 2029-04-17 |  |  |  |  | In study
26INR0524 | Fagus Solar Park 3 SLF | Greenalia Solar Power Misae III, LLC | Childress | Solar | 169.59 | 60501 Tesla 345 kV | 2027-06-28 | 2019-02-21 | True |  |  | Signed; security posted
25INR0515 | Fagus Storage SLF | Greenalia Energy Storage MISAE II LLC | Childress | Battery storage | 0 | 60501 Tesla 345kV | 2026-09-01 |  |  |  |  | In study
21INR0455 | Independence Trail Storage | KCE TX 16, LLC | Childress | Battery storage | 100 | 60501 Tesla 345kV | 2028-01-01 |  |  |  |  | In study
26INR0612 | Clay County Yang Storage | DM-CCY, LLC | Clay | Battery storage | 307.51 | 1458 Cobb Switching Station 345 kV | 2029-04-16 |  |  |  |  | In study
23INR0228 | Hiru Solar | Hecate Energy Hazel LLC | Clay | Solar | 603.7 | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | 2029-04-01 |  |  |  |  | In study
24INR0444 | Hiru Storage | Hecate Energy Hazel LLC | Clay | Battery storage | 503.6 | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | 2029-04-01 |  |  |  |  | In study
25INR0097 | Soleil Solar | Soleil Solar, LLC | Clay | Solar | 451.69 | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | 2028-12-28 | 2025-05-09 | True |  |  | Signed; security posted
28INR0155 | Coke BESS | Coke ESS, LLC | Coke | Battery storage | 220.3 | 76090 Divide Switchyard 345kV | 2028-04-10 |  |  |  |  | In study
26INR0218 | Fort Chadbourne Cattle BESS | Fort Chadbourne BESS | Coke | Battery storage | 50.23 | 6324 Fort Chadbourne 138 kv | 2027-06-29 |  |  |  |  | In study
25INR0135 | Hayrick BESS | Gransolar Texas Five LLC | Coke | Battery storage | 113.9 | 6351 Nicole 138kV | 2028-03-15 |  |  |  |  | In study
27INR0453 | Roboman Solar | Roboman Solar, LLC | Coke | Solar | 272.6 | Tap 345 kV (#76009) Twin Buttes – (#76090) Divide Ckt 1 | 2029-07-01 |  |  |  |  | In study
21INR0253 | Ulysses Solar | BNB Tennyson Solar LLC | Coke | Solar | 151.2 | 60072 Odysseus Substation 345 kV | 2027-03-17 | 2022-10-03 | True | 2026-09-18 |  | Approved for energization | Signed; security posted -> Energized
23INR0086 | Hanson Solar | Hanson Solar, LLC | Coleman | Solar | 398.83 | tap 345kV 1444 Brown - 11406 Central Bluff | 2027-08-17 | 2023-09-20 | True |  |  | Signed; security posted
23INR0794 | Invictus Energy Storage | GSA Land Holdings | Coleman | Battery storage | 140.53 | 6390 FIREROCK4A 138kV | 2028-05-31 |  |  |  |  | In study
29INR0222 | Paintbrush BESS1 | Renew Development HoldCo LLC | Coleman | Battery storage | 201.31 | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | 2030-10-15 |  |  |  |  | In study
28INR0469 | Paintbrush PV1 | Renew Development HoldCo LLC | Coleman | Solar | 251.5 | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | 2030-05-15 |  |  |  |  | In study
28INR0470 | Paintbrush PV2 | Renew Development HoldCo LLC | Coleman | Solar | 251.5 | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | 2030-05-15 |  |  |  |  | In study
29INR0220 | Paintbrush PV3 | Renew Development HoldCo LLC | Coleman | Solar | 251.5 | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | 2030-10-15 |  |  |  |  | In study
29INR0221 | Paintbrush PV4 | Renew Development HoldCo LLC | Coleman | Solar | 251.5 | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | 2030-10-15 |  |  |  |  | In study
24INR0274 | Bufflehead BESS | Boxcar Energy Storage, LLC | Collin | Battery storage | 153.77 | 2475 Lavon Switch 138kV | 2027-02-15 | 2024-04-10 |  |  |  | Signed
25INR0101 | Drake BESS | Mallard Energy Storage LLC | Collin | Battery storage | 257.3 | #833 Wylie Switch 138kV | 2027-01-29 | 2025-05-06 | True |  |  | Signed; security posted
25INR0238 | Little Ridge Storage | TX BESS B LLC | Collin | Battery storage | 252 | Tap 138kV Swindell (812) - Olinger (818) | 2027-09-01 |  |  |  |  | In study
25INR0391 | Purple Sage BESS 1 | Purple Sage, LLC | Collin | Battery storage | 156 | Anna 345 kV Bus# 2373. | 2028-02-12 | 2024-10-11 | True |  |  | Signed; security posted
25INR0392 | Purple Sage BESS 2 | Purple Sage, LLC | Collin | Battery storage | 156 | Anna 345 kV Bus# 2373 | 2028-02-12 | 2024-10-11 | True |  |  | Signed; security posted
28INR0321 | Altair Energy Storage | Altair Energy Storage | Colorado | Battery storage | 201.76 | Tap on 138 kV ALTAIR (bus# 78118) to STAFFORD HILL (bus# 78520) | 2030-03-31 |  |  |  |  | In study
26INR0259 | Cottontail Energy Center | Cottontail Energy Center, LLC | Colorado | Battery storage | 200.85 | 7258 Glidden Substation 138kV | 2027-10-19 |  |  |  |  | In study
25INR0402 | Driet BESS | Driet BESS LLC | Colorado | Battery storage | 150.52 | 7254 WEIMAR8 138kV | 2028-06-20 | 2025-12-23 |  |  |  | Signed
29INR0085 | Firefly Fields Solar | Firefly Fields Energy Center LLC | Colorado | Solar | 100.52 | Tap 138 kV <57640> <Rock Island> - <7258> <Glidden> | 2028-09-30 |  |  |  |  | In study
29INR0123 | Firefly Fields Storage | Firefly Fields Energy Center LLC | Colorado | Battery storage | 156.52 | Tap 138 kV 57640 Rock Island to 7258 Glidden | 2028-09-30 |  |  |  |  | In study
25INR0769 | Kleimann BESS | Columbus Clean Energy Center, LLC | Colorado | Battery storage | 9.9 | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Kleimann TSP Station Code: KLEIMA Load Name: LOAD1 Bus #: PTI Bus Number: 78115 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | 2026-12-08 | 2025-03-31 | True |  |  | Signed; security posted
27INR0555 | Montezuma Storage | Montezuma Storage LLC | Colorado | Battery storage | 183.88 | L_GLIDDE8_1Y; Bus number - 7258 138KV | 2030-10-16 |  |  |  |  | In study
25INR0186 | Moonlight Sonata BESS | Samsung Solar Energy 2, LLC | Colorado | Battery storage | 201.08 | Altair (78118) – Nada (78103) 138KV | 2028-07-01 |  |  |  |  | In study
27INR0147 | Paloma Energy Center | Harrison Street Development, LLC | Colorado | Solar | 193.8 | Tap 138 kV 57640 Rock Island - 57639 Sheridan | 2027-12-31 |  |  |  |  | In study
27INR0148 | Paloma Energy Center BESS | Harrison Street Development, LLC | Colorado | Battery storage | 53.6 | Tap 138kV 57640 Rock Island - 57639 Sheridan | 2027-12-31 |  |  |  |  | In study
32INR0002 | Radiant Plains Energy Center Solar | Adapture Solar Development | Colorado | Solar | 100 | Tap 138-kV Weimar (7254) to Schulenburg (7252) | 2029-12-27 |  |  |  |  | In study
30INR0045 | Radiant Plains Energy Center BESS | Adapture Solar Development | Colorado | Battery storage | 100 | Tap 138-kV Weimar (7254) to Schulenburg (7252) | 2029-12-27 |  |  |  |  | In study
27INR0321 | Rock Island Generating (TEF -Due Diligence) | Kerrville Public Utility Board Public Facility Corporation | Colorado | Gas engines | 121.8 | 57640 Rock Island 138 kV | 2027-06-01 | 2025-03-17 | True |  |  | Signed; security posted
25INR0768 | Stafford Hill BESS | Colorado Clean Energy Center, LLC | Colorado | Battery storage | 9.9 | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Stafford Hill TSP Station Code: STAFHI Load Name: LOAD1 Bus #: PTI Bus Number: 78520 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | 2026-11-14 | 2026-05-28 | True |  |  | Signed; security posted
29INR0242 | Enfinity Redbud Storage | EG Redbud LLC | Comal | Battery storage | 516.05 | 345kV Hays Energy (7043) - 345kV Bergheim (7770) | 2029-12-18 |  |  |  |  | In study
28INR0436 | Englehardt BESS | Comal BESS LLC | Comal | Battery storage | 200.51 | River Oaks (7173) | 2027-09-01 |  |  |  |  | In study
30INR0112 | Short River BESS | Horizon Energy Storage Greenfield Project Holdings LLC | Comal | Battery storage | 150.36 | 7456 LOP3378 138kV | 2030-04-30 |  |  |  |  | In study
27INR0365 | Comanche BESS | ENERGOS BESS | Comanche | Battery storage | 614.4 | #1440 Comanche Switching Station 345kV | 2029-05-07 | 2026-03-20 |  |  |  | Signed
23INR0359 | Crios BESS | BRP Crios BESS LLC | Comanche | Battery storage | 205.46 | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | 2028-03-01 |  |  |  |  | In study
27INR0050 | Darkwood BESS | Mustang Creek Solar, LLC | Comanche | Battery storage | 150.5 | Tap 345KV 1900 Comanche Peak - 1440 Comanche Switch | 2028-07-01 | 2025-11-05 | True |  |  | Signed; security posted
27INR0049 | Darkwood Solar | Mustang Creek Solar, LLC | Comanche | Solar | 152.02 | Tap 345KV 1900 Comanche Peak to 1440 Comanche SS | 2027-09-20 | 2025-11-05 | True |  |  | Signed; security posted
22INR0237 | Dragan Solar | Hecate Comanche Solar LLC | Comanche | Solar | 411 | 1440 Comanche 345kV | 2027-09-15 |  |  |  |  | In study
22INR0400 | Dragan Storage | Hecate Grid Dragan Storage LLC | Comanche | Battery storage | 408.3 | 1440 Comanche 345kV | 2030-03-31 |  |  |  |  | In study
22INR0220 | Lamkin Solar | Commanche Solar, LLC | Comanche | Solar | 101.5 | tap 69kV 258 Hamilton - 273 Gustine | 2027-11-08 | 2025-03-06 | True |  |  | Signed; security posted
24INR0157 | Merope BESS | BRP Merope BESS LLC | Comanche | Battery storage | 402.44 | 345 kV Corn Trail Switch Substation (#11441) | 2028-03-01 |  |  |  |  | In study
28INR0358 | Cherry Sage Solar 1 SLF | Cherry Sage Solar 1 LLC | Concho | Solar | 142.51 | (#60423) TREADWELL 138kV. | 2029-02-23 |  |  |  |  | In study
25INR0174 | Concho Pearl Solar | Concho Pearl Solar, LLC | Concho | Solar | 171.9 | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | 2028-01-09 | 2024-07-22 |  |  |  | Signed
25INR0175 | Concho Pearl Storage | Concho Pearl Solar, LLC | Concho | Battery storage | 162.4 | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | 2028-01-09 | 2024-07-22 |  |  |  | Signed
25INR0225 | Lucy Solar | Concho County Solar 1 LLC | Concho | Solar | 352.21 | Tap 345kV 7077 Amos Creek - 6444 San Angelo Red Creek and 7077 Amos Creek - 76009 Twin Buttes | 2027-06-30 | 2024-05-29 | True |  |  | Signed; security posted
26INR0255 | Operation Sunshine | Duck Creek Solar, LLC | Concho | Solar | 603.2 | 7077 Amos Creek 345kV | 2029-04-01 | 2025-08-27 | True |  |  | Signed; security posted
26INR0357 | Operation Sunshine Storage | Duck Creek Storage, LLC | Concho | Battery storage | 409.8 | 7077 Amos Creek 345kV | 2029-04-01 | 2025-08-27 | True |  |  | Signed; security posted
27INR0108 | Paint Rock Wind | Paint Rock Wind, LLC | Concho | Wind | 379.18 | Amos Creek (7077) – Bow Wood (76006) | 2028-10-01 | 2026-08-24 |  |  |  | Signed | In study -> Signed
29INR0139 | Trail Ranch Solar 1 | Aurora Solar LLC | Concho | Solar | 301.9 | Tap 345KV #6444 Red Creek - #7077 AMOS Creek | 2029-12-01 |  |  |  |  | In study
29INR0272 | Trail Ranch Solar 2 | Aurora Solar LLC | Concho | Solar | 132.85 | Tap 345 kV 6444 Red Creek -7077 Amos Creek | 2029-12-01 |  |  |  |  | In study | new
28INR0328 | 18-ALPHA BESS | SCOUT ENERGY MANAGEMENT, LLC | Cooke | Battery storage | 307.4 | To the 138 kV Valley View Substation, ( Bus No.691) | 2028-02-01 |  |  |  |  | In study
26INR0219 | Mountain Springs BESS | Mountain Springs BESS | Cooke | Battery storage | 150.52 | 704 Mountain Springs 138 kV | 2029-04-01 |  |  |  |  | In study
24INR0239 | Trojan BESS SLF | Trojan BESS | Cooke | Battery storage | 0 | 11735 Cedar Elm Switch 345kV | 2029-07-01 |  |  |  |  | In study
24INR0198 | Two Forks BESS | Two Forks LLC | Cooke | Battery storage | 309.8 | 684 SPRING 138kV | 2028-08-01 | 2024-05-03 | True |  |  | Signed; security posted
20INR0033 | WILDWIND | Wildcat Creek | Cooke | Wind | 180.08 | tap 345kV 1730 KrumW - 2373 Anna | 2026-04-15 | 2020-02-21 | True | 2020-12-22 | 2021-02-10 | Approved for synchronization
20INR0246 | Ryan Energy Storage | Ryan Storage LLC | Coryell | Battery storage | 51.6 | 37580 TNPancake 69kV | 2026-12-12 | 2021-02-18 | True |  |  | Signed; security posted
28INR0267 | Soluce Cotton Solar | CTPB1, LLC | Cottle | Solar | 202.91 | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | 2029-08-13 |  |  |  |  | In study
28INR0268 | Soluce Cotton Storage | CTPB1,LLC | Cottle | Battery storage | 201.54 | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | 2029-08-13 |  |  |  |  | In study
25INR0177 | Triangle Ranch Alpha | Triangle Ranch Wind | Cottle | Wind | 301.74 | Edith Clark 345 kV (#60500) | 2029-07-01 |  |  |  |  | In study
25INR0178 | Triangle Ranch Bravo | Triangle Ranch Wind | Cottle | Wind | 200.22 | Edith Clark 345 kV (#60500) | 2028-07-01 |  |  |  |  | In study
23INR0074 | BRP Ampato BESS | BRP Ampato BESS LLC | Crane | Battery storage | 121.56 | 10002 NS Crane Switch 138kV | 2027-12-01 |  |  |  |  | In study
22INR0385 | BRP Pictor BESS | BRP Pictor BESS LLC | Crane | Battery storage | 201.07 | 60400 Lynx 138kV | 2029-12-31 |  |  |  |  | In study
29INR0013 | Cattle Drive Solar | Cattle Drive Solar, LLC | Crane | Solar | 307 | 76000 North McCamey 345kV | 2028-12-31 | 2025-12-29 |  |  |  | Signed
23INR0308 | Fowler Ranch Storage | Crane BESS, LLC | Crane | Battery storage | 26.07 | 76025 Castle Mountain 138kV | 2027-09-30 |  |  |  |  | In study
24INR0383 | Soda Lake BESS 2 SLF | Crane II Solar Electric, LLC | Crane | Battery storage | 205.35 | 138 kV Soda Lake (#76026) | 2028-10-30 | 2026-08-21 |  |  |  | Signed | In study -> Signed
23INR0080 | Soda Lake Solar 2 SLF | Crane II Solar Electric, LLC | Crane | Solar | 201.74 | 138 kV Soda Lake (#76026) | 2028-10-30 | 2022-03-23 |  |  |  | Signed
29INR0279 | Tierra Loma Solar | Tierra Loma Solar, LLC | Crane | Solar | 250 | Tap 345 kV #18668 ROCK DRAW - #76000 NORTH MCCAMEY ckt 1 | 2029-09-01 |  |  |  |  | In study
29INR0280 | Tierra Loma Storage | Tierra Loma Solar, LLC | Crane | Battery storage | 200 | Tap 345 kV #18668 ROCK DRAW - #76000 NORTH MCCAMEY ckt 1 | 2029-09-01 |  |  |  |  | In study
28INR0389 | Tri-X BESS 1 SLF | Crane I Solar Electric, LLC | Crane | Battery storage | 205.3 | 138 kV Soda Lake (#76026) | 2028-10-30 | 2026-08-21 |  |  |  | Signed | In study -> Signed
20INR0143 | Tri-X Solar 1 SLF | Crane I Solar Electric, LLC | Crane | Solar | 201.5 | 138 kV Soda Lake (#76026) | 2028-10-30 | 2026-08-21 |  |  |  | Signed
26INR0110 | Western Flats Solar | Hecate Energy Point Mountain Solar Facility 1 LLC | Crane | Solar | 410.2 | Tap 138 kV 76615 Crane -76635 King Mountain; POI is 7.85 miles from Crane. | 2028-11-01 |  |  |  |  | In study
26INR0188 | Western Flats Storage | Hecate Energy Point Mountain Solar Facility 1 LLC | Crane | Battery storage | 410.7 | Tap 138 kV 76615 Crane -76635 King Mountain | 2028-11-01 |  |  |  |  | In study
26INR0366 | BLACK BEAR BESS | ESCONDIDO DRAW RESOURCES, LLC | Crockett | Battery storage | 51.2 | #6564 ILLN4A 138kV | 2028-06-01 |  |  |  |  | In study
26INR0365 | BLACK BEAR SOLAR | ESCONDIDO DRAW RESOURCES, LLC | Crockett | Solar | 102.9 | #6564 ILLN4A 138 KV | 2028-06-01 |  |  |  |  | In study
16INR0104 | Big Sampson Wind | Big Sampson Wind Project, LLC | Crockett | Wind | 265.4 | tap 345kV 76015 Cedar Canyon - 7053 Noelke | 2026-09-01 | 2019-11-08 | True | 2025-06-04 | 2025-06-16 | Approved for synchronization
22INR0455 | Blue Sky Sol | Blue Sky Solar LLC | Crockett | Solar | 101.2 | 6562 Friends Ranch 138kV | 2027-12-31 | 2022-02-01 | True |  |  | Signed; security posted
25INR0216 | Blue Sky Storage SLF | UKA North America, LLC | Crockett | Battery storage | 0 | 138 kV Friend Ranch (Bus# 6562) | 2028-06-30 |  |  |  |  | In study
29INR0184 | Gridline Solar | Big Lake Ranch LLC | Crockett | Solar | 400 | 76005 Schneeman Draw LCRA | 2029-07-01 |  |  |  |  | In study
24INR0442 | Midnight Sun Energy Storage | Midnight Sun Energy Storage, LLC | Crockett | Battery storage | 523.86 | 6601 Rio Pecos 138kV | 2028-06-29 | 2025-07-14 | True |  |  | Signed; security posted
29INR0073 | Oasis wind | NextEra Energy Interconnection Holdings, LLC | Crockett | Wind | 350 | 6562 Friend Ranch Station 138kV | 2030-07-01 |  |  |  |  | In study
25INR0489 | Ranchero BESS | Ranchero Battery Facility, LLC | Crockett | Battery storage | 150 | 7053 Noelke 345 kV | 2028-04-30 |  |  |  |  | In study
26INR0647 | Wake Wind Energy Repower | WAKE WIND ENERGY | Crosby | Wind | 252.5 | 59904 Cottonwood 345 | 2027-06-04 | 2014-02-28 |  |  |  | Signed
27INR0334 | Buffalo Jump Wind | BOULEVARD ASSOCIATES, LLC | Culberson | Wind | 740 | 1097 Culberson 345 KV | 2029-07-01 |  |  |  |  | In study
27INR0074 | Desert Hill Solar | NextEra Energy Interconnection Holdings | Culberson | Solar | 250.5 | Tap 138kV El Capitan (#10179) - Black River (#1096). | 2030-07-01 |  |  |  |  | In study
28INR0520 | SunRustler Solar | SunRustler Solar | Culberson | Solar | 301.49 | 11082 MAVRKDRW_8 138kV | 2028-06-15 |  |  |  |  | In study | new
22INR0454 | Wallace Solar | Delaware Ranch Solar, LLC | Culberson | Solar | 36 | Delaware River SW (11112) | 2027-05-14 | 2022-02-07 | True |  |  | Signed; security posted
25INR0006 | Atlanta TxHSR TPSS DS-1 | Texas Central Rail Holdings, LLC | Dallas | Other | 50 | tap 138kV 2429 Watermill E - 3083 Wilmer | 2028-07-15 |  |  |  |  | In study
27INR0457 | watermelon 1 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
27INR0458 | watermelon 2 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
27INR0459 | watermelon 3 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. 1.6 miles from 2427 WATMLL_W5 | 2029-03-01 |  |  |  |  | In study
27INR0460 | watermelon 4 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
28INR0255 | watermelon 5 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
28INR0256 | watermelon 6 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
28INR0257 | watermelon 7 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
28INR0258 | watermelon 8 energy storage | Tempus power management LLC | Dallas | Battery storage | 102.1 | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | 2029-03-01 |  |  |  |  | In study
27INR0474 | Fivemile Wind | 180 Wind LLC | Dawson | Wind | 282.3 | Tap 138kV Lamesa 138kv (10008) to Jim Payne 138kV (18880) | 2029-09-23 |  |  |  |  | In study
26INR0530 | Longview Wind | Longview Wind, LLC | Dawson | Wind | 352.6 | Venturi (Bus #59923) | 2028-12-01 | 2025-12-16 | True |  |  | Signed; security posted | new
29INR0255 | Los Toros Energy Center Solar SLF | Los Toros Energy Center, LLC | Dawson | Solar | 401.56 | Tap 1167 Mustang_8 to 11206 Dillion_P8 138 kV | 2030-03-31 |  |  |  |  | In study
29INR0271 | Los Toros Energy Center Storage SLF | Los Toros Energy Center, LLC | Dawson | Battery storage | 0 | Tap 1167 Mustang_8 to 11206 Dillion_P8 138 kV | 2030-03-31 |  |  |  |  | In study
27INR0501 | Mesquite Creek Windpower Repower | Mesquite Creek Wind LLC | Dawson | Wind | 214.2 | <59900><Long Draw><345> | 2027-12-31 |  |  |  |  | In study
21INR0022 | Red Holly Solar | GreenGo Energy | Dawson | Solar | 260 | tap 345kV 59900 Longdraw - 79641 Farmland | 2029-09-30 | 2020-10-19 |  |  |  | Signed
21INR0033 | Red Holly Storage | GreenGo Energy | Dawson | Battery storage | 50 | tap 345kV 59900 Longdraw - 79641 Farmland | 2028-05-30 | 2020-10-19 |  |  |  | Signed
21INR0029 | Red Holly Storage 1 | GreenGo Energy | Dawson | Battery storage | 50 | tap 345kV 59900 Longdraw - 79641 Farmland | 2028-05-30 | 2020-10-19 |  |  |  | Signed
24INR0555 | Shaula I BESS | Shaula Energy Project LLC | DeWitt | Battery storage | 205.77 | 5380 Shaula 345kV | 2028-06-01 |  |  |  |  | In study
22INR0251 | Shaula I Solar | Shaula Energy Project, LLC | DeWitt | Solar | 205.2 | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | 2028-06-15 | 2022-02-16 | True |  |  | Signed; security posted
22INR0267 | Shaula II Solar | Shaula Energy Project II, LLC | DeWitt | Solar | 205.2 | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | 2028-06-15 | 2022-04-27 | True |  |  | Signed; security posted
23INR0009 | Shaula III Solar | Shaula Energy Project III, LLC | DeWitt | Solar | 205.2 | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | 2025-12-24 |  |  |  |  | In study
26INR0328 | Yorktown BESS | Navitas Energy LLC | DeWitt | Battery storage | 150.49 | (#78575) LCRA Yorktown 138 kV | 2028-12-16 |  |  |  |  | In study
29INR0009 | Aurelius 2 Solar | IP Roman, LLC | Deaf Smith | Solar | 445.4 | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | 2028-09-30 | 2026-07-10 | True |  |  | Signed; security posted
29INR0010 | Aurelius 2 Wind | IP Roman Wind II, LLC | Deaf Smith | Wind | 621.6 | 23908 Deaf Smith station 345kV | 2028-09-30 |  |  |  |  | In study
29INR0361 | Aurelius 3 Natural Gas | IP Roman III Gas, LLC | Deaf Smith | Gas engines | 1275 | 23908 Deaf Smith station 345 kV | 2030-06-30 |  |  |  |  | In study
29INR0011 | Aurelius 3 Solar | IP Roman III, LLC | Deaf Smith | Solar | 445.4 | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | 2030-06-30 |  |  |  |  | In study
29INR0012 | Aurelius 3 Wind | IP Roman III, LLC | Deaf Smith | Wind | 497.3 | 23908 Deaf Smith station 345kV | 2030-06-30 |  |  |  |  | In study
29INR0003 | Aurelius Solar | IP Roman, LLC | Deaf Smith | Solar | 1124.24 | 23908 Deaf Smith station 345 kV | 2028-06-30 | 2025-10-09 | True |  |  | Signed; security posted
29INR0004 | Aurelius Wind | IP Roman Wind, LLC | Deaf Smith | Wind | 621.6 | 23908 Deaf Smith station 345 kV | 2028-06-30 | 2025-10-09 | True |  |  | Signed; security posted
24INR0134 | BRP Hemera BESS | BRP Hemera BESS LLC | Deaf Smith | Battery storage | 206.96 | 345 kV Deaf Smith Substation (#23908, Oncor) | 2029-12-01 |  |  |  |  | In study
23INR0056 | Caliche Mound Solar | CIG DS1 LLC | Deaf Smith | Solar | 406.6 | Mule Deer Switch 23921 (tap 345kV 23906 AJSwope - 23910 Windmill) | 2027-10-26 | 2023-10-12 | True |  |  | Signed; security posted
20INR0255 | Renegade Project | Renegade Renewable LLC | Deaf Smith | Solar | 515.66 | Tap 345kV 23910 Windmill - 23906 AJ Swope | 2028-01-15 | 2021-01-04 | True |  |  | Signed; security posted
24INR0200 | White Tail Solar | Mule Deer Solar LLC | Deaf Smith | Solar | 226.8 | Tap 345kV Windmill (23910) – AJ Swope (23906) | 2028-12-29 |  |  |  |  | In study
24INR0137 | Eagle Springs Solar | Eagle Springs Solar, LLC | Delta | Solar | 77.21 | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | 2027-03-29 | 2024-04-17 | True |  |  | Signed; security posted
24INR0136 | Eagle Springs Storage | Eagle Springs BESS LLC | Delta | Battery storage | 33.94 | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | 2027-03-29 | 2024-04-17 | True |  |  | Signed; security posted
25INR0227 | SERENGETI SOLAR | Abei Energy Green XIV LLC | Delta | Solar | 76.18 | Tap 138kV Enloe Tap (bus# 11806) – Delta sub (bus# 1802) | 2028-09-18 | 2025-12-30 | True |  |  | Signed; security posted | Signed -> Signed; security posted
28INR0454 | Oakley BESS | Oakley BESS LLC | Denton | Battery storage | 200.96 | Tap 138 kV 612 BLUHORSE– 684 SPRING | 2028-09-08 |  |  |  |  | In study
27INR0195 | CORUSCANT BESS | AEU Battery Project III LLC | Dickens | Battery storage | 417.79 | Tap 345kV 59904 COTTONWOOD - 60500 EDITHCLA7A | 2027-04-18 |  |  |  |  | In study
23INR0089 | Donegal Solar | HE-Cottonwood Solar LLC | Dickens | Solar | 201.57 | 59904 Cottonwood 345kV | 2028-11-01 | 2022-07-25 | True |  |  | Signed; security posted
28INR0288 | Outrider BESS | Sanders Hollow Energy Center, LLC | Dickens | Battery storage | 302 | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT. Approximately distance from the POI to Cottonwood Substation is 11.13 miles and to Edith Clarke Substation 77.6 miles. | 2029-06-26 | 2026-06-09 |  |  |  | Signed
28INR0169 | Sanders Hollow Energy Center | Sanders Hollow Energy Center, LLC | Dickens | Wind | 292.6 | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT 01 | 2029-06-23 | 2026-06-09 |  |  |  | Signed
29INR0192 | Spurland Solar I | Spurland Solar I | Dickens | Solar | 302.1 | 59908 Nova Prime 345 345kV | 2028-12-30 | 2026-08-06 | True |  |  | Signed; security posted
29INR0195 | Spurland Solar II | Spurland Solar II | Dickens | Solar | 201.6 | 59908 Nova Prime 345 345kV | 2028-12-30 | 2026-08-06 |  |  |  | Signed
25INR0165 | Timberlakes Solar | Donegalsol | Dickens | Solar | 200.71 | 59904 Cottonwood 345kV | 2028-11-15 |  |  |  |  | In study
25INR0172 | Wolf Spring Solar | Wolf Spring Solar, LLC | Dickens | Solar | 195.8 | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | 2028-08-25 | 2024-08-14 |  |  |  | Signed
25INR0173 | Wolf Spring Storage | Wolf Spring Solar, LLC | Dickens | Battery storage | 202.7 | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | 2028-08-25 | 2024-08-14 |  |  |  | Signed
29INR0107 | 7L Solar SLF | 7L Solar, LLC | Dimmit | Solar | 71.6 | Tap 69kV 5870 Brundage - 5868 Big Wells | 2029-11-13 |  |  |  |  | In study
29INR0108 | 7L Storage SLF | 7L Solar, LLC | Dimmit | Battery storage | 0 | Tap 69kV 5870 Brundage - 5868 Big Wells | 2029-11-13 |  |  |  |  | In study
26INR0555 | Desert Palm BESS | Desert Palm BESS, LLC | Dimmit | Battery storage | 201.3 | 78280 Bevo Substation 138 kV | 2028-09-01 | 2026-07-24 |  |  |  | Signed
25INR0133 | Rose Quartz BESS | Rose Quartz BESS, LLC | Dimmit | Battery storage | 101.41 | Tap 138kV 8283 Asherton - 8613 Bigwells | 2026-12-01 | 2026-07-28 |  |  |  | Signed
26INR0356 | Saluga Ranch Storage | Saluga Ranch Energy, LLC | Dimmit | Battery storage | 125.4 | Asherton 8283 - Big wells 8613 -138 kV | 2027-08-25 |  |  |  |  | In study
23INR0164 | Steppe Reserve Storage | KCE TX 25, LLC | Dimmit | Battery storage | 51.9 | 8283 Asherton 138 kV | 2028-01-01 |  |  |  |  | In study
27INR0208 | Sugarloaf BESS | Sugarloaf Clean Energy LLC | Dimmit | Battery storage | 100.6 | (#80481) PILONCIL4 138KV | 2028-01-31 |  |  |  |  | In study
27INR0373 | Velado Solar SLF | Velado Solar, LLC | Dimmit | Solar | 115.2 | Tap 138kV 78281 Dimmit - 8274 Conoco Chittam | 2028-09-14 |  |  |  |  | In study
27INR0374 | Velado Storage SLF | Velado Solar, LLC | Dimmit | Battery storage | 115.2 | Tap 138kv 78281 Dimmit - 8274 Conoco Chittam. | 2028-09-14 |  |  |  |  | In study
27INR0330 | Wild Horse Desert Solar | Wild Horse Desert Solar, LLC | Dimmit | Solar | 120 | Tap 138kV 8613 Big Well - 8212 Dilley Switch | 2028-07-01 |  |  |  |  | In study
27INR0331 | Wild Horse Desert Storage | Wild Horse Desert Solar, LLC | Dimmit | Battery storage | 90.3 | Tap 138kV 8613 Big Well - 8212 Dilley Switch | 2028-07-01 |  |  |  |  | In study
26INR0556 | Wintergarden BESS | Wintergarden BESS LLC | Dimmit | Battery storage | 201.2 | 8970 Catarina 138 kV | 2028-06-30 |  |  |  |  | In study
28INR0230 | Allthorn BESS | ALLTHORN SOLAR, LLC | Duval | Battery storage | 205.2 | Tap 138 kV BRUNI44A (#8297) - CRESTONI4A (#8695) | 2029-01-15 |  |  |  |  | In study
28INR0229 | Allthorn Solar | ALLTHORN SOLAR, LLC | Duval | Solar | 231.5 | Tap 138 kV BRUNI4A (#8297) - CRESTONI4A (#8695) | 2029-01-15 |  |  |  |  | In study
29INR0124 | Apricot Sun Solar | Apricot Sun Energy Center, LLC | Duval | Solar | 200.84 | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | 2029-09-30 |  |  |  |  | In study
29INR0125 | Apricot Sun Storage | Apricot Sun Energy Center, LLC | Duval | Battery storage | 200.84 | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | 2029-09-30 |  |  |  |  | In study
28INR0040 | Black Hawk Solar | ACE DevCo NC, LLC | Duval | Solar | 251.34 | San Miguel (5901) - Cruce (80079) double circuit transmission line. Requesting interconnection to both lines on the double circuit. This is a planned double circuit with ISD of 2027. | 2030-12-31 |  |  |  |  | In study
29INR0160 | Cazadores Solar | OCI Energy LLC | Duval | Solar | 301.62 | Tap 345 kV (80079) CRUCE7A – (5901) MIGUEL5 CKT 2 | 2029-04-10 |  |  |  |  | In study
28INR0325 | Cielo Vista Power Gas Plant | Cielo Vista Power, LLC | Duval | Gas engines | 343.8 | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | 2029-03-30 |  |  |  |  | In study
28INR0497 | Cielo Vista Power II | Cielo Vista Power II, LLC | Duval | Gas engines | 350.38 | TAP 345 kV BUS # 5901 MIGUEL5 - BUS #80280 CRUCE SM 7A Ckt-1 | 2029-03-30 |  |  |  |  | In study
27INR0150 | Cielo Vista Solar | Cielo Vista Solar, LLC | Duval | Solar | 503.34 | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | 2029-03-30 |  |  |  |  | In study
29INR0115 | Cielo Vista Storage | Cielo Vista Storage, LLC | Duval | Battery storage | 310.8 | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | 2029-03-30 |  |  |  |  | In study
26INR0393 | Dove Wing Storage | Dove Wing Energy Center, LLC | Duval | Battery storage | 122.21 | 138 kV Zenaida Bus# 80043 | 2029-09-30 |  |  |  |  | In study
29INR0146 | Estrella Dorada Wind | Estrella Dorada Wind Farm, LLC | Duval | Wind | 306 | Tap 345 kV 80079 Cruce - 5901 San Miguel Ckt 2 | 2029-07-13 |  |  |  |  | In study
28INR0168 | Guajillo Wind | Guajillo Wind LLC | Duval | Wind | 199.9 | Tap 345 kV 80079 Cruce - 5901 San Miguel CKT 01 | 2028-09-01 |  |  |  |  | In study
26INR0391 | Jumping Cactus Storage | Dove Wing Energy Center, LLC | Duval | Battery storage | 125.32 | 138 kV Zenaida Bus# 80043 | 2029-09-30 |  |  |  |  | In study
21INR0546 | Anchor Wind III | RANCHLAND WIND PROJECT LLC | Eastland | Wind | 16 | 345 kV Aspire Station (68011) | 2025-12-29 | 2020-11-30 | True | 2021-11-29 | 2022-12-13 | Approved for synchronization
26INR0468 | Basketflower Solar | Basketflower Solar, LLC | Eastland | Solar | 183 | Tap 138kV Risingstar (285) - Nimrod (289) | 2027-12-31 |  |  |  |  | In study
26INR0467 | Basketflower Storage | Basketflower Solar, LLC | Eastland | Battery storage | 92 | Tap 138kV Risingstar (285) - Nimrod (289) | 2027-12-31 |  |  |  |  | In study
26INR0603 | Damia Solar | Damia Solar, LLC | Eastland | Solar | 306 | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | 2028-07-01 |  |  |  |  | In study
26INR0602 | Damia Storage | Damia Solar, LLC | Eastland | Battery storage | 153 | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | 2028-07-01 |  |  |  |  | In study
29INR0275 | Richardson McClung Ranch BESS | Rising Star Energy Center, LLC | Eastland | Battery storage | 205.49 | 33285 Rising Star 138 kV | 2029-11-30 |  |  |  |  | In study
29INR0274 | Richardson McClung Ranch Solar | Rising Star Energy Center, LLC | Eastland | Solar | 251.95 | 33285 Rising Star 138 kV | 2029-11-30 |  |  |  |  | In study
23INR0538 | Roadrunner Crossing BESS SLF | Roadrunner Crossing BESS | Eastland | Battery storage | 0 | 68051 Reata 354kV | 2026-08-30 | 2025-02-15 | True | 2025-11-14 | 2025-12-10 | Approved for synchronization
26INR0726 | Roadrunner Crossing Wind (Uprate) | Roadrunner Wind, LLC | Eastland | Wind | 7.32 | 68051 Reata 345kV | 2027-06-30 |  | True |  |  | Signed; security posted
18INR0064 | Silver Star repower | Silver Star I Power Partners, LLC | Eastland | Wind | -7.2 | 1642 Flat Creek 138kV | 2026-12-31 | 2018-10-16 | True |  | 2020-07-28 | Approved for synchronization
28INR0195 | Star Grass Renewable Energy Solar SLF | Star Grass Renewable Energy LLC | Eastland | Solar | 150 | Tap 138kV 6310 Putnam - 3378 Carbon_8 | 2029-09-14 |  |  |  |  | In study
28INR0197 | Star Grass Renewable Energy Storage SLF | Star Grass Renewable Energy LLC | Eastland | Battery storage | 0 | Tap 138kV 6310 Putnam - 3378 Carbon_8 | 2029-09-14 |  |  |  |  | In study
26INR0574 | Apple BESS | Apple Infra LLC | Ector | Battery storage | 9.9 | Station Name - Apple Oncor 5-digit code - APPLE Oncor XFMR # - 1 ERCOT Bus Name - APPLE_9 ERCOT Bus # 1276 EROCT Load Name - LDLXFMR1 Substation Transmission kV - 138 | 2026-11-27 | 2025-04-03 | True | 2026-08-04 |  | Approved for energization
26INR0287 | Firebird BESS | TX BESS 6, LLC | Ector | Battery storage | 102.65 | Tap 138kV #1099 Southwestern Portland Tap - #1052 Rexall | 2029-06-29 |  |  |  |  | In study
28INR0227 | GPlains Solar | Gypsum Plains Solar, LLC | Ector | Solar | 151.29 | Tap 138kV #1013 WOLFSS_8 - #1103 SANDHLTA_8 | 2029-06-21 |  |  |  |  | In study
28INR0228 | GPlains Storage | Gypsum Plains Solar, LLC | Ector | Battery storage | 51.27 | Tap 138kV WOLFSS_8 (1013) - SANDHLTA_8 (1103) | 2029-06-21 |  |  |  |  | In study
21INR0268 | Greyhound Solar | Rockhound Solar 2, LLC dba "Greyhound Solar" | Ector | Solar | 335.45 | Tap 345kV 11010 Wolf - 1018 Moss | 2026-06-30 | 2022-01-15 | True | 2025-11-26 | 2026-04-24 | Approved for synchronization
28INR0205 | Gypsum Plains Solar | Gypsum Plains Solar, LLC | Ector | Solar | 503.12 | Tap 345kv line Wolf BUS# 11010 - Reiter BUS#18544 | 2029-06-21 |  |  |  |  | In study
28INR0217 | Gypsum Plains Storage | Gypsum Plains Solar, LLC | Ector | Battery storage | 211.14 | Tap 345kv 11010 Wolf - 18544 Reiter | 2029-06-21 |  |  |  |  | In study
30INR0141 | Jackrabbit Flats Solar | Jackrabbit Flats Solar LLC | Ector | Solar | 401.33 | Tap 345 kV 1185 Midland County NW - 1018 Moss | 2030-06-29 |  |  |  |  | In study
27INR0422 | M-Bar BESS I | M-Bar Energy I, LLC | Ector | Battery storage | 82.1 | 1141 Holt Switch Substation 138 kV | 2028-09-18 |  |  |  |  | In study
27INR0421 | M-Bar Solar I | M-Bar Energy I, LLC | Ector | Solar | 30.21 | 1141 Holt Switch Substation 138kV | 2028-09-18 |  |  |  |  | In study
26INR0273 | Momentum Hazy Jane BESS | MOMENTUM HAZY JANE, LLC | Ector | Battery storage | 125.5 | Tap 138kV 1102 Judkins - 1110 Edward | 2028-02-26 |  |  |  |  | In study
23INR0471 | Ophelia Solar | Ophelia Solar | Ector | Solar | 110.5 | Tap 138 kV Raceway Switch #18663 - Shin Oak POD #11128 | 2028-09-19 |  |  |  |  | In study
25INR0140 | Seragio BESS | Seragio BESS, LLC | Ector | Battery storage | 201.13 | 11140 ECTRCNTYN_8 138kV | 2028-04-30 |  |  |  |  | In study
21INR0265 | Sisters Solar | Oberon Solar LLC | Ector | Solar | 100.51 | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | 2028-09-23 | 2025-07-01 | True |  |  | Signed; security posted
27INR0570 | Sisters Solar - Phase 2 | Oberon Solar IV, LLC | Ector | Solar | 201.51 | 10009 McGee 345 kV | 2028-09-23 |  |  |  |  | In study
28INR0177 | Sisters Solar II | Oberon Solar III, LLC | Ector | Solar | 205.54 | tap 345kV 11010 Wolf Switching Station - 10012 Meteor | 2028-12-15 |  |  |  |  | In study
25INR0301 | Van Zandt Energy Storage | Rocky Mountain Energy Holdings, LLC | Ector | Battery storage | 256 | 1027 Odessa EHV Switch 138 kV | 2027-05-15 | 2025-03-03 |  |  |  | Signed
27INR0493 | Velociraptor BESS I | Velociraptor BESS I, LLC | Ector | Battery storage | 246 | 10012 METEOR_5 Substation 345kV | 2029-12-01 |  |  |  |  | In study
28INR0323 | Velociraptor BESS II | Velociraptor BESS II, LLC | Ector | Battery storage | 246.12 | Tap Wolf (#11010) - Reiter Switch (#18544) Ckt1 345KV | 2029-12-01 |  |  |  |  | In study
22INR0218 | Velociraptor Solar I | Velociraptor Solar I, LLC | Ector | Solar | 241.67 | #10012 METEOR 5 Substation 345kV | 2029-12-01 |  |  |  |  | In study
28INR0322 | Velociraptor Solar II | Velociraptor Solar II, LLC | Ector | Solar | 241.81 | Tap Wolf (#11010) - Reiter Switch (#18544) Ckt1 345KV | 2029-12-01 |  |  |  |  | In study
27INR0417 | Bluebonnet Trail Solar | Bluebonnet trail solar LLC | Ellis | Solar | 150.9 | Tap 345 kV (#2427) WATMLL_W5 - (#2466) BIGONION_5 | 2028-09-19 |  |  |  |  | In study
28INR0531 | Crape Myrtle Solar | Crape Myrtle Solar LLC | Ellis | Solar | 140.69 | Tap 345 kV 2255 OLDCNTRY_5 - 3376 NOTUS_5 | 2030-04-15 |  |  |  |  | In study
24INR0178 | Cumulus Grid BESS | Cumulus Grid, LLC | Ellis | Battery storage | 210.74 | 1906 Venus Switch Substation 345kV | 2028-01-01 | 2025-06-03 | True |  |  | Signed; security posted
28INR0100 | Digital Ranch Gas | MCV 1 LLC | Ellis | Gas engines | 378 | #1906 Venus Switch 345 kV | 2030-04-15 |  |  |  |  | In study
25INR0495 | Dolomite Storage | BT Wilson Storage, LLC | Ellis | Battery storage | 125.7 | 218 Rockett 69kV | 2026-12-01 |  |  |  |  | In study
28INR0355 | Galaxy I Solar | Galaxy Solar, LLC | Ellis | Solar | 99.42 | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | 2028-10-30 |  |  |  |  | In study
27INR0219 | Galaxy Solar | Galaxy Solar, LLC | Ellis | Solar | 177.32 | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | 2028-10-30 |  |  |  |  | In study
28INR0385 | Galaxy Solar 2 | Galaxy Solar 2, LLC | Ellis | Solar | 301.64 | 3/4-Breaker Ring Bus at 345kV Venus Switch (#1907) BKR 4920 - Navarro Switch (LST) (#68091) BKR 3B3134/3B3127 | 2029-10-30 |  |  |  |  | In study
27INR0220 | Galaxy Storage | Galaxy Solar, LLC | Ellis | Battery storage | 155 | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | 2028-10-30 |  |  |  |  | In study
28INR0387 | Galaxy Storage 2 | Galaxy Solar 2, LLC | Ellis | Battery storage | 201.87 | 3/4-Breaker Ring Bus at 345kV Venus Switch (#1907) BKR 4920 - Navarro Switch (LST) (#68091) BKR 3B3134/3B3127 | 2029-10-30 |  |  |  |  | In study
27INR0469 | Kickstart Energy Storage I | Kickstart Infrastructure LLC | Ellis | Battery storage | 1.44 | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | 2029-09-30 |  |  |  |  | In study
27INR0470 | Kickstart Energy Storage II | Kickstart Infrastructure LLC | Ellis | Battery storage | 1.44 | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | 2029-09-30 |  |  |  |  | In study
27INR0471 | Kickstart Energy Storage III | Kickstart Infrastructure LLC | Ellis | Battery storage | 1.44 | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | 2029-09-30 |  |  |  |  | In study
27INR0472 | Kickstart Energy Storage IV | Kickstart Infrastructure LLC | Ellis | Battery storage | 1.44 | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | 2029-09-30 |  |  |  |  | In study
29INR0217 | Kickstart Energy Storage V | Kickstart Infrastructure LLC | Ellis | Battery storage | 999 | 345 KV Venus 1906 to Fort Smith 3389 | 2029-12-31 |  |  |  |  | In study
29INR0218 | Kickstart Energy Storage VI | Kickstart Infrastructure LLC | Ellis | Battery storage | 1026.2 | 345 KV Venus 1907 to Navarro 68091 | 2029-12-31 |  |  |  |  | In study
22INR0523 | Midlothian 4 repower | MIDLOTHIAN ENERGY, LLC | Ellis | Gas turbine | 18 | 1940 Midlothian ANP 345kV | 2028-06-03 |  |  |  |  | In study
21INR0534 | Midlothian Unit 2 repower | MIDLOTHIAN ENERGY, LLC | Ellis | Gas turbine | 18 | 1939 Midlothian ELP 345kV | 2028-06-03 |  |  |  |  | In study
22INR0543 | Midlothian Unit 3 repower | MIDLOTHIAN ENERGY, LLC | Ellis | Gas turbine | 18 | 1940 Midlothian ELP 345kV | 2028-06-03 |  |  |  |  | In study
28INR0495 | Old Alma Road Solar | Wildcat Renewables, LLC | Ellis | Solar | 20.06 | 2326 ENNS_SE_8 138kV | 2028-10-31 |  |  |  |  | In study | new
21INR0362 | Oystercatcher Solar | Oystercatcher Solar, LLC | Ellis | Solar | 198.43 | tap 345kV 1906 Venus - 68091 Navarro | 2027-01-29 | 2021-08-20 |  | 2026-09-02 |  | Approved for energization | Signed -> Energized
26INR0241 | Sol Marina SLF Energy Center | Sol Marina Energy Center, LLC | Ellis | Solar | 171.09 | Tap 345kV Stainback Switch (bus# 2217) – Big Onion Switch (bus# 2466) | 2027-10-29 | 2025-04-25 | True |  |  | Signed; security posted
25INR0005 | Tokyo TxHSR TPSS EW-1 | Texas Central Rail Holdings, LLC | Ellis | Other | 50 | tap 138kV 2241 Ennis W - 2321 Waxahachie | 2028-07-15 |  |  |  |  | In study
29INR0196 | Two Step Solar | Two Step Solar, LLC | Ellis | Solar | 401.62 | Tap 345kV 1907 Venus - 68091 Navarro | 2029-09-17 |  |  |  |  | In study
23INR0216 | Venus Mill Storage | AIH Texas Acquisitions, LLC | Ellis | Battery storage | 100.8 | 138 kV Tap #442 Rail Port - #1905 Griffith | 2027-12-31 | 2025-12-24 |  |  |  | Signed
29INR0264 | Victory Ellis – Gas | Victory Ellis, LLC | Ellis | Gas turbine | 465.92 | Tap 345kV Nimbus (2249) – Big Onion (2466) & Stainback (2217) – Elrod Switch (3159) DCKT | 2030-09-28 |  |  |  |  | In study
28INR0529 | Victory Ellis–BESS | Victory Ellis, LLC | Ellis | Battery storage | 452.99 | Tap 345kV Nimbus (2249) – Big Onion (2466) & Stainback (2217) – Elrod Switch (3159) DCKT | 2030-09-28 |  |  |  |  | In study
23INR0202 | Erath County Solar | Erath County Solar, LLC | Erath | Solar | 207.4 | tap 345kV 68020 Romney1E - 68030 KopperlW | 2029-01-31 | 2023-06-01 | True |  |  | Signed; security posted
28INR0290 | Field Marshal Storage | Field Marshal Storage LLC | Erath | Battery storage | 150.8 | Dublin (1636) - Fullhouse (1652) 138kV | 2029-05-07 |  |  |  |  | In study
25INR0661 | McCrae Energy Storage | McCrae Energy Storage, LLC | Erath | Battery storage | 306.35 | Tap 345 kV 1900 COMCHPKW_5 - 1440 COMCHESS1_5 | 2028-09-25 | 2025-12-30 |  |  |  | Signed
25INR0440 | Bronc Rodeo Solar Project | Energiekontor US Texas SP 16 LLC | Falls | Solar | 105.7 | Tap 138 kV Line from Temple Pecan Creek (#3420) to the Cow Bayou Switch (#3385) | 2029-04-16 |  |  |  |  | In study
29INR0105 | Falls County Storage | Aurora Solar LLC | Falls | Battery storage | 60 | 3711 BALSW 345kV | 2029-10-01 |  |  |  |  | In study
28INR0147 | Fallstone Solar SLF | Fallstone Solar, LLC | Falls | Solar | 60.55 | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | 2028-09-21 |  |  |  |  | In study
28INR0149 | Fallstone Storage SLF | Fallstone Solar, LLC | Falls | Battery storage | 0 | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | 2028-09-21 |  |  |  |  | In study
28INR0262 | Pasture Rose Wind | Pasture Rose, LLC | Falls | Wind | 198.7 | TAP 345KV BUS 3721 STRANGER SW - 3711 BALE_S5 | 2029-06-07 |  |  |  |  | In study
25INR0297 | RIVERBEND SOLAR SLF | Riverbend Renewables, LLC | Falls | Solar | 301.6 | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | 2027-12-31 |  |  |  |  | In study
25INR0311 | RIVERBEND STORAGE SLF | Riverbend Renewables, LLC | Falls | Battery storage | 0 | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | 2027-12-31 |  |  |  |  | In study
24INR0040 | Rosebud Solar SLF | Rosebud Solar, LLC | Falls | Solar | 130 | Tap 69kV 67 BAGGINS - 69 BARCLAY | 2028-01-15 |  |  |  |  | In study
25INR0341 | Rosebud Storage SLF | Rosebud Storage, LLC | Falls | Battery storage | 0 | Tap 69 kV 67 BAGGINS - 69 BARCLAY | 2028-01-15 |  |  |  |  | In study
20INR0205 | Roseland Solar | Enel Green Power Roseland Solar, LLC | Falls | Solar | 254 | tap 345kV 3390 Jewett - 3399 Ratsnake | 2026-10-05 | 2020-12-10 | True | 2022-06-07 | 2022-09-26 | Approved for synchronization
22INR0506 | Roseland Solar II | Enel Green Power Roseland Solar, LLC | Falls | Solar | 254 | tap 345kV 3390 Jewett - 3399 Ratsnake | 2026-10-05 | 2020-12-10 | True | 2022-06-07 | 2022-09-26 | Approved for synchronization
20INR0106 | Wang Solar SLF | BT Yixin Solar, LLC | Falls | Solar | 144.6 | tap 345kV 3409 LakeCr1 - 3414 TempSS | 2029-01-31 |  |  |  |  | In study
22INR0514 | Wang Storage SLF | BT Yixin Solar, LLC | Falls | Battery storage | 0 | tap 345kV 3409 LakeCr1 - 3414 TempSS | 2029-01-31 |  |  |  |  | In study
28INR0286 | 2 Cedar Wind | SunWR, LLC | Fannin | Wind | 180 | Tap 345kV 1729 Valley South – Anna Switch 2373 | 2028-05-02 |  |  |  |  | In study
29INR0191 | Black Mountain Fannin Gas | Black Mountain Power LLC | Fannin | Gas combined cycle | 990.59 | 345 KV #1729 Valley South | 2030-04-26 |  |  |  |  | In study
27INR0145 | Steelhead Energy Storage | GRS BESS TEXAS SEVEN, LLC | Fannin | Battery storage | 192.1 | Tap 1593 BONHAM_P8 to Allens Creek 1835 138kV | 2029-04-30 |  |  |  |  | In study
29INR0249 | Lightcycle Energy Storage | Lightcycle Energy Storage LLC | Fayette | Battery storage | 409.69 | 9073 HOLMAN 345 kV | 2030-03-01 |  |  |  |  | In study
25INR0512 | Monument Hill Solar | RWE Solar Development, LLC | Fayette | Solar | 200 | Tap 345kV 7055 Fayette - 9074 Lytton Springs | 2029-06-30 | 2025-12-22 |  |  |  | Signed
28INR0150 | South Tripoint BESS | South Triangle Energy, LLC | Fayette | Battery storage | 204.5 | 7286 L_FAYETT8_1Y 138kV | 2030-05-30 |  |  |  |  | In study
25INR0189 | Staccato BESS | Staccato Storage, LLC | Fayette | Battery storage | 201.8 | 138kV WARDA #7312. | 2027-05-28 | 2024-08-27 | True |  |  | Signed; security posted
28INR0415 | Alkali Creek Wind | Alkali Creek Wind, LLC | Fisher | Wind | 474.4 | Tap 345 kV BUS #1048 Tonkawa - BUS #11050 Dusty Road | 2028-12-01 |  |  |  |  | In study
28INR0478 | Alkali Creek Wind 2 | Alkali Creek Wind, LLC | Fisher | Wind | 250.3 | Tap 345 kV BUS #1048 Tonkawa - BUS #11050 Dusty Road | 2028-12-01 |  |  |  |  | In study
28INR0456 | Brazos Energy Security | Golden Spread Electric | Fisher | Gas combined cycle | 3000 | Tap 345 kV (Bus #1048) Tonkawa Switch – (Bus #11050) Dusty Road | 2030-09-22 |  |  |  |  | In study | new
21INR0031 | Indigo Solar | Innovative Solar 245, LLC | Fisher | Solar | 150 | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | 2027-09-17 | 2020-09-15 | True |  |  | Signed; security posted
28INR0067 | Indigo Solar 3 | Indigo solar 3 | Fisher | Solar | 800 | Tap Line Segment Tankawa (Bus #1048) to Graham (Bus #1430) | 2028-11-01 |  |  |  |  | In study
24INR0496 | Indigo Storage | Innovative Solar 245, LLC | Fisher | Battery storage | 60 | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | 2027-09-17 | 2026-03-27 | True |  |  | Signed; security posted
25INR0528 | Indigo Storage 2 | Innovative Solar 245, LLC | Fisher | Battery storage | 60 | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | 2027-09-17 | 2026-03-27 | True |  |  | Signed; security posted
25INR0529 | Indigo Storage 3 | Innovative Solar 245, LLC | Fisher | Battery storage | 60 | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | 2027-09-17 | 2026-03-27 | True |  |  | Signed; security posted
25INR0530 | Indigo Storage 4 | Innovative Solar 245, LLC | Fisher | Battery storage | 60 | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | 2027-09-17 | 2026-03-27 | True |  |  | Signed; security posted
25INR0547 | Indigo solar 2 | Indigo Solar 2 | Fisher | Solar | 180 | Tap 345KV 68001 Clayton 345KV -68000 WShack Ckt 2 | 2027-07-15 |  |  |  |  | In study
25INR0632 | Jenna Eco-Electric Solar | Clean Energy Holdings, LLC | Fisher | Solar | 576.3 | Tap 345 kV 1048 Tonkawa Switch - 1430 Graham SES | 2029-04-16 |  |  |  |  | In study
29INR0399 | Rugged Prairie Wind | Rugged Prairie Wind, LLC | Fisher | Wind | 294.14 | Tap 345kV BUS #11305 Dermott- BUS #60706 Kirchhef | 2029-12-01 |  |  |  |  | In study | new
19INR0080 | Whitehorse Wind | MESQUITE STAR SPECIAL LLC | Fisher | Wind | 418.9 | 68001 Clayton 345kV | 2026-12-31 | 2018-12-05 | True | 2019-12-12 | 2019-12-27 | Approved for synchronization
29INR0148 | Big Field Solar | Big Field Solar Energy LLC | Foard | Solar | 506.17 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2029-12-31 |  |  |  |  | In study
28INR0535 | Daisy Solar | Daisy Solar LLC | Foard | Solar | 200.92 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2029-06-30 |  |  |  |  | In study
29INR0326 | Montgomery Ranch 2 Wind | RWE Clean Energy Development, LLC | Foard | Wind | 301.5 | 60059 Penumbra 345-kV | 2030-06-02 |  |  |  |  | In study
28INR0476 | Pease River Solar | Pease River Solar LLC | Foard | Solar | 276.35 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2029-06-30 |  |  |  |  | In study
23INR0140 | Seine BESS | BRP Seine BESS LLC | Foard | Battery storage | 308.88 | 60500 Edith Clarke 345kV | 2027-10-01 | 2024-12-01 | True |  |  | Signed; security posted
26INR0375 | Avalon BESS | Avalon BESS, LLC | Fort Bend | Battery storage | 522.12 | Tapping the 345 kV Line from Smithers (Bus# 44650) to Bellaire (Bus# 47000). | 2026-12-01 | 2024-12-17 |  |  |  | Signed
26INR0525 | Bypass BESS II | Bypass BESS II LLC | Fort Bend | Battery storage | 205.86 | 44000 Wa Parish 345 kV | 2028-04-30 |  |  |  |  | In study
24INR0405 | Crowned Heron BESS | RWE Renewables | Fort Bend | Battery storage | 154.2 | WA Parish 345 kV Bus #44000 | 2026-10-02 | 2023-06-26 | True | 2025-12-08 | 2026-01-21 | Approved for synchronization
24INR0493 | Crowned Heron BESS 2 | RWE Renewables | Fort Bend | Battery storage | 154.2 | WA Parish 345 kV Bus #44000 | 2026-10-02 | 2024-08-20 | True | 2026-01-27 | 2026-04-06 | Approved for synchronization
25INR0372 | Elan BESS | Elan BESS, LLC | Fort Bend | Battery storage | 202.65 | 42380 Needville 138kV | 2026-12-31 |  |  |  |  | In study
29INR0145 | Elysium Energy Center BESS | Adapture Solar Development | Fort Bend | Battery storage | 100 | 44030 Arcola 138 kV | 2030-01-17 |  |  |  |  | In study
23INR0556 | IEP Orchard BESS | IEP Tejas Verde LLC | Fort Bend | Battery storage | 9.99 | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | 2027-12-31 | 2023-08-09 | True | 2024-11-12 | 2024-12-06 | Approved for synchronization
25INR0242 | Pato Blanco Storage | TX BESS 4, LLC | Fort Bend | Battery storage | 71.34 | Tap 138 kV 44010 W A Parish - 42980 NASH___S02_8 | 2028-12-15 |  |  |  |  | In study
27INR0627 | Redbird BESS | Redbird BESS, LLC | Fort Bend | Battery storage | 100 | 44090 Cedar Creek 345kV | 2029-03-01 |  |  |  |  | In study
26INR0201 | Rock Rose BESS | Rock Rose Energy Storage LLC | Fort Bend | Battery storage | 208.5 | 44070 Whaley 345 kV | 2027-03-19 | 2024-06-15 | True |  |  | Signed; security posted
27INR0142 | UNICORN BESS | Unicorn Energies | Fort Bend | Battery storage | 278.98 | Tap 138 kV Wa Parish (#44015) - Crabb River Road Line (#44170) Line; CNP | 2027-09-01 |  |  |  |  | In study
25INR0504 | Lazy Frog Solar SLF | Lazy Frog Solar, LLC | Franklin | Solar | 100.4 | 11688 Thorn Tree Switch 345kV | 2028-04-17 |  |  |  |  | In study
25INR0506 | Lazy Frog Storage SLF | Lazy Frog Solar, LLC | Franklin | Battery storage | 0 | 11688 Thorn Tree Switch 345kV | 2028-04-17 |  |  |  |  | In study
24INR0150 | Lupinus Solar 1 | Lupinus Solar, LLC | Franklin | Solar | 162.31 | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | 2027-09-13 | 2025-06-26 | True |  |  | Signed; security posted
24INR0154 | Lupinus Solar 2 | Lupinus Solar 2, LLC | Franklin | Solar | 242.31 | Hagansport Switch (old Monticello Tap bus# 1794) | 2027-04-03 | 2025-03-04 | True |  |  | Signed; security posted
24INR0153 | Lupinus Storage 1 | Lupinus Solar, LLC | Franklin | Battery storage | 84.01 | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | 2027-09-13 |  | True |  |  | Signed; security posted
24INR0155 | Lupinus Storage 2 | Lupinus Solar 2, LLC | Franklin | Battery storage | 124.55 | Hagansport Switch (old Monticello Tap bus# 1794) | 2027-04-03 | 2025-03-04 | True |  |  | Signed; security posted
30INR0071 | Prairie Ridge (Gas - CC) | Tenaska Power Generation, LLC | Franklin | Gas combined cycle | 1660.4 | Tap 345 kV 11699 Woodard – 1695 Monticello | 2032-06-01 |  |  |  |  | In study
26INR0082 | Amerada Solar | Amerada Solar, LLC | Freestone | Solar | 301.57 | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | 2028-12-30 |  |  |  |  | In study
26INR0084 | Amerada Storage | Amerada Solar, LLC | Freestone | Battery storage | 150.78 | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | 2028-07-21 |  |  |  |  | In study
27INR0316 | Avant Prairie BESS | Avant Prairie ESS LLC | Freestone | Battery storage | 201.72 | Tap 345kV BIGBRNE (#3380) - JEWETT (#3390) CKT 1 | 2029-04-16 |  |  |  |  | In study
29INR0298 | BM Freestone Energy Center | Black Mountain Energy Storage II | Freestone | Gas combined cycle | 990.6 | Loop Big Brown E to Navarro Ckt 1(PTI#3380-68091) and Big Brown W to Tarantulla Ckt 1 (PTI#3381-3344) at 31.813367° -96.147730° | 2029-09-20 |  |  |  |  | In study
24INR0269 | Bar Candela Solar SLF | Bar Candela Solar Project LLC | Freestone | Solar | 200.3 | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | 2029-05-16 | 2025-05-06 |  |  |  | Signed
24INR0271 | Bar Candela Storage SLF | Bar Candela Storage Project LLC | Freestone | Battery storage | 0 | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | 2029-05-16 | 2025-05-06 |  |  |  | Signed
26INR0098 | Douie Solar | Buffalo Spring Solar LLC | Freestone | Solar | 221.2 | Tap 138 kV 3501 Sea way Teague - 3394 Jewett | 2028-04-18 | 2026-03-08 | True |  |  | Signed; security posted
26INR0033 | Fairway Storage | Fairway Storage LLC | Freestone | Battery storage | 120.3 | Tap 138kV 3503 FAIRWPOD_8 - 196 FAIRFIELD | 2027-09-24 | 2025-08-11 | True |  |  | Signed; security posted
28INR0055 | Freestone Battery Storage Project | Freestone Power Generation, LLC | Freestone | Battery storage | 210.5 | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | 2028-12-16 |  |  |  |  | In study
29INR0150 | Jewett Energy Center 1 Gas | Jewett Energy Center LLC | Freestone | Gas combined cycle | 1274 | Tap #3391 JEWETT_N5 - #46020 LMEST_POI_5 and Tap #3390 JEWETT_S5 - #46020 LMEST_POI_5 | 2029-11-01 | 2026-07-15 |  |  |  | Signed
25INR0169 | Piedra BESS | Piedra Solar, LLC | Freestone | Battery storage | 103.65 | Tap 345-kV line Navarro (68091) – Limestone (46020) | 2027-12-01 | 2024-07-02 | True |  |  | Signed; security posted
25INR0168 | Piedra Solar | Piedra Solar, LLC | Freestone | Solar | 281.7 | Tap 345-kV line Navarro (68091) – Limestone (46020)) | 2027-01-15 | 2024-07-02 | True | 2026-07-27 | 2026-08-26 | Approved for synchronization
24INR0289 | Ratcliff Solar | Greenalia Solar Power Ratcliff | Freestone | Solar | 85.74 | Tap 138kV 3279 Long Lake Tap Switch - 3280 Long Lake | 2029-04-07 |  |  |  |  | In study
27INR0186 | Silver Dollar Solar | Silver Dollar Solar Project, LLC | Freestone | Solar | 301.9 | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | 2029-10-31 |  |  |  |  | In study
27INR0187 | Silver Dollar Storage | Silver Dollar Solar Project, LLC | Freestone | Battery storage | 153.1 | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | 2029-10-31 |  |  |  |  | In study
29INR0119 | Simsboro Storage | Simsboro Storage LLC | Freestone | Battery storage | 301.6 | Tap Outlaw (3386) – Limestone (46020) | 2029-03-31 |  |  |  |  | In study
27INR0651 | Three Canes Gas P1 | CleanAI, LLC | Freestone | Gas engines | 0 | #3344 Tarantula Switching Station | 2027-11-30 |  |  |  |  | In study
27INR0652 | Three Canes Gas P2 | CleanAI, LLC | Freestone | Gas engines | 0 | Tap on the 345 kV Outlaw Switch (bus #3386) to Limestone Plant Station (bus #46020) Transmission Line | 2027-11-30 |  |  |  |  | In study
24INR0532 | Timber Cove Solar SLF | Freestone Solar, LLC | Freestone | Solar | 100.5 | Tap 138 kV 212 Winkler - 3510 Pin Oak | 2027-06-01 |  |  |  |  | In study
26INR0394 | Timber Cove Storage SLF | Freestone Solar, LLC | Freestone | Battery storage | 0 | Tap 138 kV 212 Winkler - 3510 Pin Oak | 2027-06-01 |  |  |  |  | In study
28INR0080 | Turtle Rock Storage | Turtle Rock Energy Center, LLC | Freestone | Battery storage | 135.59 | Tap 138 kV 13501 Clayhill to 13681 Reed | 2028-07-02 |  |  |  |  | In study
24INR0117 | Utley Solar | Palmera Solar Development, LLC | Freestone | Solar | 221.78 | Tap 345kV 3381 Big Brown Switch - 3391 Jewett | 2028-05-11 | 2025-12-18 | True |  |  | Signed; security posted
28INR0411 | Black Creek BESS | Francitas Renewables LLC | Frio | Battery storage | 120 | New tap between line Bigfoot4A (8221) - MooreSw8 (5827) | 2029-03-20 |  |  |  |  | In study
28INR0461 | Dilley Solar | AETS Development Holdings LLC | Frio | Solar | 200.7 | Tap 138 kV 8212 DILLEY SWITCH AEP - 8613 BIG WELLS | 2028-06-30 |  |  |  |  | In study
27INR0362 | Hamlet Solar SLF | Hamlet Solar, LLC | Frio | Solar | 201 | Tap 138kV #5895 PEARSALL - #5827 MOORE | 2029-09-04 |  |  |  |  | In study
27INR0363 | Hamlet Storage SLF | Hamlet Solar, LLC | Frio | Battery storage | 201 | Tap 138kV #5895 PEARSALL -#5827 MOORE | 2029-09-04 |  |  |  |  | In study
21INR0483 | Morrow Lake Storage | Morrow Lake Storage, LLC | Frio | Battery storage | 201.13 | Morrow Lake Switch 138kV (5896) | 2028-09-30 |  |  |  |  | In study
21INR0012 | Air Products GCA | Air Products | Galveston | Gas steam turbine | 14 | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | 2025-12-31 | 2020-08-07 | True | 2023-11-07 | 2024-07-10 | Approved for synchronization
23INR0485 | Hacienda Storage | Galveston Energy Storage LLC | Galveston | Battery storage | 205.8 | 38745 Attwater 138kV | 2027-12-01 |  |  |  |  | In study
30INR0003 | Hecate Energy Jamaica Wind | Hecate Energy LLC | Galveston | Wind | 1029.39 | 42000 P. H. Robinson 345kV | 2030-06-01 |  |  |  |  | In study
25INR0310 | IEP Blackhawk | IEP Texas Verde II, llc | Galveston | Battery storage | 100 | 38740 Heights Substation 138kV | 2026-12-01 |  |  |  |  | In study
24INR0281 | Red Egret BESS | Red Egret LLC | Galveston | Battery storage | 310.58 | 38820 FREEWAY PARK 138KV | 2027-11-17 | 2023-06-07 | True |  |  | Signed; security posted
26INR0340 | SOUTHERN SELECT ENERGY STORAGE | SOUTHERN SELECT ENERGY STORAGE LLC | Galveston | Battery storage | 204.85 | Bus Name: TNHEIGHTS_1 Bus Number: 38740 | 2027-05-24 | 2025-05-09 | True |  |  | Signed; security posted
25INR0262 | Shepard Energy Storage | Shepard Energy Storage LLC | Galveston | Battery storage | 256.79 | # 38900 Hidden Lakes - # 42015 PHR 138 KV | 2028-06-30 | 2024-01-17 | True |  |  | Signed; security posted
28INR0465 | Valcrest BESS | Flexen USA LLC | Galveston | Battery storage | 154.25 | tap 138 kV 43500 WEBSTR_B138A - 48403 W_GALV01TP_8 | 2028-12-31 |  |  |  |  | In study
28INR0490 | Vertus Energy Storage 2 | Vertus Energy Storage 2 LLC | Galveston | Battery storage | 204.93 | 38830 TNMAINLAND1 138 KV | 2028-02-15 |  |  |  |  | In study
23INR0290 | Zeya BESS | BRP Zeya BESS LLC | Galveston | Battery storage | 255.33 | 38740 Heights 138kV | 2027-12-01 | 2023-01-20 | True |  |  | Signed; security posted
25INR0353 | Marshall Spring Solar | Marshall Springs Solar, LLC | Gillespie | Solar | 150 | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | 2028-12-20 | 2025-12-26 |  |  |  | Signed
25INR0354 | Marshall Spring Storage | Marshall Springs Storage, LLC | Gillespie | Battery storage | 150 | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | 2028-12-20 | 2025-12-26 |  |  |  | Signed
24INR0514 | Rogers Draw BESS | ROGERS DRAW ENERGY STORAGE, LLC | Gillespie | Battery storage | 148.61 | 7751 Headwaters substation 138kV | 2030-07-31 | 2024-02-28 | True |  |  | Signed; security posted
26INR0452 | Cannibal Draw Solar | Cannibal Draw Solar, LLC | Glasscock | Solar | 149.5 | Sand_Bluff 345 kV (59902) | 2028-04-10 | 2025-01-17 | True |  |  | Signed; security posted
26INR0453 | Cannibal Draw Storage | Cannibal Draw Solar, LLC | Glasscock | Battery storage | 98.6 | Sand_Bluff 345 kV (59902) | 2028-04-10 | 2025-01-17 | True |  |  | Signed; security posted
25INR0138 | Champaign BESS | Champaign BESS, LLC | Glasscock | Battery storage | 201.13 | Tap 138kV Shaw POD (18664) – Desert Wind Sub (11283) new station Potterson Lake Switch | 2028-03-31 | 2025-07-31 | True |  |  | Signed; security posted
26INR0573 | Cummins BESS | RWE Solar Development, LLC | Glasscock | Battery storage | 200.89 | 1333 MCDONALD 138kV | 2028-06-30 |  |  |  |  | In study
27INR0371 | Feather Dalea BESS | RWE Clean Energy Development, LLC | Glasscock | Battery storage | 200 | 59902 Sand_Bluff 345kV | 2027-07-02 |  |  |  |  | In study
25INR0578 | Forest Creek Wind Repower | Forest Creek Wind Farm, LLC | Glasscock | Wind | 125.1 | Mcdonald 138 kV (Bus #: 1333) | 2026-12-31 | 2005-11-17 | True | 2025-07-28 | 2025-08-27 | Approved for synchronization
27INR0355 | Gardner Draw Solar | RWE Clean Energy Development, LLC | Glasscock | Solar | 309.5 | 59902 Sand Bluff 345kV | 2028-06-01 | 2025-08-07 | True |  |  | Signed; security posted | Signed -> Signed; security posted
29INR0040 | Gusty Windpower | Gusty Windpower, LLC | Glasscock | Wind | 248.9 | Tap 345kV 59903 Bearkat - 1058 Longshore_5; Anemone 345 kV Station | 2028-12-31 | 2025-12-03 | True |  |  | Signed; security posted
15INR0064b | Harald (BearKat Wind B) | McCrae Wind Energy II, LLC | Glasscock | Wind | 162.1 | 59903 Bearkat 345kV | 2026-12-03 | 2018-05-30 | True | 2020-02-10 | 2020-05-12 | Approved for synchronization
26INR0447 | Honey Mesquite Wind Farm | Honey Mesquite Wind Farm , LLC | Glasscock | Wind | 173.95 | 59902 Sand Bluff 345kV | 2026-12-30 | 2024-09-10 | True | 2026-08-03 | 2026-08-20 | Approved for synchronization
30INR0080 | Indigo Quill Gas | RWE Clean Energy Development, LLC | Glasscock | Gas turbine | 370.08 | 59902 SAND_BLUFF 345KV | 2028-12-29 |  |  |  |  | In study
24INR0578 | Panther Creek 1 Repower | Panther Creek Wind Farm I&II, LLC | Glasscock | Wind | 11 | 1058 Longshore 345kV | 2026-12-31 |  | True |  | 2024-10-02 | Approved for synchronization
24INR0582 | Panther Creek 2 Repower | Panther Creek Wind Farm I&II, LLC | Glasscock | Wind | 8 | Longshore 345kV [Bus# 1058] | 2026-12-31 |  | True |  | 2024-10-02 | Approved for synchronization
26INR0355 | Pleiades Storage | Pleiades Storage, LLC | Glasscock | Battery storage | 205.5 | Tap 138kV Einstein 23852 - 10043 St. Lawrence | 2029-09-22 |  |  |  |  | In study
25INR0608 | Proteus London-Leigh Solar SLF | London Leigh Solar, LLC | Glasscock | Solar | 600 | 345kV Bernoulli (bus # 59907) | 2028-09-30 |  |  |  |  | In study
25INR0609 | Proteus London-Leigh Storage SLF | London Leigh Solar, LLC | Glasscock | Battery storage | 0 | Bernoulli (bus # 59907) | 2028-09-30 |  |  |  |  | In study
25INR0142 | Sagewood BESS | Sagewood BESS, LLC | Glasscock | Battery storage | 100.57 | tap McDonald Road Switch (1333) – Pastores Switch (10121) ckt 1 | 2028-03-31 |  |  |  |  | In study
27INR0383 | Windjammer Windpower | Windjammer Windpower, LLC | Glasscock | Wind | 244.06 | tap 345kV 59902 Sand Bluff Wind Farm - 59907 Bernoulli | 2028-12-31 | 2025-12-03 | True |  |  | Signed; security posted
27INR0144 | Angel City Solar | Angel City Energy Center, LLC | Goliad | Solar | 221.02 | Coleto Creek (# 8164) AEP – Pawnee (#5725) STEC, 25.9 miles from Coleto Creek, 28.2 miles from Pawnee Sub. POI co-ordinates: 28.755, -97.583 | 2029-09-30 |  |  |  |  | In study
26INR0664 | Coleto Creek - Fuel Change Only | COLETO CREEK POWER LLC | Goliad | Gas steam turbine | 655 | 8162 Coleto Creek 138kV | 2026-12-15 |  |  |  |  | In study
27INR0149 | Diablo Campo Storage | Diablo Campo Energy Center, LLC | Goliad | Battery storage | 313.54 | The Coleto Greek (#8164) to Pawnee Switching Station (#5725) ; LCRA | 2029-09-30 |  |  |  |  | In study
27INR0248 | Double A Solar SLF | Double A Solar, LLC | Goliad | Solar | 132.6 | Tap 69kV 5678 Schroeder - 5675 Big Oak | 2028-05-31 |  |  |  |  | In study
27INR0257 | Double A Storage SLF | Double A Storage, LLC | Goliad | Battery storage | 0 | Tap 69kV 5678 Schroeder - 5675 Big Oak | 2028-05-31 |  |  |  |  | In study
24INR0067 | KEYS HOLLOW SOLAR SLF | Keys Hollow Solar, LLC | Goliad | Solar | 200.85 | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | 2028-03-10 | 2024-10-29 | True |  |  | Signed; security posted
24INR0068 | KEYS HOLLOW STORAGE SLF | Keys Hollow Solar, LLC | Goliad | Battery storage | 0 | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | 2028-03-10 | 2024-10-29 | True |  |  | Signed; security posted
24INR0065 | Keys Hollow Solar Phase II SLF | Keys Hollow Solar, LLC | Goliad | Solar | 200.85 | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | 2028-03-10 | 2024-10-29 | True |  |  | Signed; security posted
24INR0066 | Keys Hollow Storage Phase II SLF | Keys Hollow Solar, LLC | Goliad | Battery storage | 0 | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | 2028-03-10 | 2024-10-29 | True |  |  | Signed; security posted
28INR0303 | Kuy Creek Solar 1 SLF | Kuy Creek Solar 1 LLC | Goliad | Solar | 234.87 | Tap Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | 2029-03-20 |  |  |  |  | In study
28INR0304 | Kuy Creek Storage 1 SLF | Kuy Creek Storage 1 LLC | Goliad | Battery storage | 151.46 | Tap - Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | 2029-03-20 |  |  |  |  | In study
21INR0223 | Tulsita Solar | Ray Ranch Solar LLC | Goliad | Solar | 256.2 | Tap 138kV 8590 Tuleta - 8595 Euler | 2026-09-15 | 2022-09-19 | True | 2024-10-22 | 2024-10-30 | Approved for synchronization
29INR0063 | Columbine Wind | Wilson Wind LLC | Gonzales | Wind | 295 | TAP 345KV BUS #5380 SHAULA- BUS #5133 ELM CREEK | 2029-09-01 |  |  |  |  | In study
23INR0231 | Hoke Solar | Hoke Solar Project, LLC | Gonzales | Solar | 95.29 | tap 138kV 7595 Deer Creek - 7621 Nixon | 2027-07-05 | 2022-04-25 | True |  |  | Signed; security posted
23INR0232 | Hoke Storage | Hoke Solar Project, LLC | Gonzales | Battery storage | 33.17 | tap 138kV 7595 Deer Creek - 7621 Nixon | 2027-07-05 | 2022-04-25 | True |  |  | Signed; security posted
25INR0010 | Nockenut Springs Solar 3 | Pecan Springs Energy, LLC | Gonzales | Solar | 201.4 | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | 2029-06-05 |  |  |  |  | In study
25INR0193 | Nockenut Springs Solar 4 | Pecan Springs Energy, LLC | Gonzales | Solar | 201.15 | The 345 kV Elm Creek - South Texas Project Line (Bus #5133 - #5915) | 2029-06-05 |  |  |  |  | In study
25INR0280 | Nockenut Springs Solar 5 | Pecan Springs Energy, LLC | Gonzales | Solar | 201.15 | Tap 345 kV 5133 Elm Creek - 5915 South Texas Project | 2029-06-05 |  |  |  |  | In study
24INR0440 | Starling Solar | Starling Solar, LLC | Gonzales | Solar | 144.6 | 138-kV Birdhouse (7255) Starling Solar Phase II is a an addition of 42.24MW to the 23INR0035 (solar) filed in 2020. 23INR0181 (storage) was filed in 2021. | 2028-01-28 | 2026-02-17 |  |  |  | Signed
29INR0103 | Meitner 2 Wind | IP Meitner, LLC | Gray | Wind | 709.1 | 79000 Gray Substation 345kV | 2028-06-30 |  |  |  |  | In study
25INR0080 | Meitner Solar | IP Meitner, LLC | Gray | Solar | 702.64 | 345 kV Gray (Bus# 79000) | 2028-06-08 | 2024-01-31 |  |  |  | Signed
26INR0113 | Meitner Wind | IP Meitner, LLC | Gray | Wind | 709 | 79000 Gray Substation 345kV | 2028-05-24 | 2024-04-19 |  |  |  | Signed
27INR0234 | Lima Solar Project | Industrial Lima Project, LLC | Grayson | Solar | 101.3 | Tap 138 kV Haggerty Switch (12677) to Van Al (1754) 138kV | 2029-03-01 | 2026-09-02 |  |  |  | Signed | In study -> Signed
28INR0108 | RAYBURN ENERGY STATION II Gas (TEF-Due Diligence) | Rayburn Country Electric Cooperative, Inc. | Grayson | Gas turbine | 570 | Double Tap 138 kV Haggerty (12677) - Progress Park (#12678) & Haggerty - Winding Oaks Switch | 2028-02-26 | 2025-12-22 | True |  |  | Signed; security posted
26INR0605 | White Bright BESS | VLN, LLC | Grayson | Battery storage | 313.69 | Tap 345kV 1729 Valley South – Anna Switch 2373 | 2029-04-16 |  |  |  |  | In study
26INR0300 | Whitewright Solar 2 | SunWR, LLC | Grayson | Solar | 301.69 | Tap 345kV 1729 Valley South – Anna Switch 2373 | 2028-05-02 |  |  |  |  | In study
19INR0085 | Blue Jay Solar | Blue Jay Solar I, LLC | Grimes | Solar | 141.05 | 4 Iola 138kV | 2025-09-30 | 2020-10-26 | True | 2021-11-11 | 2022-06-28 | Approved for synchronization
21INR0538 | Blue Jay Solar II | Blue Jay Solar I, LLC | Grimes | Solar | 68.95 | 4 Iola 138kV | 2025-10-31 | 2020-10-26 | True | 2021-11-11 | 2021-11-19 | Approved for synchronization
26INR0370 | Central Power Station | Hydra-Gen Energy Unlimited | Grimes | Gas turbine | 750 | 967 Gibbons Creek 345kV | 2027-05-01 |  |  |  |  | In study
27INR0115 | Diamante BESS | BESS DIAMANTE LLC | Grimes | Battery storage | 513.68 | 40600 ROANS__POI_5 345kV | 2028-11-01 |  |  |  |  | In study
27INR0085 | Eagle Claw Energy Center | Eagle Claw Energy Center, LLC | Grimes | Battery storage | 204.58 | Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #99 345 kV | 2028-03-31 | 2025-09-15 | True |  |  | Signed; security posted
26INR0004 | GRIMES SOLAR | CG Grimes County LLC | Grimes | Solar | 153.45 | 40600 Roans Prairie 345kV | 2026-02-15 |  |  |  |  | In study
26INR0285 | Hill Valley BESS | Hill Valley BESS, LLC | Grimes | Battery storage | 245.8 | 345 kV Singleton (#44645) | 2028-07-15 | 2026-04-21 |  |  |  | Signed
27INR0190 | Millsing BESS | Millsing BESS | Grimes | Battery storage | 501.6 | 44645 CNP Singleton 345kV | 2028-10-15 |  |  |  |  | In study
26INR0324 | Misty Hollow BESS | Clear Fork BESS, LLC | Grimes | Battery storage | 245.8 | 345 kV Singleton (#44645) | 2028-07-15 | 2025-12-04 |  |  |  | Signed
27INR0379 | Scrap Iron Solar | Energiekontor US Texas SP 15 LLC | Grimes | Solar | 110.77 | Tap 138kV (#9) Bedias - (#25) North Zulch | 2028-09-01 |  |  |  |  | In study
24INR0172 | Smith Lake Solar DC | Smith Lake Solar | Grimes | Solar | 402 | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | 2028-12-29 | 2025-12-30 |  |  |  | Signed
25INR0045 | Smith Lake Storage DC | Smith Lake Solar | Grimes | Battery storage | 65 | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | 2028-12-28 | 2025-12-30 |  |  |  | Signed
28INR0394 | Treehouse Solar | Treehouse Solar, LLC | Grimes | Solar | 281.77 | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line | 2028-11-13 |  |  |  |  | In study
28INR0395 | Treehouse Storage | Treehouse Solar, LLC | Grimes | Battery storage | 209.21 | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line, ONCOR | 2028-11-13 |  |  |  |  | In study
26INR0001 | Turin TxHSR TPSS HN-6 | Texas Central Rail Holdings, LLC | Grimes | Other | 50 | 8 Crutchfield 138kV | 2028-07-15 |  |  |  |  | In study
29INR0333 | Tyler Rose Power Plant 1 | ProEnergy Services, LLC | Grimes | Gas turbine | 597.36 | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | 2029-07-01 |  |  |  |  | In study
29INR0336 | Tyler Rose Power Plant 2 | ProEnergy Services, LLC | Grimes | Gas turbine | 398.24 | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | 2029-12-01 |  |  |  |  | In study
26INR0200 | Vaughn Energy Storage | Vaughn Battery Storage, LLC | Grimes | Battery storage | 200.6 | 13 Keith 138kV | 2027-12-31 |  |  |  |  | In study
28INR0532 | Alpha Power Phase 1 | Palomino Alpha, LLC | Guadalupe | Gas turbine | 400.1 | 345kV 7042 Zorn Substation | 2028-12-31 |  |  |  |  | In study
29INR0363 | Alpha Power Phase 2 | Palomino Alpha, LLC | Guadalupe | Gas turbine | 400.1 | 345kV 7042 Zorn Substation | 2029-12-31 |  |  |  |  | In study
30INR0143 | Alpha Power Phase 3 | Palomino Alpha, LLC | Guadalupe | Gas turbine | 400.1 | 345kV 7042 Zorn Substation | 2030-12-31 |  |  |  |  | In study
31INR0025 | Alpha Power Phase 4 | Palomino Alpha, LLC | Guadalupe | Gas turbine | 400.1 | 345kV 7042 Zorn Substation | 2031-12-31 |  |  |  |  | In study
32INR0007 | Alpha Power Phase 5 | Palomino Alpha, LLC | Guadalupe | Gas turbine | 400.1 | 345kV 7042 Zorn Substation | 2032-12-31 |  |  |  |  | In study
24INR0115 | Aster Solar | Aster Solar | Guadalupe | Solar | 160.5 | 7042 Zorn 345kV | 2029-06-01 |  |  |  |  | In study
25INR0665 | CPS Rio Nogales CT201 Rotor Replacement | CPS Energy | Guadalupe | Gas combined cycle | 3.1 | 5362 RIONOG 345kV | 2026-08-07 | 2025-02-07 | True |  | 2025-04-02 | Approved for synchronization
24INR0602 | CPS Rio Nogales CT301 Rotor Replacement | CPS Energy | Guadalupe | Gas combined cycle | 3.1 | 5362 RIONOG 345kV | 2026-08-07 | 2023-11-10 | True |  | 2024-04-03 | Approved for synchronization
24INR0145 | Calpine Guadalupe Peakers | Guadalupe Peaking Energy Center, LLC | Guadalupe | Gas turbine | 450 | 7044 Marion 345kV | 2030-05-30 |  |  |  |  | In study
29INR0211 | Enfinity Juniper Storage | EG Juniper LLC | Guadalupe | Battery storage | 261.08 | Hickory Forest (7225) | 2029-12-18 |  |  |  |  | In study
27INR0093 | Guadalupe Battery Storage Project | Guadalupe Power Partners, LP | Guadalupe | Battery storage | 210.5 | # 7044 Marion 345kV | 2030-05-30 |  |  |  |  | In study
23INR0088 | Nockenut Springs Solar 1 | Pecan Springs Energy, LLC | Guadalupe | Solar | 203.17 | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | 2029-06-05 | 2023-11-17 | True |  |  | Signed; security posted
24INR0007 | Nockenut Springs Solar 2 | Pecan Springs Energy, LLC | Guadalupe | Solar | 203.26 | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | 2029-06-05 | 2023-11-17 | True |  |  | Signed; security posted
23INR0483 | Rio Nogales CT1 Rotor Replacement | CPS Energy | Guadalupe | Gas combined cycle | 3.1 | Rio Nogales Substation 5362 RIONOG 345kV | 2026-08-07 | 2023-01-20 | True |  | 2023-04-27 | Approved for synchronization
27INR0117 | Roble BESS | Flexen USA LLC | Guadalupe | Battery storage | 154.3 | 7180 L_ZORN__8_1Y 138kV | 2028-12-01 |  |  |  |  | In study
24INR0287 | Rockridge Solar | Magnolia Solar Development, LLC | Guadalupe | Solar | 211.2 | 7225 Hickory Forest 138kV | 2028-06-27 | 2025-03-14 |  |  |  | Signed
28INR0391 | Ruedrich BESS | Ruedrich BESS | Guadalupe | Battery storage | 200.58 | LINE TAP OF CIBOLO (7608) AND McQUEENEY (7606) | 2028-11-09 |  |  |  |  | In study
29INR0175 | Black Mountain Hale Gas | Fort Worth Power Core LLC | Hale | Gas combined cycle | 990.6 | 345 kV Blackwater Draw Switch (#23920) | 2030-04-16 |  |  |  |  | In study
27INR0181 | Elk Unit 4 | Golden Spread Electric Cooperative, Inc. | Hale | Gas turbine | 210 | 141607 AEEC_5 | 2027-02-28 | 2025-12-30 | True |  |  | Signed; security posted
28INR0498 | Old Aqueduct BESS II | Tempus Power Management LLC | Hale | Battery storage | 300.96 | 23920 BLKWTRDR_5 345kV | 2030-03-01 |  |  |  |  | In study
22INR0330 | Old Aqueduct Batt | Old Aqueduct LLC | Hale | Battery storage | 300.96 | 23920 Blackwater 345kV | 2030-03-01 |  |  |  |  | In study
22INR0462 | Old Aqueduct Solar | Old Aqueduct Solar | Hale | Solar | 511.63 | 23920 Blackwater 345kV | 2028-06-01 |  |  |  |  | In study
22INR0596 | Grizzly Ridge BESS SLF | Grizzly Ridge Solar LLC | Hamilton | Battery storage | 0 | Pottsville Switching Substation (Bus# 178) | 2030-07-01 | 2021-10-18 | True | 2023-02-10 |  | Approved for energization
23INR0233 | Earthwise Solar | Quanah Solar 2 | Hardeman | Solar | 370.5 | Tap 345kV 60504 Tesla - 61001 Jim Treece | 2028-12-31 |  |  |  |  | In study
26INR0496 | Hardeman BESS | Quanah BESS LLC | Hardeman | Battery storage | 104 | 6050 PAUL 138kV | 2028-06-30 |  |  |  |  | In study
26INR0173 | Juniper Ridge BESS 1 | Lazy U ESS 1 | Hardeman | Battery storage | 251.5 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] 345kV ckt2 | 2029-06-30 |  |  |  |  | In study
26INR0174 | Juniper Ridge BESS 2 | Lazy U ESS 2 | Hardeman | Battery storage | 251.5 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] ckt2 | 2029-06-30 |  |  |  |  | In study
26INR0171 | Lazy U Solar 1 | Lazy U Solar 1 | Hardeman | Solar | 252 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A ckt2 | 2029-06-30 |  |  |  |  | In study
26INR0172 | Lazy U Solar 2 | Lazy U Solar 2 | Hardeman | Solar | 252 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A CKT2 | 2029-06-30 |  |  |  |  | In study
27INR0063 | Supra Wind | NextEra Energy Interconnection Holdings, LLC | Hardeman | Wind | 205.86 | Tap #6101 Riley 7A to #60505 Edithcla 7B 345kV | 2027-12-23 |  |  |  |  | In study
23INR0055 | Tabor Solar | Quanah Solar LLC | Hardeman | Solar | 506.4 | Tap 345kV 60504 Tesla - 61001 Jim Treece | 2027-04-16 |  |  |  |  | In study
25INR0002 | Barcelona TxHSR TPSS HN-4 | Texas Central Rail Holdings, LLC | Harris | Other | 50 | tap 138kV 45885 HocklyC - 46220 Peters | 2028-07-15 |  |  |  |  | In study
23INR0127 | Beacon Storage | AES Distributed Energy, Inc | Harris | Battery storage | 408.7 | 40450 Deepwater 345kV | 2029-10-01 |  |  |  |  | In study
25INR0434 | Bluegill BESS | Bluegill BESS, LLC | Harris | Battery storage | 251 | Tap 138 kV 40130 Atascocita - 40690 East Gate | 2028-10-31 |  |  |  |  | In study
26INR0548 | Burnet Bay Storage | TOCE TX BESS 4, LLC | Harris | Battery storage | 207.83 | tap 138kV 40390 Crosby - 40790 Haney | 2029-06-01 |  |  |  |  | In study
26INR0590 | Callisto ID Energy Center | Tempus Power management LLC | Harris | Battery storage | 100 | 47170 (H_O_C__B138) 138kV | 2028-06-01 |  |  |  |  | In study
22INR0558 | Callisto II Energy Center | Callisto II Energy Center LLC | Harris | Battery storage | 203.2 | 47150 HO Clarke 138kV | 2026-12-17 | 2023-12-11 | True |  |  | Signed; security posted
24INR0500 | Claire BESS | BRP Blue Topaz 3, LLC | Harris | Battery storage | 406.01 | 40011 Cedar Bayou 138kV | 2027-12-17 |  |  |  |  | In study
27INR0436 | Coati Energy Storage | PowerPulse LLC | Harris | Battery storage | 202.8 | Bus # 40830, Humble, 138 kV | 2029-06-15 |  |  |  |  | In study
24INR0196 | Dori BQ BESS | Sunnyside Energy LLC | Harris | Battery storage | 154 | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | 2027-08-30 | 2023-05-31 |  |  |  | Signed
23INR0040 | Dori BQ Solar | Sunnyside Energy, LLC | Harris | Solar | 50.42 | tap 138kV 47210 Holmes – 42680 Garden Villas | 2027-08-30 | 2022-12-01 |  |  |  | Signed
22INR0546 | Enchanted Rock NEWPP | Generate ER-NG, LLC | Harris | Gas engines | 30 | 40475 Deusen 138kV | 2026-02-28 | 2024-04-30 | True |  |  | Signed; security posted
24INR0413 | Furay Battery Energy Storage System | Blue Topaz 1, LLC | Harris | Battery storage | 304 | Tap 138kV 45660 Jonte substation – 46332 Scenic Woods Tapping both radial lines. | 2028-09-30 |  |  |  |  | In study
24INR0419 | High Plains Storage | ROBP Holdings, LLC | Harris | Battery storage | 157.7 | 45880 Hockley 138kV | 2028-05-30 |  |  |  |  | In study
26INR0546 | Hobby BESS I | Airport Storage II LLC | Harris | Battery storage | 602.56 | Double Tap 138kV 42680 Garden Villas – 48250 Hall & 42680 Garden Villas – 48013 Chocolate Bayou | 2027-10-15 |  |  |  |  | In study
25INR0602 | Hockley BESS | Regis Hockley LLC | Harris | Battery storage | 9.99 | 30.021619, -95.846315 Station Name (Station Code): Hockley (HK) LONG CODE: HOCKLY Short Code: HK TR5 ERCOT Bus Name: Hockley Feeder: HK-91 ERCOT Load Name: TR5 CNP XFMR #: HK TR5 ERCOT Bus #: 45880 Node: 0101 | 2027-03-01 | 2024-04-29 | True |  |  | Signed; security posted | new
25INR0420 | Houston BESS | SMT Houston | Harris | Battery storage | 227.9 | Tap 138 kV LAUDER (#46002) - RITTENHOUSE (#46282) ckt 95 | 2028-01-01 |  |  |  |  | In study
24INR0073 | Hyacinth Storage | Hyacinth Storage, LLC | Harris | Battery storage | 103.05 | 46500 Tomball 345 kV | 2030-12-25 |  |  |  |  | In study
24INR0584 | Kegans BESS (Houston IV BESS) | SMT Houston IV LLC | Harris | Battery storage | 164.6 | 44140 CLODINE 138kV | 2026-09-05 | 2024-11-07 | True | 2026-05-06 | 2026-06-08 | Approved for synchronization
26INR0545 | Knight Airport BESS I | Airport Storage I LLC | Harris | Battery storage | 522.46 | Tap 138kV 48126 Gulfgate - 48199 Knight 06 and 42680 Garden Villas - 42770 Ashville 06 | 2027-10-15 |  |  |  |  | In study
24INR0481 | Little York BESS | ESTX-PLD-HOUSTON5, LLC | Harris | Battery storage | 9.96 | Station Name (TDSP Station Code): Little York (LK) Load/Load Transformer Name: TR3 PTI BUS number: 45995 Voltage in kV (Transmission Level): 138kV Node (associated w/ load/load XFMR in NMMS): TR3 | 2026-11-12 | 2025-08-20 | True | 2026-06-05 | 2026-06-15 | Approved for synchronization
28INR0074 | Massey Storage | Massey Storage, LLC | Harris | Battery storage | 102.86 | Tap 138kV Chevron_NewSub(#99300) and Cedar Bayou Tap(#48065) circuit 84 | 2028-01-03 |  |  |  |  | In study
26INR0341 | Megamouth Energy Storage | GCI Megamouth, LLC | Harris | Battery storage | 101.3 | 42750 Mykawa 138 kV | 2028-12-31 | 2025-11-18 |  |  |  | Signed | new
26INR0345 | NET Power Demonstration plant | NET Power LLC | Harris | Gas turbine | 25.5 | 42360 Mirage POI 8 138kV | 2027-08-21 |  |  |  |  | In study
24INR0410 | NRG Greens Bayou 6 (TEF-Due Diligence) | NRG Greens Bayou 6 LLC | Harris | Gas turbine | 445 | Position 1/0 PSSE 40710, Greens Bayou Substation, 138 kV | 2028-05-01 | 2025-02-07 | True |  |  | Signed; security posted
23INR0382 | Outer Loop BESS | Black Mountain Energy Storage II | Harris | Battery storage | 201.2 | 40700 Greens Bayou 345kV | 2027-12-06 |  |  |  |  | In study
28INR0154 | Pamela Heights I | Pamela heights I Energy Center LLC | Harris | Battery storage | 101.65 | #47150 HOC 138kV | 2026-12-18 | 2025-10-07 | True |  |  | Signed; security posted
27INR0245 | Pez Rojo BESS | Pez Rojo BESS, LLC | Harris | Battery storage | 217.23 | Tap 138 kV #40260 Chamon - #40912 King | 2029-02-01 | 2026-05-01 |  |  |  | Signed
26INR0317 | Pinnacle Point Energy Storage | GCI Pinnacle Point, LLC | Harris | Battery storage | 101.3 | Tap Highlands (Bus # 40812) - HANEY ( BUS # 40790) 138 kV | 2029-07-10 |  |  |  |  | In study
26INR0503 | Rex Storage | Rex BESS, LLC | Harris | Battery storage | 256.4 | Tap 138 kV 48096 El Dorado - 43610 Scarsdale CKT 92 | 2028-10-30 |  |  |  |  | In study
24INR0081 | SANJAC BESS | Castleman Power | Harris | Battery storage | 202.37 | 40270 Riverside 138kV | 2027-04-04 |  |  |  |  | In study
23INR0126 | Sigma Storage | AES Distributed Energy, Inc | Harris | Battery storage | 408.4 | 40460 Deepwater 138kV | 2029-10-01 |  |  |  |  | In study
26INR0343 | Stinger Energy Storage | Stinger Energy Storage LLC | Harris | Battery storage | 200.8 | Tap Atascocita 138kV Substation (Bus # 40130) - Lake Houston (Bus #40820) | 2028-03-01 |  |  |  |  | In study
29INR0245 | Texas Deepwater BESS | TDWP Partners LLC | Harris | Battery storage | 313.29 | #40881 Parkes Substation 138 kV | 2029-03-05 |  |  |  |  | In study
28INR0433 | Blue Spring Solar | Flat Creek Solar, LLC | Haskell | Solar | 301 | #60515 Clear Crossing 345 kV | 2028-10-28 |  |  |  |  | In study
23INR0059 | Briggs Solar | IP Quantum III, LLC | Haskell | Solar | 323.7 | tap 345kV 60515 Clear Crossing - 60507 Pendulo | 2028-04-15 | 2025-03-15 | True |  |  | Signed; security posted
24INR0058 | Briggs Storage | IP Quantum III, LLC | Haskell | Battery storage | 336 | tap 345kV 60515 Clear Crossing - 60507 Pendulo | 2028-04-15 | 2025-03-15 | True |  |  | Signed; security posted
26INR0146 | DMF Sagerton Solar SLF | Double Mountain Fork LLC | Haskell | Solar | 125.5 | Tap 138kV 6158 Aspermont – 6161 Paint Creek | 2028-12-15 |  |  |  |  | In study
26INR0148 | DMF Sagerton Storage SLF | Double Mountain Fork LLC | Haskell | Battery storage | 0 | Tap 138kV 6158 Aspermont – 6161 Paint Creek | 2028-12-15 |  |  |  |  | In study
24INR0125 | Grasshopper Solar | Grasshopper Solar LLC | Haskell | Solar | 407.68 | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | 2028-10-01 |  |  |  |  | In study
22INR0374 | Inertia Solar | Inertia Solar Project, LLC | Haskell | Solar | 202.39 | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | 2029-03-31 | 2023-05-10 | True |  |  | Signed; security posted
27INR0217 | Journey Solar | Journey Solar, LLC | Haskell | Solar | 124.7 | Tap 138kV Paint Creek 6161 - Aspermont 6158 | 2027-09-14 |  |  |  |  | In study
20INR0012 | Lueders Solar | Innovative Solar 75 | Haskell | Solar | 40 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | 2029-12-31 |  |  |  |  | In study
28INR0408 | Max 4 Wind | Lake Creek Wind, LLC | Haskell | Wind | 352.6 | Tap 345 kV Gauss7D (Bus# 60703) to Quasar7A (Bus# 60712) Transmission Line | 2029-08-31 |  |  |  |  | In study
26INR0521 | Millers Branch Solar III | Miller's Branch Solar LLC | Haskell | Solar | 133 | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | 2026-10-01 | 2021-06-14 | True | 2026-05-26 | 2026-07-10 | Approved for synchronization
21INR0207 | Quantum Solar | IP QUANTUM II, LLC | Haskell | Solar | 321.66 | 60089 Kilby Station 345kV | 2026-09-01 | 2023-10-26 | True | 2026-03-06 | 2026-04-10 | Approved for synchronization
26INR0310 | Quantum Storage | IP Quantum II BESS, LLC | Haskell | Battery storage | 321.75 | 60089 Kilby Switching Station 345kV | 2026-09-01 | 2023-10-26 | True | 2026-03-26 | 2026-04-10 | Approved for synchronization
26INR0501 | Rolling Plains BESS | Haskell County BESS LLC | Haskell | Battery storage | 120 | 6104 SMOKY HILL 345kV | 2028-06-30 |  |  |  |  | In study
24INR0291 | Rubicon Alpha Wind | Throckmorton Wind, LLC | Haskell | Wind | 222.6 | 60507 pendulo7A 345kV | 2027-07-31 | 2024-05-08 | True |  |  | Signed; security posted
23INR0031 | Solace Solar | IP QUANTUM, LLC. | Haskell | Solar | 321.64 | tap 345kV 1430 Graham - 1048 Tonkawas | 2026-09-01 | 2024-01-30 | True | 2026-01-30 | 2026-03-03 | Approved for synchronization
26INR0309 | Solace Storage | IP Quantum BESS, LLC | Haskell | Battery storage | 321.79 | tap 345kV 1430 Graham - 1048 Tonkawas | 2026-09-01 | 2025-03-21 | True | 2026-01-30 | 2026-03-03 | Approved for synchronization
25INR0694 | Hays Energy Unit 1 Repower | HAYS ENERGY, LLC | Hays | Gas turbine | 18 | 7043 Hays Energy 345kV | 2028-07-01 |  |  |  |  | In study
22INR0586 | Hays Energy Unit 2 Repower | HAYS ENERGY, LLC | Hays | Gas turbine | 18 | 7043 Haysen 345kV | 2028-07-01 |  |  |  |  | In study
21INR0527 | Hays Energy Unit 3 Repower | HAYS ENERGY, LLC | Hays | Gas turbine | 18 | 7043 Hays 345kV | 2028-07-01 |  |  |  |  | In study
25INR0695 | Hays Energy Unit 4 Repower | HAYS ENERGY, LLC | Hays | Gas turbine | 18 | 7043 Hays Energy 345kV | 2028-07-01 |  |  |  |  | In study
24INR0387 | PaleAle BESS | Momentum Energy Storage Partners,LLC | Hays | Battery storage | 75.38 | Tap 138 kV Bus 7506 L_CEDAVA8_1Y - Bus 7507 L_FRIEND8_1Y | 2027-04-15 |  |  |  |  | In study
24INR0355 | Anatole Renewable Energy Storage | Anatole Renewable Energy LLC | Henderson | Battery storage | 207.82 | (Bus# 6951) Eustace Southeast 138kV Substation (owned by Rayburn Electric Cooperative) | 2027-06-30 | 2024-05-10 | True |  |  | Signed; security posted
27INR0014 | Kit Fox Storage | Kit Fox Storage, LLC | Henderson | Battery storage | 153.6 | Walton Switch (6899) 138KV | 2029-07-01 |  |  |  |  | In study
27INR0198 | Musgravite Solar | Solex Ridge, LLC | Henderson | Solar | 100.6 | Tap 138 kV (6855) Coffee - (6849) New York. | 2027-11-01 | 2025-05-20 | True |  |  | Signed; security posted
28INR0029 | Old Fiddler Energy Storage | Old Fiddler Energy Storage LLC | Henderson | Battery storage | 224.55 | 3233 Foggle Switch 138 kV | 2029-04-16 |  |  |  |  | In study
23INR0464 | Sloan Storage | Sloan Energy Storage LLC | Henderson | Battery storage | 200.9 | 3179 Pauline 138kV | 2026-03-27 |  |  |  |  | In study
28INR0075 | Wild Paw Storage | Wild Paw Energy Center, LLC | Henderson | Battery storage | 301.17 | Tap 345kV 3124 Trinidad - 3130 Forest Grove | 2028-09-30 |  |  |  |  | In study
27INR0233 | Anawa La BESS | Anawa La Solar LLC | Hidalgo | Battery storage | 103.7 | Tap 138KV 8394 Liston- 8392 Bates | 2027-08-31 |  |  |  |  | In study
28INR0524 | Anawa La Gas | Anawa La Solar LLC | Hidalgo | Gas combined cycle | 250 | Liston 138 KV to Bates 138 KV | 2028-12-30 |  |  |  |  | In study
27INR0232 | Anawa La Solar | Anawa La Solar LLC | Hidalgo | Solar | 93.3 | TAP 138 KV 8394 LISTON - 8392 BATES | 2027-08-31 |  |  |  |  | In study
25INR0239 | Big Five Storage | TX BESS 3 LLC | Hidalgo | Battery storage | 102.18 | Tap 138kV (5784) Redgtss - (8380) Nedina | 2028-01-15 |  |  |  |  | In study
27INR0338 | Billie Storage | Weslaco Storage LLC | Hidalgo | Battery storage | 83.75 | Tap 138kV 8357 North Weslaco – 8358 North Mercedes | 2029-09-02 |  |  |  |  | In study
25INR0039 | Borderland ESC | FRESH AIR ENERGY II, LLC | Hidalgo | Battery storage | 200 | tap 138kV 8380 NEDIN4A – 8632 NMCALLEN4C | 2028-11-30 |  |  |  |  | In study
23INR0456 | Bronze Quinta Storage | KCE TX 28, LLC | Hidalgo | Battery storage | 103.51 | S_MCALLN 8371 (S. McAllen 138kV Substation) | 2028-01-01 |  |  |  |  | In study
23INR0480 | Camellia Storage | Camellia Storage Project LLC | Hidalgo | Battery storage | 90.76 | Tap 138 kV 8358 NORTH MERCEDES - 8327 HARLINGEN 138 kV | 2028-06-30 |  |  |  |  | In study
26INR0442 | Donna BESS | Donna Solar LLC | Hidalgo | Battery storage | 53.91 | Tap 345 kV 80137 Stewart Road - 8383 North Edinburg | 2029-02-22 |  |  |  |  | In study
27INR0205 | Donna Solar | Donna Solar LLC | Hidalgo | Solar | 168.13 | Tap 345 kV (80137) Stewart Road - (8383) North Edinburg CKT ID#01 | 2029-02-22 |  |  |  |  | In study
28INR0247 | Eligius BESS | Eligius Storage LLC | Hidalgo | Battery storage | 174.66 | tap 138kV Liston (#8394) – JL Bates (#8392) line, AEP | 2028-11-28 |  |  |  |  | In study
24INR0491 | Gunnar BESS | Gunnar Reliability Project LLC | Hidalgo | Battery storage | 154.75 | 8029 CLOSNER4A 138kV | 2026-11-25 | 2023-09-22 | True | 2026-08-28 | 2026-09-08 | Approved for synchronization | Energized -> Approved to connect
25INR0376 | Hawkins BESS | BRP BLUE TOPAZ 7, LLC | Hidalgo | Battery storage | 150.43 | 85005 ELGATO4A 138 kV | 2028-01-16 |  |  |  |  | In study
25INR0040 | McMEXICO STORAGE | FRESH AIR ENERGY II, LLC | Hidalgo | Battery storage | 201.9 | 8644 Trade Zone 138kV | 2028-11-30 |  |  |  |  | In study
19INR0055 | Monte Cristo II Wind | Monte Cristo Windpower II, LLC | Hidalgo | Wind | 233.9 | 8574 Pomelo 345kV | 2028-12-31 | 2025-12-19 | True |  |  | Signed; security posted
26INR0682 | North Edinburg BESS 1 | Edinburg ESS Assets LLC | Hidalgo | Battery storage | 9.99 | TSP Station Name: North Edinburg TSP Station Code: NEDIN Load Name / Load Transformer Name: LOAD3 Bus #: PTI Bus Number: 8380 Voltage (Transmission level kV): 138 kV Node (associated w/ load/load XFMR in NMMS): LD03 | 2026-08-21 | 2025-06-10 | True | 2026-05-05 | 2026-08-10 | Approved for synchronization
24INR0447 | PSE Chihuahua TX Storage | PureSky Development Inc | Hidalgo | Battery storage | 200 | Tap 138kV 8392 Bates – 8394 Liston | 2028-06-30 |  |  |  |  | In study
24INR0448 | PSE Minnesota TX Storage | PureSky Development Inc | Hidalgo | Battery storage | 94 | Tap 138kV 8372 North Pharr – 8906 North Alamo | 2028-06-30 |  |  |  |  | In study
24INR0449 | PSE Richardson TX Storage | PureSky Development Inc. | Hidalgo | Battery storage | 100 | TAP 138KV 8374 SOUTH EAST EDINBURG - 8029 CLOSNER | 2028-06-30 |  |  |  |  | In study
23INR0462 | Palladium Storage | Palladium Energy Storage LLC | Hidalgo | Battery storage | 156.33 | Tap 138 kV 8656 Luna - 8033 Pantera | 2028-06-30 |  |  |  |  | In study
25INR0192 | Palmvalley Storage | Palm Valley BESS LLC | Hidalgo | Battery storage | 100 | Frontera (#8980) | 2027-05-01 |  |  |  |  | In study
26INR0444 | Sullivan BESS | Sullivan Solar LLC | Hidalgo | Battery storage | 72.19 | Tap 138kV 8798 La Grulla - 8355 Goodwin | 2029-02-25 |  |  |  |  | In study
26INR0443 | Sullivan Solar | Sullivan Solar LLC | Hidalgo | Solar | 170.68 | Tap 138kV 8798 La Grulla - 8355 Goodwin | 2029-02-25 |  |  |  |  | In study
22INR0387 | Val Vista Grid BESS 1 | Val Vista Grid, LLC | Hidalgo | Battery storage | 209.32 | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | 2029-03-30 | 2025-12-31 |  |  |  | Signed
24INR0102 | Val Vista Grid BESS 2 | Val Vista Grid, LLC | Hidalgo | Battery storage | 210.56 | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | 2029-03-30 | 2025-12-31 |  |  |  | Signed
22INR0499 | Aquilla Lake 3 Wind | Aquilla Lake 3 Wind | Hill | Wind | 297.4 | tap 345 kV 68040 Kopperl to 68091 Navarro | 2026-11-20 | 2024-01-24 | True | 2026-07-02 | 2026-07-14 | Approved for synchronization
25INR0046 | Blue Skies BESS | ACTX BESS Project LLC | Hill | Battery storage | 306.26 | 68090 SAM SW 345kV | 2028-04-01 | 2024-06-20 | True |  |  | Signed; security posted
33INR0005 | Bullock Gas | Bullock Data Center, LLC | Hill | Gas combined cycle | 1400 | BULLOCK 345 KV STATION (Bus# 68096) | 2032-07-01 |  |  |  |  | In study
24INR0023 | Compadre Solar | Hill Solar I, LLC | Hill | Solar | 405.7 | tap 345kV 68090 Sam Switch - 1907 Venus | 2026-10-31 | 2022-11-12 | True | 2024-10-30 | 2024-11-13 | Approved for synchronization
25INR0166 | Compadre Solar II | Hill Solar II, LLC | Hill | Solar | 201.4 | Tap 345kV 68090 Sam Switch – 3389 Fort Smith | 2026-12-31 | 2024-12-24 | True | 2026-04-27 | 2026-07-16 | Approved for synchronization
26INR0313 | Edens Solar | Hill PV, LLC | Hill | Solar | 70.75 | Tap 69kV 3532 Itasca - 3523 Hillsboro | 2028-04-09 |  |  |  |  | In study
27INR0646 | Files BESS SLF | Files BESS | Hill | Battery storage | 34 | Fort Smith Switch (#3389) 345 kV | 2029-11-07 |  |  |  |  | In study
26INR0402 | HILLBORO BESS | Abei Energy Green XI LLC | Hill | Battery storage | 130.9 | Tap 138kV Ash Creek Switch (Bus #3473) – Revolution Switch (Bus #3387) | 2028-09-21 |  |  |  |  | In study
27INR0312 | HILLBORO WIND | Abei Energy Green XI LLC | Hill | Wind | 33.2 | Tap 138kV Ash Creek Switch (Bus #3473) – Revolution Switch (Bus #3387) | 2028-09-21 |  |  |  |  | In study
24INR0124 | High Noon Solar | High Noon Solar Project, LLC | Hill | Solar | 182 | Tap 138kV 445 Yates - 444 Covington | 2028-05-09 | 2024-05-03 | True |  |  | Signed; security posted
24INR0126 | High Noon Storage | High Noon Solar Project, LLC | Hill | Battery storage | 94 | Tap 138kV 445 Yates - 444 Covington | 2028-05-09 | 2024-05-08 | True |  |  | Signed; security posted
33INR0006 | Liberty Thermal Energy Center | Liberty Data Center I, LLC | Hill | Gas combined cycle | 1400 | LIBERTY 345 KV STATION (Bus# 68092) | 2032-07-01 |  |  |  |  | In study
24INR0407 | Mercury Solar III | Mercury Solar | Hill | Solar | 203.5 | 68092 Liberty Station 345kV | 2029-04-01 | 2025-12-12 | True |  |  | Signed; security posted
21INR0258 | Mercury Storage SLF | Mercury Storage, LLC | Hill | Battery storage | 0 | 68092 Liberty Station 345kV | 2029-07-01 |  |  |  |  | In study
29INR0158 | NRG Prairie Energy Center | NRG Prairie Energy Center LLC | Hill | Gas combined cycle | 1253 | Tap #1907 Venus Switch – #3389 Fort Smith Switch 345 kV | 2030-12-31 |  |  |  |  | In study
25INR0233 | OCI Cobb Creek ESS | Hillsboro Solar Project LLC | Hill | Battery storage | 201.6 | tap 345kV 1907 Venus - 68090 Sam Sw | 2028-12-31 | 2024-07-24 | True |  |  | Signed; security posted
25INR0229 | OCI Cobb Creek Solar | Hillsboro Solar Project LLC | Hill | Solar | 203.1 | tap 345kV 1907 Venus - 68090 Sam Sw | 2027-12-31 | 2024-07-24 | True |  |  | Signed; security posted
24INR0106 | Payne Battlecreek | Gransolar Texas Ten, LLC | Hill | Solar | 84.99 | tap 138kV 213 Haney - 3515 Hubbard | 2027-08-25 | 2024-02-23 |  |  |  | Signed
28INR0404 | Penelope Solar | Ash Creek Project LLC | Hill | Solar | 97.8 | New sub in the 234 Chatt - 3473 Ash Creek 138kV line | 2029-09-24 |  |  |  |  | In study
28INR0472 | Seven Angels Energy Storage I | Seven Angels Infrastructure LLC | Hill | Battery storage | 514 | 68090 Sam Switch Bus 345kV | 2028-12-31 |  |  |  |  | In study
28INR0473 | Seven Angels Energy Storage II | Seven Angels Infrastructure LLC | Hill | Battery storage | 514 | 68090 Sam Switch Bus 345kV | 2028-12-31 |  |  |  |  | In study
25INR0122 | Vial BESS | Gransolar Texas Eleven LLC | Hill | Battery storage | 135.18 | Chatt(234) - Pecan Street (3352) 138kV | 2027-09-15 | 2025-08-04 | True |  |  | Signed; security posted
25INR0231 | Apache Hill BESS | APACHE HILL ENERGY CENTER | Hood | Battery storage | 201.15 | 363 Hood 138kV | 2026-10-31 | 2024-06-26 | True | 2026-09-18 |  | Approved for energization | Signed; security posted -> Energized
27INR0288 | Rain Lily Solar 1 | Rain Lily Solar 1 LLC | Hood | Solar | 147.76 | Tap 138kV #350 ABBYBEND - #363 HOOD | 2028-10-15 | 2026-09-16 | True |  |  | Signed; security posted | In study -> Signed; security posted
27INR0285 | Rain Lily Storage 1 | Rain Lily Storage One, LLC | Hood | Battery storage | 105.6 | Tap 138kV #350 ABBYBEND - #363 HOOD | 2028-10-15 | 2026-09-16 | True |  |  | Signed; security posted | In study -> Signed; security posted
24INR0567 | Wolf Hollow III | Wolf Hollow II Power LLC | Hood | Gas turbine | 306.32 | 1877 Mitchell Bend 345KV | 2027-05-31 |  |  |  |  | In study
24INR0326 | Blarney Solar | Blarney Solar Project LLC | Hopkins | Solar | 81.46 | 138 kV Ridgeway Switch | 2027-10-01 | 2024-04-22 |  |  |  | Signed
23INR0229 | CH Solterra LLC | CH Solterra LLC | Hopkins | Solar | 143 | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | 2027-05-31 |  |  |  |  | In study
23INR0494 | Cartwheel BESS 1 | Cartwheel BESS, LLC | Hopkins | Battery storage | 154.2 | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | 2026-12-31 | 2023-11-10 | True | 2025-06-26 | 2025-09-10 | Approved for synchronization
23INR0495 | Cartwheel BESS 2 | RWE Renewables | Hopkins | Battery storage | 156.91 | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | 2028-06-15 |  |  |  |  | In study
25INR0204 | Cedar Range Solar | Cedar Range, LLC | Hopkins | Solar | 150.64 | “Sweet Tea” 345 kV switchyard that taps the Allen Switch – Stouts Creek 345 kV Line | 2027-09-17 | 2025-07-02 |  |  |  | Signed
27INR0451 | Dairyland Storage | ENGIE IR Holdings LLC | Hopkins | Battery storage | 301.8 | To 345 kV Birthright Station (#11684) | 2029-04-30 |  |  |  |  | In study
27INR0097 | JUNIPERUS BESS | BLUE STONE RENEWABLE XXI LLC | Hopkins | Battery storage | 169.6 | Tap 345kV Cash Switch (bus# 2464) - Sandy Ranch Switch (bus# 2621) | 2029-07-09 |  |  |  |  | In study
26INR0304 | JUNIPERUSSS | BLUE STONE RENEWABLE XXI LLC | Hopkins | Solar | 80.33 | Tap 345kV Cash Switch (bus# 2464) - Sandy Ranch Switch (bus# 2621) | 2029-07-09 |  |  |  |  | In study
26INR0409 | Lucky 7 Solar | Lucky 7 Solar Farm LLC | Hopkins | Solar | 101.35 | Tap 345kV 2621 Sandy Ranch Switch - 2464 CASH SWITCH | 2027-09-20 | 2025-08-13 | True |  |  | Signed; security posted
29INR0056 | Palomino Solar | Palomino Renewables | Hopkins | Solar | 301.2 | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | 2028-12-31 |  |  |  |  | In study
29INR0057 | Palomino Storage | Palomino Renewables | Hopkins | Battery storage | 155.1 | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | 2029-05-01 |  |  |  |  | In study
20INR0203 | Pine Forest Solar | Pine Forest Solar I, LLC | Hopkins | Solar | 301.51 | Monticello Switch – Allen Switch 345 kV Line | 2027-02-01 | 2020-07-29 | True | 2025-06-03 | 2025-07-03 | Approved for synchronization
29INR0189 | Project Alpha Solar | SGE Alpha Energy LLC | Hopkins | Solar | 121.95 | 138 kV COOPER LAKE PUMP TAP bus# 1822 ---- 138 KV #1814 SULPHUR SPRINGS | 2029-09-24 |  |  |  |  | In study
26INR0256 | Camino Ranch Solar 2 SLF | Camino Ranch Solar Project LLC | Houston | Solar | 237.21 | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | 2028-12-09 | 2025-12-31 |  |  |  | Signed
24INR0412 | Camino Ranch Solar SLF | Camino Ranch Solar Project LLC | Houston | Solar | 296.42 | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | 2028-12-09 | 2025-12-31 |  |  |  | Signed
26INR0257 | Camino Ranch Storage 2 SLF | Camino Ranch Solar LLC | Houston | Battery storage | 238.45 | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | 2028-12-09 | 2025-12-31 |  |  |  | Signed
24INR0420 | Camino Ranch Storage SLF | Camino Solar Ranch, LLC | Houston | Battery storage | 298.06 | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | 2028-12-09 | 2025-12-31 |  |  |  | Signed
26INR0176 | Dionysus Solar | Dionysus Solar, LLC | Houston | Solar | 153.26 | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | 2028-12-15 | 2026-07-31 |  |  |  | Signed
26INR0177 | Dionysus Storage | Dionysus Solar, LLC | Houston | Battery storage | 77.28 | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | 2028-12-15 | 2026-07-31 |  |  |  | Signed
27INR0196 | Houston County BESS | Houston ESS, LLC | Houston | Battery storage | 125.4 | Tap ETEC 138kV #6733 Mustang Prairie to #6732 Latexo Sub | 2029-12-31 |  |  |  |  | In study
26INR0363 | Saint Charles Energy Storage | RSN STORAGE 001, LLC | Houston | Battery storage | 202.7 | TAP 138kV 3345 FLATBRA_8 - 3351 JIM_ENG_8 | 2029-04-16 |  |  |  |  | In study
25INR0143 | Ariji BESS | Ariji BESS, LLC | Howard | Battery storage | 100.32 | Tap 138kV 1394 GTTYVTAP_8 - 1322 BIGSPRIG_8 | 2029-03-31 | 2025-08-01 | True |  |  | Signed; security posted
26INR0301 | Bhalu Storage | Bhalu Storage, LLC | Howard | Battery storage | 205.5 | Tap 138kV Bulldog (#23833) – Elbow (#23834) | 2028-04-21 |  |  |  |  | In study
27INR0325 | Calf Creek Storage | Coyote Ridge Storage, LLC | Howard | Battery storage | 103.3 | Buffalo 138 kV Substation #23837 | 2030-04-01 |  |  |  |  | In study
22INR0347 | Crater BESS | BRP Crater BESS LLC | Howard | Battery storage | 310.28 | Tap 345 kV Rockhound Switch (10062) – Prong Moss Switch (10057) ckt 1 | 2029-05-01 |  |  |  |  | In study
19INR0174 | Elbow Creek repower | Elbow Creek Wind Project, LLC | Howard | Wind | 0 | 1058 Longshore 345kV | 2027-03-31 | 2007-11-30 |  |  | 2019-06-27 | Approved for synchronization
29INR0019 | Infinium Solar | Jackalope Flats Solar, LLC | Howard | Solar | 401.6 | #1058 Longshore Switch - #18548 Prairieland Switch 345kV Ckt 1 | 2029-07-01 |  |  |  |  | In study
25INR0338 | Les Energy Storage | Rocky Mountain Energy Development, LLC | Howard | Battery storage | 205.13 | Tap 138 kV 1326 Stanton East – 11324 Leatherwood Pod | 2028-04-30 |  |  |  |  | In study
25INR0106 | Luthor Solar | TREX US Luthor LLC | Howard | Solar | 101 | Tap 138kV 23831 Luther Station – 10032 Little Luther | 2027-09-25 |  |  |  |  | In study
25INR0629 | Midland Energy Storage | Midland Energy Storage LLC | Howard | Battery storage | 204.7 | Tap 345kV 10057 Prong Moss Switch - 10062 Rockhound Switch CKT 1 | 2029-06-09 |  |  |  |  | In study
25INR0611 | Odessa Energy Storage | Odessa Energy Storage LLC, | Howard | Battery storage | 202.8 | 1058 LONGSHORE 345kV | 2029-05-01 |  |  |  |  | In study
28INR0419 | PRI Solar | BHER Power Resources, Inc. | Howard | Solar | 63.84 | The 345 kV Falcon Seaboard (#1025) substation; Oncor | 2027-01-31 |  |  |  |  | In study
27INR0323 | Prairie Blossom Storage | Prairie Blossom Storage, LLC | Howard | Battery storage | 122.5 | Tap 138kV #1322 Big Spring Switch – #1366 Big Spring CRMWD | 2029-05-08 |  |  |  |  | In study
26INR0485 | Prospector Energy Storage | Prospector Storage LLC | Howard | Battery storage | 204.6 | Natural Dam 138kV Substation (23836) | 2026-09-30 |  |  |  |  | In study
29INR0178 | Rattlesnake Gap Solar SLF | ET Fuels US Inc. | Howard | Solar | 0 | 10119 Tributary Switch 138 kV | 2029-06-01 |  |  |  |  | In study
29INR0179 | Rattlesnake Gap Storage SLF | ET Fuels US Inc. | Howard | Battery storage | 0 | 10119 Tributary Switch 138 kV | 2029-06-01 |  |  |  |  | In study
29INR0177 | Rattlesnake Gap Wind SLF | ET Fuels US Inc. | Howard | Wind | 200 | 10119 Tributary Switch 138 kV | 2029-06-01 |  |  |  |  | In study
27INR0512 | Silver Hills Windpower | Silver Hills Windpower, LLC | Howard | Wind | 54.05 | 10066 Prong Moss Switch 138kV | 2029-06-01 |  |  |  |  | In study
28INR0327 | 18-BRAVO BESS | Scout Energy Management, LLC | Hunt | Battery storage | 407 | 138 kV Commerce Switch Substation. Bus no. #1816 | 2028-02-01 |  |  |  |  | In study
26INR0464 | Ceres BESS | Ceres BESS, LLC | Hunt | Battery storage | 202.7 | Tap 138 kV 6883 QUINLAN NORTH SS - 6860 UNION VALLEY SS | 2028-08-10 |  |  |  |  | In study
27INR0461 | Fermata BESS | Fermata BESS, LLC | Hunt | Battery storage | 204 | Tap 345kV 2464# CASHSW_T5 – 2461# ROYSE_N5 | 2028-07-01 |  |  |  |  | In study
22INR0425 | MAKALU SOLAR | Abei Energy Green X LLC | Hunt | Solar | 50.16 | Tap 138kV 977 Pruitt - 971 Greenville | 2028-07-24 |  |  |  |  | In study
25INR0371 | McMurtre Storage | BT McMurtre Storage, LLC | Hunt | Battery storage | 176.13 | tap 138kV 1819 Commerce South - 1815 Cumby Tap | 2027-12-31 | 2025-09-17 | True |  |  | Signed; security posted
22INR0281 | Pink Solar SLF | Pink Solar, LLC | Hunt | Solar | 152.41 | 971 Pruitt 138kV | 2029-07-31 | 2022-08-30 |  |  |  | Signed
29INR0293 | Pink Storage SLF | Pink Solar, LLC | Hunt | Battery storage | 0 | 971 Pruitt 138kV | 2029-07-31 |  |  |  |  | In study
27INR0631 | Power Lane II - Gas | GEUS | Hunt | Gas engines | 104.5 | GREENV_IN_8 (977) via (future) GEUS_STM Substation | 2027-08-15 |  |  |  |  | In study
27INR0489 | Power Lane II Gas - Alternate | GEUS | Hunt | Gas engines | 104.39 | Tap 138kV Caddo Mills Explorer (11832) – Scatter Branch Sub (1818) Line via (future) GEUS_STM Substation | 2027-06-01 |  |  |  |  | In study
25INR0246 | VALDIVIAN SOLAR | Abei Energy Green III LLC | Hunt | Solar | 74.9 | 138kV 1816 Commerce Switch - 1809 Wolf City | 2028-09-22 | 2026-09-03 | True |  |  | Signed; security posted | In study -> Signed; security posted
27INR0023 | Panhandle Flagship Solar 2 | Panhandle Solar Group Operating Company LLC | Hutchinson | Solar | 304.4 | 345 kV Railhead Substation (RAILHEAD #79005). Station 2 (27INR0023) connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 (27INR0022 & 27INR0025) connects to POIB via 22.5 mile tie-line | 2031-06-30 | 2025-08-28 |  |  |  | Signed
27INR0024 | Panhandle Flagship Solar 3 | Panhandle Solar Group Operating Company LLC | Hutchinson | Solar | 260.3 | 345 kV Railhead Substation (RAILHEAD #79005).Station 3 (27INR0024) connects to Station 2 (27INR0023) via a 4.4 mile internal tie line. Station 2 connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 connects to POI | 2031-06-30 | 2025-08-28 |  |  |  | Signed
29INR0356 | Enfinity Cedar | EG Cedar LLC | Irion | Battery storage | 150 | 138kV Newton T.Busby Substation (60356) | 2030-07-17 |  |  |  |  | In study
26INR0185 | Beitel Energy Storage | Brazos Energy Storage, LLC | Jack | Battery storage | 200.6 | 579 Jack County 138kV | 2027-12-31 |  |  |  |  | In study
23INR0174 | Campsey Wind | RWE Clean Energy Development, LLC | Jack | Wind | 238.3 | tap 345kV 1458 Cobb - 1429 Jacksboro | 2028-06-01 |  |  |  |  | In study
24INR0094 | Dovetail Solar 1 | Hecate Energy Dovetail Solar 1 LLC | Jack | Solar | 666.1 | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | 2028-04-12 |  |  |  |  | In study
24INR0095 | Dovetail Solar 2 | Hecate Energy Dovetail Solar 2 LLC | Jack | Solar | 666.1 | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing | 2029-04-20 |  |  |  |  | In study
24INR0097 | Dovetail Solar 3 | Hecate Energy Dovetail Solar Holdings LLC | Jack | Solar | 666.1 | Tap 345kV 1421 Willow Creek – 11523 THOMPRIC | 2029-04-20 |  |  |  |  | In study
24INR0098 | Dovetail Storage | Hecate Energy Dovetail Storage LLC | Jack | Battery storage | 508.7 | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | 2028-04-12 |  |  |  |  | In study
22INR0301 | Fortuna Wind | RWE Renewables Development, LLC | Jack | Wind | 295.3 | Tap 345kV 1429 Jacksboro - 1730 WKrum | 2026-07-01 | 2024-08-08 |  |  |  | Signed
26INR0215 | JackGard BESS | Jackgard BESS | Jack | Battery storage | 200.59 | 1429 Jacksboro 345kV | 2028-04-17 |  |  |  |  | In study
23INR0334 | Liberty Senate Energy Storage 1 | Senate Solar LLC | Jack | Battery storage | 207.4 | 1445 Burwick 345kV | 2027-10-27 |  |  |  |  | In study
26INR0460 | Lightning Ridge Energy Storage | Lightning Ridge Storage LLC | Jack | Battery storage | 204.7 | Tap #1429 Jacksboro Substation 345kV | 2028-03-21 |  |  |  |  | In study
25INR0657 | O'Bannion Energy Storage | O'Bannion Energy Storage, LLC | Jack | Battery storage | 306.4 | 1506 Long Hollow Switch 345 kV | 2028-04-21 | 2025-12-05 | True |  |  | Signed; security posted
24INR0011 | Pinnington Storage | Hecate Energy Longhorn Storage LLC | Jack | Battery storage | 502.67 | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | 2029-04-20 |  |  |  |  | In study
24INR0375 | Possum Kingdom BESS | PK Solar, LLC | Jack | Battery storage | 200.86 | Tap 345kV 1421 Willow Creek – 11523 Thomas Price | 2028-10-29 | 2025-07-30 | True |  |  | Signed; security posted
24INR0118 | Possum Kingdom Solar | PK Solar, LLC | Jack | Solar | 262.22 | Tap 345kV 1421 Willow Creek Switch – 11523 Thomas Price | 2028-06-21 | 2025-07-25 | True |  |  | Signed; security posted
30INR0110 | Thunder Bird 1 Gas | BKV Power Ventures Jack, LLC 3 | Jack | Gas combined cycle | 1272.8 | Tap Double circuit line between Jacksbro_5 (1429) to Willowck_5 (1421) and Jacksbro_5 (1429) to Hendrch_5 (1443) | 2030-06-14 |  |  |  |  | In study
28INR0509 | Thunder Bird 2 Gas | BKV Power Ventures Jack, LLC 3 | Jack | Gas combined cycle | 1272.8 | Tap Double circuit line between Jacksbro_5 (1429) to Willowck_5 (1421) and Jacksbro_5 (1429) to Hendrch_5 (1443) | 2031-06-14 |  |  |  |  | In study
25INR0660 | Wooderson Energy Storage | Wooderson Energy Storage, LLC | Jack | Battery storage | 306.4 | Tap 345 kV 11418 TECUMSEH- 1421 Willow Creek | 2028-09-30 |  |  |  |  | In study
25INR0441 | Dios BESS | Dios BESS, LLC | Jackson | Battery storage | 201.08 | 8117 GANADO138kV | 2027-12-31 | 2025-04-03 | True |  |  | Signed; security posted
20INR0236 | New Hickory Solar | New Hickory Solar LLC | Jackson | Solar | 209.15 | OLD_HCKRY_5 bus 5323 345 kV | 2026-12-29 | 2020-06-30 | True | 2026-07-20 | 2026-09-15 | Approved for synchronization | Energized -> Approved to connect
27INR0251 | Sayle Solar SLF | Sayle Solar LLC | Jackson | Solar | 122.4 | Tap 69kV #5522 Edna - #5518 El Toro SW | 2028-05-31 |  |  |  |  | In study
27INR0260 | Sayle Storage SLF | Sayle Storage LLC | Jackson | Battery storage | 122.3 | Tap 69kV #5522 Edna - #5518 El Toro SW | 2028-05-31 |  |  |  |  | In study
27INR0554 | Texas Sun Solar | Pigg Grounds LLC | Jackson | Solar | 71.7 | Cordele Substation ; Bus no. 5524 | 2027-12-18 |  |  |  |  | In study
23INR0361 | Third Coast BESS | Third Coast BESS LLC | Jackson | Battery storage | 102.82 | 8125 Lolita substation 138kV | 2028-12-15 | 2023-05-17 | True |  |  | Signed; security posted
30INR0020 | Willow Oak Gas | Willow Oak Energy LLC | Jefferson | Gas combined cycle | 1298 | 40850 Jordan | 2030-01-01 |  |  |  |  | In study
28INR0375 | Barranca Wind 1 | Barranca Wind Energy, LLC | Jim Hogg | Wind | 300.9 | Tap the 345 kV CENIZO (#80225) - DELSOL (#80307) line | 2028-06-01 |  |  |  |  | In study
28INR0376 | Barranca Wind 2 | Barranca Wind Energy, LLC | Jim Hogg | Wind | 298.6 | Tap the 345 kV CENIZO7C (#80225) - DELSOL7C (#80307) line. | 2028-06-01 |  |  |  |  | In study
30INR0041 | Bell Song Solar | Bell Song Solar, LLC | Jim Hogg | Solar | 167.6 | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | 2029-09-15 |  |  |  |  | In study
30INR0049 | Bell Song Solar 2 | Bell Song Solar, LLC 2 | Jim Hogg | Solar | 167.6 | Tap 345kV (#80079) CRUCE7A - (#80355) DELSOL7A ckt 1 | 2030-03-16 |  |  |  |  | In study
31INR0009 | Bell Song Solar 3 | Bell Song Solar, LLC 3 | Jim Hogg | Solar | 167.6 | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | 2030-08-31 |  |  |  |  | In study
28INR0242 | Ciervo Wind | RWE Clean Energy Development, LLC | Jim Hogg | Wind | 301.5 | Tap 345 kV 80355 DelSol7A - 80079 Cruce CKT 2 | 2028-12-31 |  |  |  |  | In study
29INR0154 | Las Mujeres Solar | Las Mujeres Solar, LLC | Jim Hogg | Solar | 684.33 | Cruces 7A (Bus #80079) | 2029-12-01 |  |  |  |  | In study
28INR0072 | Mirando Valley Wind | ACE DevCo NC LLC | Jim Hogg | Wind | 478.74 | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | 2028-07-06 | 2025-12-31 | True |  |  | Signed; security posted
28INR0434 | Viento Bravo Wind | Webb Wind, LLC | Jim Hogg | Wind | 366.51 | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | 2028-07-06 | 2025-12-31 | True |  |  | Signed; security posted
27INR0307 | Beaverhead Solar SLF | Beaverhead Solar, LLC | Jim Wells | Solar | 61.5 | Direct to Sub 69kv #5653 Ben Bolt. | 2029-05-11 |  |  |  |  | In study
27INR0308 | Beaverhead Storage SLF | Beaverhead Solar, LLC | Jim Wells | Battery storage | 61.5 | Direct to Sub 69kv #5653 Ben Bolt. | 2029-05-11 |  |  |  |  | In study
23INR0331 | Orange Grove BESS | Talitha Energy Project, LLC | Jim Wells | Battery storage | 61.39 | 5660 Orange Grove Switching Station 138 kV | 2027-04-30 | 2022-11-30 | True |  |  | Signed; security posted
27INR0249 | Raghorn Solar SLF | Raghorn Solar LLC | Jim Wells | Solar | 91.9 | Tap 69kV #5654 San Diego - #5658 Orange Grove | 2028-05-31 |  |  |  |  | In study
27INR0259 | Raghorn Storage SLF | Raghorn Storage LLC | Jim Wells | Battery storage | 0 | Tap 69kV #5654 San Diego - #5658 Orange Grove | 2028-05-31 |  |  |  |  | In study
24INR0075 | Blue Bird Solar | Gigawatt Solar LLC | Johnson | Solar | 425.97 | tap 345kV 1880 Rocky Creek - 1898 Mitchell Bend Switch | 2028-12-15 | 2024-01-18 |  |  |  | Signed
27INR0173 | Trenno BESS | JSB1, LLC | Johnson | Battery storage | 202.56 | Tap 138kV 2281 Godley - 2888 Carmichael | 2027-09-13 | 2025-08-18 |  |  |  | Signed
22INR0457 | Anson BAT | Anson II Storage LLC | Jones | Battery storage | 153.55 | tap 345 kV 68004 Phantom Hill station | 2027-12-01 | 2024-08-15 | True |  |  | Signed; security posted
20INR0242 | Anson Solar 2 | Anson Solar Center 2, LLC | Jones | Solar | 200.9 | existing tap 345 kV 68004 Phantom Hill station | 2026-10-01 | 2024-08-15 | True | 2025-11-04 | 2025-11-25 | Approved for synchronization
21INR0247 | Anson Solar Center, Phase III | Anson Solar Center 3, LLC | Jones | Solar | 200 | tap 345kV 68000 WShack - 68001 Clayton | 2028-06-01 |  |  |  |  | In study
25INR0473 | Crowded Star I BESS | Jones City Solar II, LLC | Jones | Battery storage | 202.69 | 68014 Open Sky | 2027-07-09 | 2025-12-01 | True |  |  | Signed; security posted
20INR0241 | Crowded Star Solar | Jones City Solar, LLC | Jones | Solar | 218.79 | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | 2026-08-17 | 2019-12-17 | True | 2026-04-22 | 2026-05-28 | Approved for synchronization
22INR0274 | Crowded Star Solar II | Jones City Solar II, LLC | Jones | Solar | 189.5 | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | 2026-09-18 | 2019-12-17 | True | 2026-06-22 | 2026-07-08 | Approved for synchronization
29INR0015 | Funston Solar | Funston Solar LLC | Jones | Solar | 351.1 | tap 345 kV 68000 West Shackelford – 68004 Phantom Hill Circuit 2 | 2027-02-26 | 2024-10-23 | True |  |  | Signed; security posted
30INR0146 | Hackberry Draw Solar | Orsted Onshore Development North America, LLC | Jones | Solar | 652.96 | Tap 345 kV (68000) West Shackleford - (60515) Clear Crossing Ckt 2 | 2030-04-30 |  |  |  |  | In study
26INR0440 | Hamby Solar | Abilene GCE LLC | Jones | Solar | 205.8 | 6245 ABILENE ROBERTSON PRISON 138 KV | 2028-06-27 | 2025-12-31 | True |  |  | Signed; security posted
29INR0393 | Lone Tiger Solar | Origis Development, LLC | Jones | Solar | 242.8 | Tap 345 kV Claytonville (#68001) to phantom hill (#68004) | 2029-10-06 |  |  |  |  | In study | new
27INR0452 | Moccasin Storage | ENGIE IR Holdings LLC | Jones | Battery storage | 603.08 | Tap 345kV #60707 Kirchhoff - #60515 Clear Crossing CKT-1 | 2028-07-01 |  |  |  |  | In study
24INR0378 | Solara BESS 1 | CED Development Inc. | Jones | Battery storage | 150 | 60387 Hendrick 138kV | 2027-11-30 |  |  |  |  | In study
24INR0379 | Solara BESS 2 | CED Development Inc. | Jones | Battery storage | 150 | 60387 Hendrick 138kV | 2027-11-30 |  |  |  |  | In study
23INR0244 | Tiger Solar | Vaca Del Sol, LLC | Jones | Solar | 250.9 | 68004 PHANTOM HILL 345KV | 2027-02-26 | 2024-10-30 | True |  |  | Signed; security posted
26INR0068 | Charro Creek Solar 1 SLF | Charro Creek Solar LLC | Karnes | Solar | 203 | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | 2029-12-31 |  |  |  |  | In study
26INR0070 | Charro Creek Solar 2 SLF | Charro Creek Solar LLC | Karnes | Solar | 203 | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | 2029-12-31 |  |  |  |  | In study
26INR0072 | Charro Creek Solar 3 SLF | Charro Creek Solar LLC | Karnes | Solar | 203 | Tap on PAWNEESW5 (#5725) - COLETO7A (#8164) Line | 2029-12-31 |  |  |  |  | In study
26INR0069 | Charro Creek Storage 1 SLF | Charro Creek Solar LLC | Karnes | Battery storage | 0 | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | 2029-12-31 |  |  |  |  | In study
26INR0071 | Charro Creek Storage 2 SLF | Charro Creek Solar LLC | Karnes | Battery storage | 0 | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | 2029-12-31 |  |  |  |  | In study
26INR0073 | Charro Creek Storage 3 SLF | Charro Creek Solar LLC | Karnes | Battery storage | 0 | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | 2029-12-31 |  |  |  |  | In study
27INR0151 | Coyote Den Storage | Coyote Den Energy Center, LLC | Karnes | Battery storage | 156.93 | The Kenedy Switching Station #2 (#8186) to Rosata POD (#8153) Line ; AEP | 2030-09-30 |  |  |  |  | In study
28INR0073 | Daystar Solar | Choate Solar, LLC | Karnes | Solar | 150 | 5728 Choate 138kV | 2028-09-15 |  |  |  |  | In study
27INR0152 | New Shepherd Solar | New Shepherd Energy Center, LLC | Karnes | Solar | 150.84 | the Kenedy Switching Station #2 (#8186) – Rosata POD (#8153) line, AEP. | 2030-09-30 |  |  |  |  | In study
25INR0491 | Tarim BESS | BRP Tarim BESS LLC | Karnes | Battery storage | 201 | 5727 Pawnee Switching Substation 138kV | 2027-12-01 |  |  |  |  | In study
29INR0332 | White Star Energy Storage | White Star Energy Storage, LLC | Karnes | Battery storage | 201.2 | Milton Substation 78583 L_MILTON8_1Y | 2029-12-31 |  |  |  |  | In study
28INR0442 | Zunkerville BESS | Zunkerville Energy, LLC | Karnes | Battery storage | 206.74 | 345kV BUS #5725 PAWNEE SWITCHING STATION | 2029-12-01 |  |  |  |  | In study
28INR0443 | Zunkerville Solar | Zunkerville Energy, LLC | Karnes | Solar | 200.67 | #5725 PAWNEE SWITCHING STATION 345kV | 2029-12-01 |  |  |  |  | In study
27INR0531 | Erika BESS | Erika Solar, LLC | Kaufman | Battery storage | 100 | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | 2029-07-01 |  |  |  |  | In study
24INR0303 | Erika Solar | Erika Solar, LLC | Kaufman | Solar | 200.5 | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | 2026-11-25 | 2023-10-12 | True | 2026-08-14 | 2026-08-27 | Approved for synchronization
26INR0502 | Fudge Ranch BESS | Crandall BESS LLC | Kaufman | Battery storage | 104 | <6902><TALTY_RC><138kV> | 2027-06-30 |  |  |  |  | In study
22INR0426 | LUBIO SOLAR | BDPU Solar Lubio LLC | Kaufman | Solar | 54.71 | tap 138kV 2727 Crandall - 2724 Kaufman Northwest | 2028-04-20 | 2024-11-08 |  |  |  | Signed
24INR0339 | Mystic Springs Renewable Energy Solar SLF | Mystic Spring Renewable Energy LLC | Kaufman | Solar | 258.83 | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | 2028-03-31 | 2025-10-30 |  |  |  | Signed
24INR0340 | Mystic Springs Renewable Energy Storage SLF | Mystic Spring Renewable Energy LLC | Kaufman | Battery storage | 0 | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | 2028-03-31 |  |  |  |  | In study
29INR0250 | Slash Pine Storage | EG Slash Pine LLC | Kaufman | Battery storage | 200 | 1698 Sulphur Springs Switch and 3174 Canton Switch 138 kV | 2029-09-17 |  |  |  |  | In study
28INR0432 | Solarville BESS SLF | Ville Solar, LLC | Kaufman | Battery storage | 0 | Tap 345 kV (#2432)Tri Corner - (#3105) Elkton | 2028-09-19 |  |  |  |  | In study
26INR0086 | Solarville Solar SLF | Ville Solar, LLC | Kaufman | Solar | 402.86 | Tap 345kV #3123 Trinidad Switch – #2432 Tri Corner. | 2029-07-01 |  |  |  |  | In study
28INR0431 | Solarville Wind SLF | Ville Solar, LLC | Kaufman | Wind | 0 | Tap 345 kV (#2432)Tri Corner - (#3105) Elkton | 2028-09-19 |  |  |  |  | In study
22INR0552 | Sowers Storage | Sowers Energy Storage LLC | Kaufman | Battery storage | 208.89 | 6894 Rose Hill_RC Sub 138 kV | 2027-07-01 | 2022-04-22 | True |  |  | Signed; security posted
23INR0222 | Sunbelt Solar | Rose Hill Solar LLC | Kaufman | Solar | 81.5 | tap 138kV 6902 Talty - 6801 Patton | 2026-12-31 |  |  |  |  | In study
23INR0409 | Sunbelt Storage | Rose Hill Solar LLC | Kaufman | Battery storage | 52 | Tap 138kV 6902 Talty - 6894 Rose Hill | 2026-12-31 |  |  |  |  | In study
27INR0456 | Yellow Leaf BESS | Lightsource Renewable Energy Development LLC | Kaufman | Battery storage | 103.1 | Tap 138kV Crandall (#2727) – Kaufman Northwest (#2724) | 2028-09-25 |  |  |  |  | In study
28INR0412 | Yellow Leaf II BESS | Yellow Leaf Energy Storage LLC | Kaufman | Battery storage | 205.74 | Tap 138kV 2727 CRANDALL1_8 - 2724 KAUFMN_8 | 2028-09-25 |  |  |  |  | In study
27INR0455 | Yellow Leaf Solar | Lightsource Renewable Energy Development LLC | Kaufman | Solar | 103.19 | Tap 138kV Crandall (#2727) – Kaufman Northwest (#2724) | 2028-09-25 |  |  |  |  | In study
23INR0163 | Ringtail Ridge Storage | KCE TX 26, LLC | Kendall | Battery storage | 100.57 | 7150 Kendall 138kV | 2028-05-23 |  |  |  |  | In study
28INR0180 | Green Ocelot Solar | Ocelot Solar LLC | Kenedy | Solar | 357 | Tap 345kV 80076 Ajo - 8601 Cebolla | 2028-11-17 |  |  |  |  | In study
28INR0189 | Green Ocelot Storage | Ocelot Solar LLC | Kenedy | Battery storage | 178.5 | Tap 345kV 80076 Ajo 80076 - 8601 Cebolla | 2028-11-17 |  |  |  |  | In study
27INR0309 | Tall Saddle Solar | Tall Saddle Solar, LLC | Kenedy | Solar | 252.3 | 80076 AJO SUBSTATION 345kV | 2029-10-15 |  |  |  |  | In study
27INR0310 | Tall Saddle Wind | Tall Saddle Wind, LLC | Kenedy | Wind | 522.8 | 80076 AJO SUBSTATION 345kV | 2029-10-15 |  |  |  |  | In study
30INR0164 | Buzzer Butte 2 Solar | Origis Development, LLC | Kent | Solar | 242.8 | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911) | 2030-09-01 |  |  |  |  | In study | new
29INR0394 | Buzzer Butte Solar | Origis Development, LLC | Kent | Solar | 242.8 | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911) | 2030-09-01 |  |  |  |  | In study | new
28INR0301 | Carpet Tech Solar One | CT Solar One | Kent | Solar | 110.7 | #59911 MHOS 345 kV | 2029-06-01 |  |  |  |  | In study
27INR0435 | Clairemont Solar 1 | Clairemont Solar LLC | Kent | Solar | 251.75 | 59908 Novaprime 345kV | 2029-02-13 | 2025-11-24 | True |  |  | Signed; security posted
27INR0447 | Jay Flat BESS | Jay Flat BESS LLC | Kent | Battery storage | 259.36 | 59908 Novaprime 345kV | 2029-02-13 |  |  |  |  | In study
29INR0294 | Spurland Solar III | Spurland Solar III, LLC | Kent | Solar | 321.85 | Nova Prime Substation | 2029-12-29 |  |  |  |  | In study
22INR0215 | TEXAS SOLAR NOVA 3 | Texas Solar Nova 1, LLC | Kent | Solar | 200.2 | tap 345kV 11305 Dermott - 59904 Cottonwood | 2026-01-31 |  |  |  |  | In study
25INR0202 | East West BESS | East West Energy Storage, LLC | Kerr | Battery storage | 122.6 | 7750 LCRA MOUNTAIN HOME SUB | 2028-03-17 | 2024-07-12 |  |  |  | Signed
25INR0653 | Southfork Energy Storage | Southfork Energy Storage, LLC | Kimble | Battery storage | 306.4 | tap 345kV 60709 Oersted - 60616 Edison CKT 1 | 2028-11-30 |  |  |  |  | In study
27INR0127 | Bigway Solar I | NextEra Energy Interconnection Holdings, LLC | King | Solar | 195.2 | Tap 345kV 59904 Cottonwood - 60500 Edith Clarke Ckt #2 | 2027-12-31 | 2025-02-15 | True |  |  | Signed; security posted
27INR0128 | Bigway Solar II | NextEra Energy Interconnection Holdings, LLC | King | Solar | 206 | Tap 345KV #59904 Cottonwood - #60500 Edith Clarke Ckt #2 | 2027-12-31 | 2025-02-15 | True |  |  | Signed; security posted
25INR0401 | WOE Gyp King Wind | KSK Wind Farm 1, LLC | King | Wind | 304.29 | Tap 138kV 33798 GYP_18 – 6088 BENJ4A | 2030-08-31 |  |  |  |  | In study
24INR0508 | White Oak King Wind | KSK Wind Farm 1, LLC | King | Wind | 606.5 | 345 kV Gauss ( Bus # 60701) | 2030-08-31 |  |  |  |  | In study
24INR0541 | Kinney County Energy | Kinney County Energy, LLC | Kinney | Battery storage | 101.2 | Tap 138kV 8252 Brackett4A - 78255 L_PINTCR8_1Y | 2027-05-15 |  |  |  |  | In study
23INR0284 | Las Moras Battery | Las Moras Storage, LLC | Kinney | Battery storage | 101 | 8252 Brackett 138kV | 2029-07-01 |  |  |  |  | In study
25INR0502 | Longday BESS SLF | Longday Solar | Kinney | Battery storage | 0 | Tap 138 kV 8252 Brackettville - 8260 Escondido | 2027-12-15 |  |  |  |  | In study
25INR0501 | Longday Solar SLF | Longday Solar | Kinney | Solar | 200.8 | Tap138 kV 8252 Brackettville - 8260 Escondido | 2027-12-15 |  |  |  |  | In study
29INR0251 | Sugarberry Solar SLF | EG Sugarberry LLC | Kinney | Solar | 125 | 78255 Pinto Creek 138 kV | 2029-12-18 |  |  |  |  | In study
29INR0252 | Sugarberry Storage SLF | EG Sugarberry LLC | Kinney | Battery storage | 0 | 78255 Pinto Creek 138 kV | 2029-12-18 |  |  |  |  | In study
25INR0623 | Turkey Creek Battery Energy Storage System SLF | Greenray Solar Corporation | Kinney | Battery storage | 0 | 7425 ODLASW 138 kV | 2028-09-01 |  |  |  |  | In study
25INR0622 | Turkey Creek Solar SLF | Greenray Solar Corporation | Kinney | Solar | 180.9 | 7425 ODLASW 138kV | 2028-09-01 |  |  |  |  | In study
24INR0516 | French Riviera Storage | Arana Creek Battery Storage LLC | Kleberg | Battery storage | 75 | 5646 Riviera Substation 69kV | 2028-05-01 |  |  |  |  | In study
26INR0143 | Santa Garcias Solar | Oxy Renewable Energy LLC | Kleberg | Solar | 265 | Tap 138kV 8515 Alazan - 8458 Barney Davis | 2029-05-30 | 2025-12-31 |  |  |  | Signed
26INR0617 | Knox County Moore Storage | DM-KCM, LLC | Knox | Battery storage | 77 | 6110 Munday East Substation 138kV | 2028-06-30 |  |  |  |  | In study
26INR0112 | Lemma Solar | Greening USA Corp. | Knox | Solar | 100.61 | 6088 Benjamin AEP 138kV | 2028-07-01 |  |  |  |  | In study
28INR0009 | Oriole BES | Rolling Plains Solar | Knox | Battery storage | 150.39 | Tap 345kV 6076 Foxtail - 60791 Perigee | 2028-12-29 | 2025-12-08 |  |  |  | Signed
28INR0008 | Oriole Solar | Rolling Plains Solar | Knox | Solar | 503.91 | Tap 345kV 6076 Foxtail - 60791 Perigee | 2028-12-29 | 2025-12-08 |  |  |  | Signed
28INR0206 | Wagon Timber Solar | Wagon Timber Solar, LLC | Knox | Solar | 172.1 | 6110 Munday East 138kV | 2029-09-03 |  |  |  |  | In study
28INR0207 | Wagon Timber Storage | Wagon Timber Storage, LLC | Knox | Battery storage | 53.49 | 6110 Munday East 138kV | 2029-09-03 |  |  |  |  | In study
26INR0531 | West Munday Wind | Lake Creek Wind, LLC | Knox | Wind | 351.91 | Tap 345kV 60703 Gauss7D – 60712 Quasar | 2029-08-31 | 2025-07-21 | True |  |  | Signed; security posted
24INR0258 | Zeissel Solar | ZSS Power, LLC | Knox | Solar | 451.52 | #60094 Joule 345kV | 2028-06-30 | 2024-02-24 | True |  |  | Signed; security posted
26INR0089 | Crescent C BESS | OCI La Salle ESS LLC | La Salle | Battery storage | 508.34 | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) CKT#2 | 2028-02-12 |  |  |  |  | In study
25INR0395 | Hinkell BESS | Reveille BESS | La Salle | Battery storage | 78.05 | 8612 Reveille 138kV | 2027-07-01 |  |  |  |  | In study
26INR0088 | La Salle Solar | La Salle Solar LLC | La Salle | Solar | 512.6 | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) (Cuernos 345 kV New Station) | 2028-09-13 | 2025-11-03 | True |  |  | Signed; security posted
22INR0357 | Loma Pinta Solar | Loma Pinta Wind Energy, LLC | La Salle | Solar | 203.06 | 5705 Fowlerton 138kV | 2028-05-31 |  |  |  |  | In study
16INR0112 | Loma Pinta Wind | Enerverse | La Salle | Wind | 197.01 | 5705 Fowlerton 138kV | 2026-12-31 | 2017-12-13 |  |  |  | Signed
26INR0184 | Arc Energy Storage | Paris Energy Storage, LLC | Lamar | Battery storage | 204.5 | Tap 138kV 1693 Paris Switch - 11806 ENLOE T8 | 2028-06-30 |  |  |  |  | In study
27INR0409 | Baker Branch BESS | Mockingbird Storage Center, LLC | Lamar | Battery storage | 287.22 | Pacific Switch (PACSW) 345 kV Bus 11683 | 2029-12-31 |  |  |  |  | In study
23INR0026 | Baker Branch Solar | Mockingbird Solar Center, LLC | Lamar | Solar | 469.42 | tap 345kV 1692 Paris - 1690 Valley | 2026-09-30 | 2022-02-14 | True | 2024-04-01 | 2024-04-10 | Approved for synchronization
23INR0441 | Bug Tussle Wind Project | Bug Tussle Wind, LLC | Lamar | Wind | 396.8 | Tap 1729 Valley South and 1692 Paris | 2028-09-18 | 2024-07-10 |  |  |  | Signed
22INR0202 | Delilah Solar 1 | Delilah Solar Energy LLC | Lamar | Solar | 300 | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | 2026-12-31 | 2020-12-22 | True | 2023-07-11 | 2024-03-21 | Approved for synchronization
22INR0203 | Delilah Solar 2 | Delilah Solar Energy II LLC | Lamar | Solar | 317.58 | 345 kV TTRSW 11688 | 2026-12-31 | 2020-12-22 | True | 2024-10-29 | 2025-01-13 | Approved for synchronization
25INR0368 | Echols Grove Solar | Echols Grove, LLC | Lamar | Solar | 201.56 | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | 2027-06-30 | 2024-07-06 | True |  |  | Signed; security posted
23INR0486 | Lamar Unit 1 Repower | La Frontera Holdings, LLC | Lamar | Gas combined cycle | 66 | 1692 Paris Switch Station 345kV | 2027-12-18 |  |  |  |  | In study
24INR0262 | Lan Battery SLF | BR Solar, LLC | Lamar | Battery storage | 0 | Tap 345kV 1729 Valley South – 1692 Paris Switch | 2028-08-26 |  |  |  |  | In study
22INR0314 | Lan Solar SLF | BR Solar, LLC | Lamar | Solar | 182.2 | Tap 345kV 1729 Valley South – 1692 Paris Switch | 2028-08-26 |  |  |  |  | In study
23INR0225 | MRG GOODY SOLAR | MRG GOODY SOLAR PROJECT, LLC | Lamar | Solar | 170.82 | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | 2026-08-28 | 2023-11-07 | True | 2026-02-06 | 2026-03-27 | Approved for synchronization
24INR0305 | MRG Goody Storage | MRG Goody Solar Project LLC | Lamar | Battery storage | 52.29 | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | 2026-08-28 | 2023-11-07 | True | 2026-02-06 | 2026-03-27 | Approved for synchronization
25INR0505 | Mud Cat Solar SLF | Mud Cat Solar, LLC | Lamar | Solar | 100.5 | Tap 138KV 11768 Hawk Hollow – 1768 Deport | 2028-09-18 |  |  |  |  | In study
25INR0507 | Mud Cat Storage SLF | Mud Cat Solar, LLC | Lamar | Battery storage | 0 | 11768 Hawk Hollow – 1768 Deport 138kV | 2028-09-18 |  |  |  |  | In study
28INR0087 | North Royal Thermal (TEF- Due Diligence) | Invenergy Energy Transition Development LLC | Lamar | Gas turbine | 479 | Tap 345kV 1695 MOSES_5 - 11699 WOODARD_5 | 2030-08-01 |  |  |  |  | In study
24INR0186 | Rowdy Creek Solar | Rowdy Creek Solar LLC | Lamar | Solar | 351.78 | Woodfin Switch (#1465) 345kV | 2027-12-29 | 2025-05-02 | True |  |  | Signed; security posted
26INR0470 | Roxton Solar | Roxton Solar, LLC | Lamar | Solar | 116.8 | Tap 138 KV Bois Pump (1835) - Brookston (1833) | 2028-07-21 | 2026-09-03 | True |  |  | Signed; security posted | In study -> Signed; security posted
26INR0469 | Roxton Storage | Roxton Solar, LLC | Lamar | Battery storage | 102 | Tap 138 KV Bois Pump (1835) - Brookston (1833) | 2028-07-21 | 2026-09-03 | True |  |  | Signed; security posted | In study -> Signed; security posted
21INR0221 | Samson Solar 1 | Samson Solar Energy LLC | Lamar | Solar | 250 | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | 2026-12-31 | 2020-08-26 | True | 2021-06-30 | 2021-08-31 | Approved for synchronization
21INR0490 | Samson Solar 2 | Samson Solar Energy II LLC | Lamar | Solar | 203 | 345 kV TTRSW 11688 | 2026-12-31 | 2020-08-27 | True | 2024-08-19 | 2024-10-14 | Approved for synchronization
21INR0491 | Samson Solar 3 | Samson Solar Energy III LLC | Lamar | Solar | 250 | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | 2026-12-31 | 2020-08-27 | True | 2021-06-30 | 2021-10-26 | Approved for synchronization
30INR0002 | Southeast Oklahoma Pumped Storage | Apex Energy Solutions, LLC | Lamar | WAT | 1232 | 1692 Paris Switch 345kV | 2030-01-01 |  |  |  |  | In study
25INR0164 | Star Dairy Solar | Star Dairy Solar LLC | Lamar | Solar | 115.61 | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | 2027-07-12 | 2024-12-09 |  |  |  | Signed
25INR0334 | Star Dairy Storage | Star Dairy Storage | Lamar | Battery storage | 205.24 | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | 2027-07-12 | 2024-12-09 |  |  |  | Signed
28INR0277 | Aurora Energy Storage | Aurora Energy Storage, LLC | Lampasas | Battery storage | 306.2 | Tap 345kV --- KILL_SS_5 (3422) --- BUCK_H_5 (3424) | 2028-09-26 |  |  |  |  | In study
28INR0324 | Barkley Creek Solar | 174 Power Global Properties, LLC | Lampasas | Solar | 312.37 | Tap 345 kV Line from Russel Gap Switch (Bus# 3348) - Killeen Switch (Bus# 3422) | 2029-10-15 |  |  |  |  | In study
25INR0666 | GIBSON BRANCH BESS | Gibson Branch BESS LLC | Lampasas | Battery storage | 142.9 | 7064 Lampasas Substation 138kV | 2028-01-15 |  |  |  |  | In study
24INR0494 | Hana Springs BESS | Black Mountain Energy Storage II LLC | Lampasas | Battery storage | 100.8 | 7064 LAMPASAS 138KV | 2028-05-15 |  |  |  |  | In study
28INR0462 | Senterfitt Solar | AETS Development Holdings LLC | Lampasas | Solar | 68.39 | Tap 138 kV 7080 Lometa - 7064 Lampasas | 2029-07-03 |  |  |  |  | In study
26INR0147 | Seven Springs Solar | Hancock Springs, LLC | Lampasas | Solar | 145 | Tap 7061 COPPERAS COVE 7260 Kempner 138kV | 2028-05-26 | 2025-08-28 | True |  |  | Signed; security posted
30INR0037 | Solgen Solar | Lampasas Hybrid Energy LLC | Lampasas | Solar | 160.2 | 7066 Adamsville 138kV | 2029-08-30 |  |  |  |  | In study
30INR0038 | Solgen Storage | Lampasas Hybrid Energy LLC | Lampasas | Battery storage | 150.3 | 7066 Adamsville 138kV | 2029-08-30 |  |  |  |  | In study
24INR0543 | Thomas Cameron BESS | Thomas Cameron BESS LLC | Lampasas | Battery storage | 205.5 | Tap 345kV 3424 BUCKHORN SWITCH - 3422 KILLEEN SWITCH | 2029-04-28 | 2024-10-30 | True |  |  | Signed; security posted
24INR0069 | Triple B Solar Alt#2 | Triple B Solar LLC | Lampasas | Solar | 150 | Tap 138kV 7066 Adamsville - 7064 Lampasas | 2028-07-01 |  |  |  |  | In study
27INR0091 | Oak Tree Energy Storage | Live Oak Energy Storage, LLC | Lavaca | Battery storage | 310.2 | Tap Shaula (#5380) – South Texas (#5915) | 2030-09-20 | 2026-05-26 |  |  |  | Signed | In study -> Signed
30INR0091 | BM Great Rock Energy Center | Black Mountain Energy Storage II | Leon | Gas combined cycle | 1981.2 | Tap <345kV> <967> <GIBN_CREK_5> - <46020> <LIMEST_POI_5> Ckt<18> and <345kV> <79007> < YELLOW WOLF> - <46020> <LIMEST_POI_5> Ckt<50> | 2029-05-15 |  |  |  |  | In study
26INR0632 | Dempsey Solar SLF | Dempsey Solar LLC | Leon | Solar | 245.34 | Tap 138 KV Ridge (#37)-Robertson (#32) line; BEPC | 2028-09-08 |  |  |  |  | In study
28INR0238 | Dempsey Storage SLF | Dempsey Storage LLC | Leon | Battery storage | 0 | Tap the 138 KV Ridge (#37)-Robertson (#32) line; BEPC | 2028-09-08 |  |  |  |  | In study
25INR0230 | Great Rock BESS | Great Rock Storage LLC | Leon | Battery storage | 300.9 | Tap 345kV 46020 Limestone - 967 Gibbon Creek Ckt 18 | 2027-12-20 | 2024-08-23 |  |  |  | Signed
24INR0422 | Hollow Branch Creek Solar | Hollow Branch Creek Solar LLC | Leon | Solar | 460 | Tap 345kV 3390 Jewett - 44645 Singleton | 2028-06-30 | 2024-10-22 | True |  |  | Signed; security posted
25INR0513 | Kahla Storage | BT Kahla Storage, LLC | Leon | Battery storage | 200.9 | Tap 345kV 46020 Limestone 967 Gibbons Creek Circuit 50 | 2028-12-29 |  |  |  |  | In study
25INR0693 | Leon BESS | Leon BESS | Leon | Battery storage | 153.7 | Tab 138kv 3355 Grapeland_Magnolia - 3357 Pleasant_Springs. | 2028-02-16 |  |  |  |  | In study
25INR0342 | Nickel Spruce Solar | Nickel Spruce Solar LLC | Leon | Solar | 150 | Tap 138kV 6735 Pleasant Springs Switching Station - 6736 Middl | 2027-12-15 |  |  |  |  | In study
27INR0092 | Pecan BESS | Gransolar Texas Three LLC | Leon | Battery storage | 157.12 | (PSSE BUS# 47) HILTOPLKS8 138kV | 2028-12-31 |  |  |  |  | In study
21INR0428 | Pecan Prairie North | CG Leon County II LLC | Leon | Solar | 324.11 | CTT Yellow Wolf, bus # 79007 | 2027-05-01 | 2021-02-26 | True |  |  | Signed; security posted
21INR0371 | Pecan Prairie South | ConnectGen Operating LLC | Leon | Solar | 132.98 | CTT Yellow Wolf, bus # 79007 | 2027-05-01 | 2021-02-21 | True |  |  | Signed; security posted
25INR0199 | Bonham Solar SLF | J&J Solar Ranch LLC | Limestone | Solar | 138.4 | TAP 138 kV MEXIA_2_1_8 3632 - GROES_SE1_8 3634 | 2027-04-06 | 2024-08-07 | True |  |  | Signed; security posted
26INR0619 | Bonham Storage SLF | J&J Solar Ranch LLC | Limestone | Battery storage | 104.92 | Tap 138kV 3632 Mexia_Main - 3634 Groesbeck_Main | 2027-07-01 |  | True |  |  | Signed; security posted
21INR0260 | Chariot Storage | Chariot Storage LLC | Limestone | Battery storage | 50 | tap 69kV 99 Ben Hur - 107 Prairie Hill | 2028-02-29 |  |  |  |  | In study
23INR0367 | Fewell Solar | Fewell Solar LLC | Limestone | Solar | 203.5 | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | 2028-05-15 | 2023-08-18 | True |  |  | Signed; security posted
28INR0048 | Findley BESS | Adon Texas Sixteen LLC | Limestone | Battery storage | 51.74 | Tap 69kV #107 Prairie Hill - #99 Ben Hur | 2028-01-01 |  |  |  |  | In study
25INR0021 | Findley Solar | Adon Texas Sixteen LLC | Limestone | Solar | 50.34 | Tap 69kV #107 Prairie Hill - #99 Ben Hur | 2028-01-01 |  |  |  |  | In study
24INR0298 | Leighton Solar | Lavender Solar LLC | Limestone | Solar | 181 | 98 Fernleaf 138 kV | 2027-12-06 | 2024-05-28 | True |  |  | Signed; security posted
24INR0127 | Naduah Solar | Gransolar Texas Fifteen, LLC | Limestone | Solar | 77.6 | Tap 69kV Ben Hur (99) - Prairie Hill (107) | 2028-04-15 |  |  |  |  | In study
28INR0013 | Varadero Solar | NextEra Energy Interconnection Holdings, LLC | Limestone | Solar | 206 | #68092 Liberty Station 345kV | 2029-04-01 | 2025-12-12 | True |  |  | Signed; security posted
25INR0621 | Anagram Solar | Anagram Solar | Live Oak | Solar | 130.56 | 8156 Charter 138 kV | 2027-12-31 |  |  |  |  | In study
22INR0467 | Bird Dog Energy Storage | VESI 37 LLC | Live Oak | Battery storage | 60.4 | 5669 Argenta 69kV | 2026-10-23 | 2024-02-16 | True | 2026-08-05 | 2026-08-28 | Approved for synchronization
23INR0487 | Brightside Solar Alt POI | Brightside Solar, LLC | Live Oak | Solar | 50 | 8156 Charter Substation 138kV | 2026-08-14 | 2020-06-11 | True |  |  | Signed; security posted
27INR0375 | Buck Ranch Solar SLF | Buck Ranch Solar, LLC | Live Oak | Solar | 40.8 | 5690 WEST GEORGE WEST SUB 69kV | 2028-08-02 |  |  |  |  | In study
27INR0376 | Buck Ranch Storage SLF | Buck Ranch Solar, LLC | Live Oak | Battery storage | 40.8 | 5690 WEST GEORGE WEST SUB 69kV | 2028-08-09 |  |  |  |  | In study
26INR0529 | Electric E - West Texas Generation | Electric E Power Marketing | Loving | Gas turbine | 43.64 | #11166 ENPOD 138kV | 2028-04-09 |  |  |  |  | In study
30INR0099 | Quadspring BESS | Quadspring BESS, LLC | Loving | Battery storage | 200.7 | 138 kV ANDRANCHT_8(#1081) - Loving_8(#1092) | 2030-06-30 |  |  |  |  | In study
23INR0310 | Dunkel BESS | Momentum Energy Storage Partners | Lubbock | Battery storage | 226.4 | 59156 Yellow House Canyon 115kV | 2027-11-02 |  |  |  |  | In study
25INR0176 | Masava Storage | Savannah Oaks Solar Project, LLC | Madison | Battery storage | 257.04 | tap 345 kV 46020 Limestone Plant - 967 Gibbons Creek ckt 18 | 2028-09-30 |  |  |  |  | In study
25INR0131 | SOSA Storage | Sosa Energy Center, LLC | Madison | Battery storage | 154.63 | Tap 138kV 25 North Zulch - 47 Hilltop Lakes | 2027-07-20 | 2023-12-05 | True |  |  | Signed; security posted
25INR0286 | Savannah Oaks Solar | Savannah Oaks Solar Project LLC | Madison | Solar | 201.19 | Tap 345kV 46020 Limestone Plant - 967 Gibbons Creek | 2028-09-30 |  |  |  |  | In study
26INR0411 | Tex-Bar ESS | Tex-Bar ESS LLC | Madison | Battery storage | 201.5 | Tap 345kV JEWETT_S5 (#3390) -- SINGLETON (#44645) | 2029-09-08 | 2025-12-26 |  |  |  | Signed
26INR0247 | Jane Storage Energy Center | NMRE Holdings, LLC | Martin | Battery storage | 240.6 | 59901 Grelton 345 kV | 2030-11-01 |  | True |  |  | Signed; security posted
24INR0275 | Picadillo BESS | Black Mountain Energy Storage II | Martin | Battery storage | 100.83 | 23837 Buffalo 138kV | 2028-05-15 | 2024-01-23 |  |  |  | Signed
25INR0396 | Stewart Grady BESS | Grady BESS | Martin | Battery storage | 150.5 | Tap 138kV 11368 Expanse Switch – 23841 Sale Ranch | 2029-04-17 |  |  |  |  | In study
28INR0341 | Bastion BESS | BESS BASTION LLC | Matagorda | Battery storage | 154.3 | Blessing Substation 138 kV (ID 8121) | 2028-11-01 |  |  |  |  | In study
26INR0376 | Blackcat Storage | Matagorda ESS, LLC | Matagorda | Battery storage | 200.59 | 138kV Blackcat Substation (#80124) | 2027-12-31 |  |  |  |  | In study
27INR0141 | Bluefox Solar 1 | Industrial November Project LLC | Matagorda | Solar | 402.6 | #8754 Zoisite 345kV | 2029-05-31 |  |  |  |  | In study
28INR0063 | Bluefox Solar 2 | Industrial November Project LLC | Matagorda | Solar | 401.8 | #8754 Zoisite 345kV | 2030-01-17 |  |  |  |  | In study
28INR0064 | Bluefox Solar 3 | Industrial November Project LLC | Matagorda | Solar | 201.8 | #8754 Zoisite 345kV | 2030-04-18 |  |  |  |  | In study
25INR0271 | City Breeze BESS | City Breeze BESS LLC | Matagorda | Battery storage | 143.1 | 8111 MAGILL4A 138KV | 2027-03-18 | 2024-05-15 | True |  |  | Signed; security posted
26INR0250 | Duffy BESS | Duffy Energy Storage LLC | Matagorda | Battery storage | 241.05 | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | 2026-12-31 | 2025-07-28 | True |  |  | Signed; security posted
23INR0057 | Duffy Solar | Duffy Project Co LLC | Matagorda | Solar | 502.46 | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | 2027-12-31 | 2023-04-12 | True |  |  | Signed; security posted
24INR0338 | Eldora BESS | Eldora Energy LLC | Matagorda | Battery storage | 201.31 | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | 2028-07-02 | 2023-11-15 | True |  |  | Signed; security posted
24INR0337 | Eldora Solar | Eldora Energy LLC | Matagorda | Solar | 200.94 | Tap 345 kV 5915 South Texas Project – 44200 Hillje Ckt 1 | 2028-07-02 | 2023-11-15 | True |  |  | Signed; security posted
25INR0232 | Isaac Solar | Industrial Bravo Project LLC | Matagorda | Solar | 50.73 | 8114 Conoco 138kV | 2027-04-15 | 2023-10-18 | True |  |  | Signed; security posted
22INR0342 | Matagorda Solar | Matagorda Solar Farm, LLC | Matagorda | Solar | 101 | 5555 Shropshire 69kV | 2027-08-25 | 2022-06-08 | True |  |  | Signed; security posted
26INR0362 | Midfield BESS Project SLF | HQC Solar Holdings 1, LLC | Matagorda | Battery storage | 0 | Tap 138kV 8121 Blessing - 8125 Lolita | 2028-07-01 |  |  |  |  | In study
26INR0347 | Midfield PV Project SLF | HQC Solar Holdings 1, LLC | Matagorda | Solar | 150 | Tap 138kV 8121 Blessing - 8125 Lolita | 2028-07-01 |  |  |  |  | In study
26INR0714 | Pavlov BESS2 | Matagorda Clean Energy Center, LLC | Matagorda | Battery storage | 9.99 | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Pavlov TSP Station Code: PAVLOV Load Name: 138_13_1 Bus #: PTI Bus Number: 8608 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | 2026-12-13 | 2025-06-18 | True |  |  | Signed; security posted
24INR0020 | Percy Farm Solar | Percy Farm Solar 1, LLC | Matagorda | Solar | 198.63 | Tap 345kV 8123 Blessing - 5915 STP | 2029-05-31 |  |  |  |  | In study
20INR0155 | Peyton Creek Wind II | RWE Renewables Development, LLC | Matagorda | Wind | 241.2 | 42400 Refuge 345kV | 2026-12-31 | 2026-04-29 | True | 2024-12-30 | 2025-02-05 | Approved for synchronization
25INR0604 | Pledger BESS | Regis Pledger LLC | Matagorda | Battery storage | 9.5 | 29.188382, -95.911558 CNP Pledger Substation LONG Name: PLEDGER Short Name: PG ERCOT Bus #: 43120 ERCOT Load Name: TR2 Connectivity Node: TR2 | 2026-11-04 | 2024-04-29 | True |  |  | Signed; security posted
25INR0405 | Pledgor BESS | Pledgor BESS | Matagorda | Battery storage | 100.33 | Tap Gulftie (43340) – Pledger (43120) circuit 60 | 2028-04-06 |  |  |  |  | In study
26INR0429 | Post Trail Energy | Post Trail Energy, LLC | Matagorda | Battery storage | 103.5 | Tap 138kV Conoco 8138 - Black Cat 80124 | 2028-10-16 |  |  |  |  | In study
26INR0258 | Running Iron Solar | Running Iron Solar, LLC | Matagorda | Solar | 204.74 | Tap 138kV Conoco 8138 - Black Cat 80124 | 2028-10-16 |  |  |  |  | In study
27INR0557 | STP Unit2 High Pressure Turbine Upgrade | Constellation South Texas, LLC | Matagorda | Nuclear | 1336.52 | 5915 SO_TEX__345A 345 kV | 2027-04-23 |  |  |  |  | In study
23INR0466 | Shoshana Storage | Shoshana Storage Project LLC | Matagorda | Battery storage | 221 | Tap STP – Refuge ckt 27 | 2028-05-30 |  |  |  |  | In study
27INR0120 | Solar Star Bay City Storage | Solar Star Bay City Storage | Matagorda | Battery storage | 206.27 | Tap 138kV Conoco (#8138) – Black Cat (#80124) | 2029-02-27 |  |  |  |  | In study
27INR0465 | Althea Storage | Sugaree Solar LLC | Maverick | Battery storage | 251.3 | Tap Escondido (8260) - Brackettville (8252) | 2028-09-21 | 2025-09-29 | True |  |  | Signed; security posted
24INR0142 | De Los Santos | BRP De Los Santos BESS LLC | Maverick | Battery storage | 200.97 | 78016 Sunglow Substation 138kV | 2027-12-01 |  |  |  |  | In study
27INR0253 | Old Victory Energy Center | Nova Clean Energy LLC | Maverick | Battery storage | 202.5 | 8692 MAVERICK4A 138kV | 2030-06-01 |  |  |  |  | In study
26INR0311 | Senator Aggreko Solar | Senator Aggreko Solar LLC | Maverick | Solar | 258.91 | 138 kV Sunglow Substation (#78016) | 2029-03-31 | 2025-12-31 |  |  |  | Signed
26INR0312 | Senator Aggreko Storage | Senator Aggreko Storage LLC | Maverick | Battery storage | 147.63 | 138 kV Sunglow Substation (#78016) | 2029-03-31 | 2025-12-31 |  |  |  | Signed
24INR0617 | Serrano Storage | Maverick ESS, LLC | Maverick | Battery storage | 185.59 | 8267 GANSO Substation 138kV | 2027-12-01 |  |  |  |  | In study
27INR0389 | Sugaree Solar | Sugaree Solar LLC | Maverick | Solar | 251.4 | 138kV Escondido (8260) to Brackettville (8252) | 2028-09-21 | 2025-09-29 | True |  |  | Signed; security posted
28INR0110 | Biggs BESS | Biggs Battery Facility, LLC | McCulloch | Battery storage | 200 | 76006 Bow Wood 345 kV | 2029-06-16 |  |  |  |  | In study
28INR0111 | Biggs Solar | Biggs Solar Farm, LLC | McCulloch | Solar | 400 | #76006 Bow Wood 345 kV | 2029-06-16 |  |  |  |  | In study
27INR0593 | Pecan Ridge | Luminous Energy Renewables LLC | McCulloch | Battery storage | 150.79 | 60386 HEARTLAN2A 69kV | 2027-06-30 |  |  |  |  | In study
25INR0071 | Albatross BESS | Albatross Solar, LLC | McLennan | Battery storage | 50.4 | From Bus #165 Windsor Switch To Bus #161 McGregor | 2028-12-30 | 2026-09-02 | True |  |  | Signed; security posted | In study -> Signed; security posted
25INR0579 | Albatross BESS 2 | Albatross Solar, LLC | McLennan | Battery storage | 159.6 | Tap 138kV 165 Windsor Switch - 161 McGregor | 2028-12-30 | 2026-09-02 | True |  |  | Signed; security posted | In study -> Signed; security posted
28INR0157 | Axtell BESS | PP Axtell BESS LLC | McLennan | Battery storage | 306.94 | 345 kV Tiger Creek Switch (#3379) | 2029-04-16 |  |  |  |  | In study
24INR0104 | Braswell Solar | Gransolar Texas Nine, LLC | McLennan | Solar | 42.6 | Tap 69kV 147 Lorena - 3580 Eddy Substation (Will be converted to 138kV line before 3/14/25 per TSP) | 2028-03-15 |  |  |  |  | In study
29INR0229 | Brazos Energy Center 1 | Ferrovial Energy US 1 | McLennan | Battery storage | 300.6 | Tap <345><3791><POSSUMTROT_5 >-<3403> <LAKE_HALL_5> | 2029-09-18 |  |  |  |  | In study
29INR0230 | Brazos Energy Center 2 | Ferrovial Energy US 1 | McLennan | Battery storage | 300.6 | Tap <345><3791><POSSUMTROT_5 >-<3403> <LAKE_HALL_5> | 2029-09-18 |  |  |  |  | In study
24INR0356 | Cibeles Solar | Elawan Cibeles Solar, LLC | McLennan | Solar | 252.3 | 3379 Tiger Creek Switch (TIGERCREEK_5) 345 kV Substation | 2028-08-15 | 2025-02-25 | True |  |  | Signed; security posted
28INR0363 | Finch Storage | Finch Storage, LLC | McLennan | Battery storage | 201.3 | 165 WINDSORSW 138kV | 2028-09-30 |  |  |  |  | In study
26INR0111 | Graphic Packaging Gas | Graphic Packaging International | McLennan | Gas turbine | 43.36 | Tap 138kV 3446 Peppervine Switch - 3544 Castleman Substation | 2027-02-15 | 2026-07-30 | True |  |  | Signed; security posted
28INR0294 | Infrakey Waco Data Park Gas 1 | Infrakey Capital LLC | McLennan | Gas turbine | 180 | Tap 345kV 246 BOSQUESW5 – 3406 ELM_MOTT__5 | 2030-06-01 |  |  |  |  | In study
27INR0498 | Infrakey Waco Data Park Gas 2 | Infrakey Capital LLC | McLennan | Gas turbine | 0 | 252 BOSQUESW8 138kV (Brazos Connection) | 2030-06-01 |  |  |  |  | In study
24INR0038 | Jaguar Solar | PP Jaguar Solar LLC | McLennan | Solar | 300.87 | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | 2027-12-11 | 2022-09-12 | True |  |  | Signed; security posted
26INR0252 | Neutron Storage | Elawan Neutron Storage, LLC | McLennan | Battery storage | 104.5 | Tap 345kV 13405 Trading House - 68090 Sam Switch | 2028-04-29 | 2025-12-05 | True |  |  | Signed; security posted
26INR0380 | Pepper Solar Farm | Pepper Solar Farm LLC | McLennan | Solar | 120.72 | Tap 345kV 3405 THOUSE__5 - 3406 ELM_MOTT_5 | 2027-09-20 | 2025-06-23 | True |  |  | Signed; security posted
26INR0422 | PowerVault BESS | SMT Elm Mott BESS | McLennan | Battery storage | 254.8 | Tap 345kV 3406 Elm Mott - 3405 Tradinghouse Ses | 2028-07-01 |  |  |  |  | In study
19INR0100 | Prairie Hill Wind | Prairie Hill LLC | McLennan | Wind | 297.2 | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | 2027-09-30 | 2018-09-17 | True | 2020-10-19 | 2020-11-12 | Approved for synchronization
27INR0607 | Prairie Phoenix Wind | Prairie Hill Wind Project LLC | McLennan | Wind | 297.25 | 3403 Lake Hall 345kV | 2028-08-24 |  |  |  |  | In study
23INR0349 | Tokio Solar | Gransolar Texas Eight, LLC | McLennan | Solar | 170.45 | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | 2027-08-25 | 2023-11-06 | True |  |  | Signed; security posted
24INR0161 | Miranda Solar Project | Miranda Solar Project, LLC | McMullen | Solar | 261.67 | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | 2027-12-06 | 2024-07-16 | True |  |  | Signed; security posted
25INR0610 | Adam Bryant BESS | Adam Bryant BESS LLC | Medina | Battery storage | 99.52 | Tap 138kV 5225 HONDO – 5819 HONDO CREEK | 2027-12-01 |  |  |  |  | In study
27INR0206 | Chacon Creek | Cattlemen BESS LLC | Medina | Battery storage | 188.95 | (#8962) LYTLE4A 138KV | 2027-10-31 |  |  |  |  | In study
28INR0392 | Devine Mary BESS | Devine Mary BESS | Medina | Battery storage | 200.58 | 5813 PEARSONSW8 138 kV | 2028-11-21 |  |  |  |  | In study
27INR0203 | Dunlay Solar | Medina PV, LLC | Medina | Solar | 150.5 | Tap 138kV 5813 PearsonSW - 5225 Hondo | 2030-12-31 |  |  |  |  | In study
27INR0301 | Hondo Arroyo Solar | Hondo Creek Solar, LLC | Medina | Solar | 60.4 | Tap 138 kV 5225 Hondo - 5813 Pearson | 2028-07-01 |  |  |  |  | In study
27INR0437 | Hondo Arroyo Storage | Hondo Creek Solar, LLC | Medina | Battery storage | 100.7 | Tap 138 kV 5225 Hondo - 5813 Pearson | 2028-07-01 |  |  |  |  | In study
29INR0152 | Ranger BESS | Nova Clean Energy LLC | Medina | Battery storage | 155.2 | SSWG Bus name: CSTROVILESB8 , Bus# : 5804 Planning Bus long name: CSTROVILESB8, 138 kV | 2029-04-29 |  |  |  |  | In study
24INR0386 | Black & Gold Energy Storage | Black & Gold Energy Storage, LLC | Menard | Battery storage | 203.8 | 6364 Yellow Jacket Sub 138kV | 2027-07-30 | 2024-08-14 | True |  |  | Signed; security posted
27INR0241 | Callan Solar | Menard PV, LLC | Menard | Solar | 90.97 | Tap 69kV 60386 Heartland to 6363 Yellow Jacket | 2029-12-30 |  |  |  |  | In study
27INR0290 | Drill Baby Drill BESS | SBESS TX8 LLC | Midland | Battery storage | 204.31 | 23859 SALTFLAT 138KV | 2028-10-11 |  |  |  |  | In study
26INR0597 | Electric E - West Texas Generation 2 | Electric E Power Marketing | Midland | Gas turbine | 0 | #18664 SHAWPD 138kV | 2028-09-19 |  |  |  |  | In study
26INR0231 | Energy City BESS | Energy City BESS LLC | Midland | Battery storage | 204.9 | Tap 138kV AQUEDUCT SUB(#1172) - Mockingbird North Tap(#11299) | 2029-05-07 |  |  |  |  | In study
29INR0305 | Flurry Gas 1 | NET Power Canaveral LLC | Midland | Gas combined cycle | 109.8 | Tap 345 kV 1185 Midland County Northwest Switch (bus #1185) – Midland East (bus #1021) 345 kV Line Ckt 01 | 2029-04-16 |  |  |  |  | In study
23INR0300 | Holzer Solar | Greater Bryant G Solar, LLC | Midland | Solar | 17.7 | 11165 Sloan Switch 138kV | 2026-11-16 | 2022-07-18 | True | 2026-06-11 | 2026-07-02 | Approved for synchronization
25INR0144 | Jasper BESS | Jasper BESS, LLC | Midland | Battery storage | 201.13 | Tap 138kV 71230 Pleasant Farms - 1236 Pegasus South | 2028-10-11 | 2026-07-27 | True |  |  | Signed; security posted | Signed -> Signed; security posted
26INR0121 | Pioneer Hutt Solar (Alternative POI) | NextEra Energy Interconnection Holdings LLC | Midland | Solar | 116 | TAP 345kV 11028 Odessa Ehv - 59901 Grelton (West C) | 2028-07-01 |  |  |  |  | In study
23INR0502 | Adelite Storage | Adelite Storage Project LLC | Milam | Battery storage | 231.88 | Tap 138kV Thorndale North (bus #3659) – Rookie Switch (bus #3701) | 2028-04-20 | 2024-08-27 | True |  |  | Signed; security posted
26INR0635 | Aquila Solar | Ben Milam Solar 5 | Milam | Solar | 500 | 3706 Gibson Switch 345kV | 2026-11-12 |  |  |  |  | In study
26INR0630 | Betel Storage I | BETEL STORAGE I | Milam | Battery storage | 500 | 3377 Little Pond Switch ( LTPSW) 345 | 2026-08-12 |  |  |  |  | In study
26INR0633 | Betel Storage II | BETEL STORAGE II | Milam | Battery storage | 500 | 3377 Little Pond 345 | 2026-12-17 |  |  |  |  | In study
29INR0058 | Brahman Renewables Solar | Brahman Renewables | Milam | Solar | 100.6 | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | 2029-05-01 |  |  |  |  | In study
29INR0059 | Brahman Renewables Storage | Brahman Renewables | Milam | Battery storage | 206.88 | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | 2029-05-01 |  |  |  |  | In study
25INR0214 | Burgos Solar | Twin Oaks Solar, LLC | Milam | Solar | 105.52 | 3701 Rookie Switch 138 kV | 2027-11-22 |  |  |  |  | In study
22INR0605 | Camino Santiago Solar | Camino Solar Project, LLC | Milam | Solar | 196.3 | 345 kV Herndon Switch Substation (#3804) | 2027-09-01 | 2024-12-06 | True |  |  | Signed; security posted
27INR0216 | Champs Elysees BESS | Champs Elysees Renewables, LLC | Milam | Battery storage | 256.1 | Tap 345 kV 3377 Little Pond Switch - 3704 Hog Creek Switch | 2027-12-15 |  |  |  |  | In study
21INR0203 | Eastbell Milam Solar | EDP RENEWABLES NORTH AMERICA LLC | Milam | Solar | 244.86 | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | 2026-11-01 | 2022-09-02 | True | 2023-10-13 | 2023-11-01 | Approved for synchronization
24INR0208 | Eastbell Milam Solar II | Cattlemen Solar Park II LLC | Milam | Solar | 150.6 | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | 2026-11-01 | 2023-10-25 | True | 2024-09-13 | 2024-11-20 | Approved for synchronization
25INR0442 | Happy Dog Storage | Rosula Storage LLC | Milam | Battery storage | 104.52 | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | 2027-08-04 | 2024-12-16 |  |  |  | Signed
25INR0382 | HappyDogSolar | Rosula Solar LLC | Milam | Solar | 85.54 | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | 2027-08-04 | 2024-12-16 |  |  |  | Signed
23INR0235 | Hoyte Solar | Milano Solar LLC | Milam | Solar | 206.75 | (3707) Cannon Switch 138kV | 2027-04-15 | 2022-10-14 | True |  |  | Signed; security posted
29INR0120 | MilamStation Power Secured Gas Generation | LCC-TX8, LLC | Milam | Gas combined cycle | 846 | Little Pond Switch (Bus #3377) – Hog Creek Switch (Bus #3704) 345 kV Line | 2029-09-25 |  |  |  |  | In study
27INR0494 | Obbligato BESS | Obbligato BESS, LLC | Milam | Battery storage | 200.71 | Tap 138kV 120# TALBRTRIDG – 3683# MINERVA1_8 | 2030-02-28 |  |  |  |  | In study
27INR0441 | Pavo Creek Storage | Pavo Creek Storage, LLC | Milam | Battery storage | 154.2 | Tap #3659 Thorndale North - #3701 Rookie Switch 138 kV | 2028-09-21 |  |  |  |  | In study
23INR0468 | Petunia Storage Project | Petunia Storage Project LLC | Milam | Battery storage | 231.86 | 138kV Tap 3675 Rogers - 3485 Tin Roof Pod | 2028-06-30 |  |  |  |  | In study
23INR0478 | Rhoda Storage | Milam Energy, LLC | Milam | Battery storage | 141.23 | Tap 138kV 32 Robertson - 64 Milano | 2028-08-01 | 2025-12-31 |  |  |  | Signed
28INR0185 | San Gabriel Solar | San Gabriel Solar LLC | Milam | Solar | 255 | Tap 138 kV 3750 Vosslake - 3749 Buckholts | 2028-07-01 | 2026-08-06 |  |  |  | Signed
28INR0191 | San Gabriel Storage | San Gabriel Solar LLC | Milam | Battery storage | 127.5 | Tap 138 kV 3750 Vosslake - 3749 Buckholts | 2028-07-01 | 2026-08-06 |  |  |  | Signed
27INR0071 | Sandow Lakes Energy Station | SL Energy Power Plant I, LLC | Milam | Gas turbine | 1291.6 | #13430 Sandow Switch 138kV | 2028-04-01 |  |  |  |  | In study
22INR0350 | Sandow Solar | Sandow Lakes Ranch Solar I, LLC | Milam | Solar | 287.18 | tap one 345kV 7040 Austrop - 13429 Sandow line | 2028-06-01 |  | True |  |  | Signed; security posted
26INR0609 | Scorpius Solar | Ben Milam Solar 4 | Milam | Solar | 600 | 3377 LTPSW 345KV | 2029-06-14 |  |  |  |  | In study
25INR0389 | Stoneridge BESS | Stoneridge Solar, LLC | Milam | Battery storage | 101.9 | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP CKT 2 | 2026-12-31 | 2024-04-19 | True | 2025-06-26 | 2025-07-10 | Approved for synchronization
24INR0031 | Stoneridge Solar | Stoneridge Solar, LLC | Milam | Solar | 201.6 | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP Beulah Switch to tap above line | 2026-12-31 | 2023-05-15 | True | 2025-01-10 | 2025-04-01 | Approved for synchronization
24INR0070 | Sypert Branch Solar Project | Sypert Branch Solar LLC | Milam | Solar | 261.15 | Tap 345kV #3751 Scooter Switch - #3687 Bell County East Switch Ckt 2 | 2026-04-30 | 2023-10-12 | True | 2025-12-10 | 2025-12-12 | Approved for synchronization
24INR0042 | Yaupon Solar SLF | Yaupon Solar, LLC | Milam | Solar | 200.78 | Tap 345 kV Gibson Switch (3706) – TNP One (39950) | 2026-11-18 | 2023-09-28 | True | 2026-05-27 | 2026-08-13 | Approved for synchronization
24INR0169 | Yaupon Storage SLF | Yaupon Solar, LLC | Milam | Battery storage | 0 | to Tap 345 kV Gibson Switch (3706) – TNP One (39950) | 2028-07-01 | 2023-09-28 | True |  |  | Signed; security posted
29INR0065 | Cash Mills Storage Center | Mills Storage Center | Mills | Battery storage | 200.66 | Tap Line between Evant (bus#7068) and Goldthwaite (Bus# 7070) | 2029-06-01 |  |  |  |  | In study
26INR0238 | Clapton Solar | Clapton Solar | Mills | Solar | 200.99 | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | 2028-08-09 |  |  |  |  | In study
26INR0430 | Clapton Storage | Clapton BESS | Mills | Battery storage | 208.91 | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | 2028-08-09 |  |  |  |  | In study
28INR0438 | Moss Rock Storage | Invenergy Storage Development LLC | Mills | Battery storage | 157.12 | #7070 Goldthwaite 138kV | 2029-12-31 |  |  |  |  | In study
16INR0085 | Priddy Wind | ENGIE North America | Mills | Wind | 302.4 | tap 345kV 1444 Brown – 3422 Killeen | 2026-12-31 | 2020-08-13 | True | 2021-10-13 | 2021-11-19 | Approved for synchronization
27INR0105 | Starlight Solar | Mills Tx Solar LLC | Mills | Solar | 130.72 | tap the 138 kV Goldthwaite (#7070) – San Saba Switch (#77074) | 2030-05-09 | 2025-12-31 |  |  |  | Signed
27INR0107 | Starlight Storage | Mills Tx Solar LLC | Mills | Battery storage | 208.96 | Tap 138kV 7070 Goldthwaite – 77074 San Saba Switch | 2030-05-09 | 2025-12-31 |  |  |  | Signed
25INR0139 | Dolce BESS | Dolce BESS, LLC | Mitchell | Battery storage | 100.65 | Tap 138kV 1189 BARBER_LK1_8 - 19520 CHINAGRVX2_8 | 2029-01-31 |  |  |  |  | In study
25INR0430 | Hackberry Creek Solar | Hackberry Creek Solar LLC | Mitchell | Solar | 175.51 | tap 345kV 10053 Cattleman Switch - 1058 Longshore Switch | 2028-01-01 | 2025-12-02 | True |  |  | Signed; security posted
27INR0348 | Johnson Grass Solar | Johnson Grass Solar ,LLC | Mitchell | Solar | 195.8 | Tap 138kV (#11395) Navigation - (#10054) Cattlemen | 2028-04-19 |  |  |  |  | In study
28INR0307 | Prairie Power Wind | Prairie Power Wind, LLC | Mitchell | Wind | 302.9 | Tap 345 kV Longshore Switch (Bus# 1058) to Cattleman Switch (Bus# 10053) CKT 4 | 2029-04-17 |  |  |  |  | In study
28INR0119 | Rabbit Hollow Energy Storage | Rabbit Hollow Energy Storage, LLC | Mitchell | Battery storage | 341.8 | 1190 Barber Lake Switch 138kV | 2029-12-31 |  |  |  |  | In study
29INR0212 | Rosenix Solar | Rosenix Solar, LLC | Mitchell | Solar | 501.64 | Cattleman (#10053) – Gasconades (#76030) | 2030-04-20 |  |  |  |  | In study
29INR0213 | Rosenix Storage | Rosenix Solar, LLC | Mitchell | Battery storage | 258.26 | Cattleman (#10053) – Gasconades (#76030) | 2030-04-20 |  |  |  |  | In study
23INR0143 | Sepik BESS | BRP Sepik BESS LLC | Mitchell | Battery storage | 204.96 | tap 138kV 11342 Loraine South – 10050 Ranger Camp | 2028-03-01 |  |  |  |  | In study
27INR0327 | Sunflower Valley Storage | Sunflower Valley Storage, LLC | Mitchell | Battery storage | 205.7 | 1414 Champion Creek Substation 345 kV | 2029-04-17 |  |  |  |  | In study
26INR0420 | Whitetail BESS | Hunt Energy Network, LLC | Mitchell | Battery storage | 180 | tap Salt Mine (#23846) to Bulldog (#23833) 138kV | 2029-06-08 |  |  |  |  | In study
25INR0589 | Zeus Mitchell BESS | Mitchell BESS | Mitchell | Battery storage | 1042.94 | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | 2029-04-17 |  |  |  |  | In study
26INR0686 | Zeus Mitchell BESS II | Zeus Mitchell BESS II, LLC | Mitchell | Battery storage | 1042.94 | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | 2027-05-01 |  |  |  |  | In study
25INR0588 | Zeus Mitchell Solar | Mitchell Solar, LLC | Mitchell | Solar | 804.71 | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | 2029-04-17 |  |  |  |  | In study
26INR0387 | Zeus Spade BESS | Spade BESS | Mitchell | Battery storage | 446.3 | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | 2028-03-20 |  |  |  |  | In study
26INR0386 | Zeus Spade Wind | Spade Wind, LLC | Mitchell | Wind | 987.3 | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | 2028-03-20 |  |  |  |  | In study
30INR0140 | Enfinity Primrose | EG Primrose LLC | Montague | Battery storage | 200 | (741) DYEMOUND Substation 138kV | 2030-07-17 |  |  |  |  | In study
25INR0190 | Fortissimo BESS | Fortissimo BESS, LCC | Montague | Battery storage | 202.65 | 741 Dyemound 138kV | 2028-04-24 |  |  |  |  | In study
28INR0423 | Prairie Branch BESS | Prairie Branch Energy, LLC | Montague | Battery storage | 310.17 | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | 2029-12-01 |  |  |  |  | In study
28INR0422 | Prairie Branch Solar | Prairie Branch Energy, LLC | Montague | Solar | 301.23 | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | 2029-12-01 |  |  |  |  | In study
27INR0109 | Two Barbaras BESS | Two Barbaras BESS | Montgomery | Battery storage | 217.16 | Tap 138 kV Pinehurst (#46240) – Mill Creek (#44850) Line | 2029-01-04 | 2025-10-01 | True |  |  | Signed; security posted
27INR0324 | LONE STAR INDUSTRIAL PARK GAS POWER PROJECT | LONE STAR INDUSTRIAL PARK, LLC | Morris | Gas engines | 166 | 1795 Monticello SES 138kV | 2028-05-11 |  |  |  |  | In study
29INR0021 | Buzios BESS SLF | Buzios Energy Storage, LLC | Motley | Battery storage | 0 | Tap 345kV 59904 Cottonwood - 23922 White River Ckt 2 | 2029-07-01 |  |  |  |  | In study
24INR0399 | Buzios Solar | Roaring Springs Solar, LLC | Motley | Solar | 252 | Tap between Cottonwood (#59904) and White River (#23922) | 2026-07-31 | 2023-11-06 | True | 2025-08-27 | 2025-10-01 | Approved for synchronization
28INR0017 | Sitges Wind | Whistling Flats Wind, LLC | Motley | Wind | 600 | Tap 345kV 59904 Cottonwood–60500 Edith Clarke | 2030-03-31 |  |  |  |  | In study
27INR0313 | Spindletop Solar | Banita Creek Solar LLC | Nacogdoches | Solar | 286.4 | Tap Stryker [3109] - Lufkin [3117] 345 kV line | 2027-12-29 | 2025-12-29 | True |  |  | Signed; security posted
26INR0161 | Timberline Solar | Timberline Renewables, LLC | Nacogdoches | Solar | 201 | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | 2029-10-05 |  |  |  |  | In study
26INR0162 | Timberline Storage | Timberline Renewables, LLC | Nacogdoches | Battery storage | 100.5 | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | 2029-10-05 |  |  |  |  | In study
21INR0421 | Armadillo Solar | Armadillo Solar Center, LLC | Navarro | Solar | 150.48 | 3387 Revolution 138kV | 2026-12-31 | 2021-02-02 | True | 2026-07-27 |  | Approved for energization
25INR0247 | Bluebonnet Prairie Wind | Bluebonnet Prairie Wind, LLC | Navarro | Wind | 180 | Tap 138kV 200 CHATFIELD - 3454 MONTFTSS__8 | 2028-07-15 | 2025-07-03 | True |  |  | Signed; security posted
21INR0324 | Board Creek Wind | Limestone Wind Project, LLC | Navarro | Wind | 299.2 | 345kV 3386 Outlaw Switch | 2026-10-31 | 2021-08-19 | True | 2022-09-19 | 2022-10-06 | Approved for synchronization
26INR0180 | Cape Rich BESS | Cape Rich BESS | Navarro | Battery storage | 150.52 | 3387 Revolution Switch 138kV | 2030-04-18 | 2025-02-03 |  |  |  | Signed
26INR0130 | Elm Flats Solar SLF | Orca Falls Solar, LLC | Navarro | Solar | 125.84 | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | 2027-11-01 | 2025-11-21 | True |  |  | Signed; security posted
26INR0131 | Elm Flats Storage SLF | Orca Falls Solar, LLC | Navarro | Battery storage | 0 | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | 2027-11-01 | 2025-11-21 | True |  |  | Signed; security posted
24INR0120 | Eytcheson Ranches Solar | Gransolar Texas Fourteen, LLC | Navarro | Solar | 76.42 | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | 2028-01-01 |  |  |  |  | In study
24INR0206 | Glasgow Solar | Glasgow Solar LLC | Navarro | Solar | 203.5 | Tap 345kV #2466 Big Onion - #68091 Navarro | 2028-03-16 | 2023-11-08 | True |  |  | Signed; security posted
24INR0207 | Glasgow Storage | Glasgow Solar LLC | Navarro | Battery storage | 101 | Tap 345kV #2466 Big Onion - #68091 Navarro | 2028-03-16 | 2023-11-08 | True |  |  | Signed; security posted
23INR0171 | Goodalta Solar | GoodAlta Power Center LLC | Navarro | Solar | 221.36 | tap 138kV 3127 Trinidad - 212 Winkler | 2027-09-20 |  |  |  |  | In study
25INR0220 | Hector Solar | Hector Solar, LLC | Navarro | Solar | 81.59 | Haney (213) - Hubbard_8 (3515) 138kV Line | 2028-10-08 |  |  |  |  | In study
25INR0221 | Hector Storage | Hector Solar, LLC | Navarro | Battery storage | 42.69 | Haney (213) - Hubbard_8 (3515) 138kV Line | 2028-10-08 |  |  |  |  | In study
24INR0256 | Kennedy Solar | Kennedy Bypass Solar LLC | Navarro | Solar | 101.5 | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | 2028-12-31 |  |  |  |  | In study
24INR0391 | Kennedy Storage | Kennedy Bypass Solar LLC | Navarro | Battery storage | 25.3 | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | 2028-12-31 |  |  |  |  | In study
28INR0467 | Main Horn Solar | Main Horn Solar LLC | Navarro | Solar | 100.43 | 3387 Revolution 138 KV | 2029-09-17 |  |  |  |  | In study
28INR0335 | Oak Valley Solar | Oak Valley Solar LLC | Navarro | Solar | 251.3 | 68091 (Navarro) (345) | 2029-09-28 |  |  |  |  | In study
24INR0086 | Pisgah Ridge Solar 2 | Pisgah Ridge Solar 2, LLC | Navarro | Solar | 101.89 | Tap 345kV 68091 Navarro - 46020 Limestone | 2029-03-31 |  |  |  |  | In study
24INR0087 | Pisgah Ridge Storage 3 | Pisgah Ridge 3, LLC | Navarro | Battery storage | 101.36 | Tap 345kV 68091 Navarro - 46020 Limestone | 2029-03-31 |  |  |  |  | In study
28INR0182 | Ponferrada Solar | Karol Solar VI | Navarro | Solar | 148.87 | Tap 138 KV 3456 CORSWEST1_8 - 3457 CORS_MOBT_8 | 2029-04-06 |  |  |  |  | In study
26INR0228 | Santa Monica Solar | Karol Solar IV | Navarro | Solar | 105.85 | Tap 345 KV 68091 NAVARRO - 3381 BIGBRNW_5 Ckt 2 | 2028-09-20 |  |  |  |  | In study
22INR0437 | TORMES SOLAR | BDPU SOLAR TORMES LLC | Navarro | Solar | 356.6 | tap 345kV 1906 Venus - 68091 Navarro | 2027-03-31 | 2024-04-10 | True |  |  | Signed; security posted
24INR0188 | Tehuacana Creek Solar | Tehuacana Creek Solar LLC | Navarro | Solar | 505.43 | Tap 345kV 3381 Big Brown – 68091 Navarro circuit | 2027-05-18 | 2024-11-25 | True |  |  | Signed; security posted
24INR0205 | Wensowitch Solar | Greenalia Solar Power Wensowitch LLC | Navarro | Solar | 146.08 | Tapping 138 kV line Telico (192) to Montfort Switch (3454) | 2029-04-17 |  |  |  |  | In study
25INR0029 | Whistle Solar | Gransolar Texas Nineteen, LLC | Navarro | Solar | 56.3 | Tap 138kV 213 Haney – 3478 Navarro | 2028-05-15 |  |  |  |  | In study
28INR0292 | Wildflower Storage | Wildflower Storage LLC | Navarro | Battery storage | 359.1 | Drane switch #3295 | 2028-09-30 |  |  |  |  | In study
25INR0018 | Yellow Cat Wind | Yellow Cat Wind LLC | Navarro | Wind | 262 | Tap 345kV 1906 Venus - 68091 Navarro | 2027-03-05 | 2024-07-09 | True |  |  | Signed; security posted
26INR0625 | Buffalo Gap 2 Wind Repower | Buffalo Gap Wind Farm 2, LLC | Nolan | Wind | 231.49 | 6216 Bluff Creek 138 kV | 2027-02-01 | 2005-02-28 | True |  |  | Signed; security posted
26INR0297 | Buzzi Maryneal Wind Project | Buzzi Unicem USA | Nolan | Wind | 18 | 1413 SWEETCRK-9 | 2026-01-02 |  |  |  |  | In study
24INR0627 | Champion Wind Repower | Champion Wind Farm, LLC | Nolan | Wind | 0.31 | Bus# 1048 - Tonkawa | 2026-12-31 | 2007-01-19 | True |  | 2025-01-13 | Approved for synchronization
23INR0008 | Harley Hand Solar | HECTATE ENERGY HARLEY HAND SOLAR LLC | Nolan | Solar | 505.5 | 11420 Sweetwater East 345kV | 2029-04-07 |  |  |  |  | In study
23INR0214 | Harley Hand Storage | Hecate Energy Harley Hand Storage LLC | Nolan | Battery storage | 503.4 | 11420 Sweetwater East 345kV | 2029-04-07 |  |  |  |  | In study
28INR0349 | Jaguarundi Energy Storage | PowerPulse LLC | Nolan | Battery storage | 152.02 | Bus # 1339, Eskota 138kV | 2029-11-10 |  |  |  |  | In study
18INR0031 | Maryneal Wind | Maryneal Windpower, LLC | Nolan | Wind | 182.4 | 71050 Bitter Creek 345kV | 2026-08-31 | 2020-01-31 | True | 2021-01-08 | 2021-04-23 | Approved for synchronization
28INR0386 | Sagebrush Wind | ACE DevCo NC, LLC | Nolan | Wind | 200.5 | TAP 345KV 11420 SWEETWATER EAST - 11406 CENTRAL BLUFF CKT2 | 2029-12-01 |  |  |  |  | In study
23INR0473 | Sepanta Solar | BREG - Belgian Renewable Energy Group | Nolan | Solar | 218 | 10198 ESKOTA_9 138kV (PSS/E BUS #10198, Station Name: ESKOTA_8, kV: 138 kV) Property is adjacent (West) to the Oncor Sweetwater Eskota Switch #10198. POI would simply be on the other side of the fence of the switch. | 2029-09-18 |  |  |  |  | In study
18INR0073 | Sweetwater 1 repower | Leeward Energy | Nolan | Wind | 3 | 71050 Bitter Creek 345kV | 2024-11-30 | 2002-10-23 |  |  |  | Signed
17INR0068 | Sweetwater 2 repower | Leeward Energy | Nolan | Wind | 7.3 | 71050 Bitter Creek 345kV | 2024-11-30 | 2003-06-27 |  |  | 2017-12-20 | Approved for synchronization
29INR0325 | Sweetwater 4 Repower | Sweetwater Wind 4 LLC | Nolan | Wind | 421.2 | <71050> <L_BITTCR5_1Y> <345kV> | 2029-02-01 |  |  |  |  | In study
28INR0504 | Sweetwater 5 Repower | Sweetwater Wind 5 LLC | Nolan | Wind | 79.1 | Bitter Creek Substation | 2029-02-01 |  |  |  |  | In study
27INR0218 | Themisto Solar | Themisto Solar, LLC | Nolan | Solar | 301.4 | Tap 345kV Champion Creek #1414 – Sweetwater East #11420 | 2029-06-30 |  |  |  |  | In study
27INR0576 | Trailblazer BESS | Trailblazer Infrastructure LLC | Nolan | Battery storage | 261.97 | 11420 Sweetwater East Switch 345 kV | 2027-12-12 |  |  |  |  | In study
27INR0575 | Trailblazer Natural Gas Generation Plant | Trailblazer Infrastructure LLC | Nolan | Gas turbine | 1026 | 11420 Sweetwater East Switch 345 kV | 2027-12-12 |  |  |  |  | In study
27INR0578 | Trailblazer Solar | Trailblazer Infrastructure LLC | Nolan | Solar | 323.02 | #11420 Sweetwater East Switch 345 kV | 2027-12-12 |  |  |  |  | In study
17INR0069 | Trent repower | TRENT WIND FARM LLC | Nolan | Wind | 6.4 | 1338 Eskota 138kV | 2026-01-01 | 2018-10-19 |  |  | 2019-05-09 | Approved for synchronization
28INR0437 | Barbara BESS | Barbara BESS LLC | Nueces | Battery storage | 200.51 | LINE TAP OF WESTSIDE (8485) AND WEIL TRACT (8482) 138 KV TRANSMISSION LINE | 2028-05-02 |  |  |  |  | In study
24INR0528 | Blanquilla BESS | Blanquilla BESS LLC | Nueces | Battery storage | 200.78 | Tap 138kV 8452 LON_HILL4A - 8441 NUECES_B4A | 2028-05-19 | 2024-09-05 | True |  |  | Signed; security posted
26INR0222 | GOTHAM BESS | AEU BATTERY PROJECT IV LLC | Nueces | Battery storage | 151.2 | 5640 DRISCOLLSUB9 69kV | 2027-03-17 |  |  |  |  | In study
27INR0337 | Jalisco Cogen | HEP Power Generation, LLC | Nueces | Gas combined cycle | 167.8 | 8475 JAVELINA4A 138 KV | 2029-05-31 |  |  |  |  | In study
28INR0121 | Jalisco Peaker | HEP Power Generation, LLC | Nueces | Gas turbine | 183.6 | 8475 JAVELINA4A 138kV | 2029-05-31 |  |  |  |  | In study
25INR0329 | Lynx Energy Storage | Corpus Battery Storage, LLC | Nueces | Battery storage | 125.3 | 138KV Tap 8921 Terra Verde - 8518 Kingsville | 2026-05-01 | 2024-04-09 | True | 2026-03-19 | 2026-04-07 | Approved for synchronization
27INR0655 | Lynx Energy Storage_Full | Corpus Battery Storage, LLC | Nueces | MWH | 50 | PRIMAVERA 138kV Substation | 2027-12-01 |  |  |  |  | In study | new
25INR0375 | NavBoot BESS | Navboot BESS LLC | Nueces | Battery storage | 303.7 | 8858 MCKENZIE4A 138kV | 2027-11-11 | 2025-10-20 |  |  |  | Signed
23INR0061 | Noria Solar DCC | Noria Hondo Solar LLC | Nueces | Solar | 145 | 85000 Nelson Sharpe 345kV | 2028-04-21 | 2022-10-12 | True |  |  | Signed; security posted
23INR0062 | Noria Storage | Noria Hondo Solar LLC | Nueces | Battery storage | 75 | 85000 Nelson Sharpe 345kV | 2028-04-21 | 2022-10-12 | True |  |  | Signed; security posted
27INR0047 | Sunscape Renewable Energy Solar SLF | Sunscape Renewable Energy LLC | Nueces | Solar | 522.75 | Bus# 8455 Lon C Hill to Bus# 80078 Reforzar 345 kV Line | 2028-10-31 | 2024-07-18 | True |  |  | Signed; security posted
27INR0048 | Sunscape Renewable Energy Storage SLF | Sunscape Renewable Energy LLC | Nueces | Battery storage | 0 | Tap 345kV 8455 Lon C Hill -- 80078 Reforzar | 2028-10-31 | 2024-07-18 | True |  |  | Signed; security posted
25INR0076 | Violet Storage | VIOLET STORAGE | Nueces | Battery storage | 151 | McKenzie Road (8858) 138 kV Substation | 2029-07-01 |  |  |  |  | In study
21INR0509 | McClure Solar | McClure Solar LLC | Palo Pinto | Solar | 105.73 | tap 69kV 785 Oran - 343 Morris Sheppard | 2025-12-31 |  |  |  |  | In study
26INR0364 | Pollo Pinto Solar | TX Palo Pinto SB 6, LLC | Palo Pinto | Solar | 100.57 | Tap 138kV 331 RWMILLER - 320 JAYBIRD | 2029-02-24 |  |  |  |  | In study
25INR0482 | Vault Solar | PPM THR Solar | Palo Pinto | Solar | 108.5 | Tap #331 Rwmiller - #320 Jaybird 138kV | 2027-12-31 | 2026-06-30 | True |  |  | Signed; security posted
26INR0498 | Buckaroo BESS | Weatherford BESS LLC | Parker | Battery storage | 120 | Tap 138kV BROCK(487) – STHBROCKSW(489) | 2027-12-08 |  |  |  |  | In study
27INR0571 | Nabla Energy Storage I | Nabla Park LLC | Parker | Battery storage | 750 | Double Tap 345kV Parker (1436) - Benbrook (1873 & 1869) DCKT | 2029-09-17 |  |  |  |  | In study
28INR0466 | Nabla Energy Storage II | Nabla Park LLC | Parker | Battery storage | 750 | Double Tap 345kV Parker (1436) - Benbrook (1873 & 1869) DCKT | 2029-09-17 |  |  |  |  | In study
23INR0368 | Rocking X Solar | 7100 Tin Top LLC | Parker | Solar | 602.2 | Tap the 345 kV Parker Switch (bus#1436) – Comanche Peak SES (bus#1900) Double-Circuit line, Circuit 1. | 2027-09-20 |  |  |  |  | In study
26INR0734 | Alamo Street BESS2 | Momentum Pilsner, LLC | Pecos | Battery storage | 9.99 | TSP Station Name: Alamo Street Sub TNP TSP Station Code: ALAMO_ST Load Name / Load Transformer Name: ALAMO_2 Bus #: PTI Bus Number: 38331 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 9631 | 2027-03-30 | 2023-02-01 | True |  |  | Signed; security posted
29INR0324 | Ashtrom Marigold BESS SLF | Marigold BESS LLC | Pecos | Battery storage | 153.9 | 860 GIRVINSW 345kV | 2029-04-26 |  |  |  |  | In study
22INR0386 | BRP Octans BESS | BRP OCTANS BESS LLC | Pecos | Battery storage | 129.57 | 6671 Tombstone 138kV | 2029-12-01 |  |  |  |  | In study
30INR0018 | Big Canyon Wind | Longfellow Wind, LLC | Pecos | Wind | 1500 | 38441 Bottlebrush 345kV | 2030-07-01 | 2025-12-24 | True |  |  | Signed; security posted
26INR0537 | Comanche Creek generating station | Longfellow Power LLC | Pecos | Gas engines | 107 | TNCENTRY1_1 [138 kV] ( 38431) | 2027-12-31 |  |  |  |  | In study
17INR0070 | Desert Sky repower | DESERT SKY WIND FARM LLC | Pecos | Wind | 7.2 | two LCRA 138kV | 2023-05-16 | 2018-10-18 | True |  | 2019-09-06 | Approved for synchronization
28INR0114 | Elk Ridge Solar | Elk Ridge Solar, LLC | Pecos | Solar | 503 | AEP Solstice Substation #60404 | 2030-07-01 | 2026-09-22 | True |  |  | Signed; security posted | In study -> Signed; security posted
27INR0139 | Gatsby Energy Storage | Gatsby Energy Storage LLC | Pecos | Battery storage | 103.36 | Fort Lancaster 138 kV Substation (PSSE Bus #76579) | 2030-12-31 |  |  |  |  | In study
29INR0347 | Glass Mountain BB Solar 1 | Glass Mountain Solar, LLC | Pecos | Solar | 302.66 | Tap 345kV 60404 Solstice to 38441 Bottlebrush | 2029-03-01 |  |  |  |  | In study
29INR0348 | Glass Mountain BB Solar 2 | Glass Mountain Solar II, LLC | Pecos | Solar | 302.66 | Tap 345kV 60404 Solstice to 38441 Bottlebrush | 2029-03-01 |  |  |  |  | In study
29INR0357 | Glass Mountain BB Solar 3 | Glass Mountain Solar III, LLC | Pecos | Solar | 302.61 | Tap 345kV 60404 Solstice to 38441 Bottlebrush | 2029-10-01 |  |  |  |  | In study
29INR0358 | Glass Mountain BB Solar 4 | Glass Mountain Solar IV, LLC | Pecos | Solar | 302.61 | Tap 345kV 60404 Solstice to 38441 Bottlebrush | 2029-10-01 |  |  |  |  | In study
29INR0349 | Glass Mountain BB Solar 5 | Glass Mountain Solar V, LLC | Pecos | Solar | 302.61 | Tap 345kV 60404 Solstice to 38441 Bottlebrush | 2029-10-01 |  |  |  |  | In study
26INR0550 | Grand Mesa BESS | PERRY GREEN POWER LLC | Pecos | Battery storage | 253.28 | 76582 MESA VIEW SWITCH 138kV | 2027-09-28 |  |  |  |  | In study
30INR0084 | Gravitas I Natural Gas | S&S Renewables, LLC | Pecos | Gas engines | 1247.04 | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | 2030-06-30 |  |  |  |  | In study
30INR0083 | Gravitas I Solar | S&S Renewables, LLC | Pecos | Solar | 1124.75 | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | 2030-06-30 |  |  |  |  | In study
30INR0085 | Gravitas I Wind | S&S Renewables, LLC | Pecos | Wind | 636.54 | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | 2030-06-30 |  |  |  |  | In study
18INR0069 | Indian Mesa repower | Nextera | Pecos | Wind | 9.3 | 76019 Indian NWP 138kV | 2026-12-31 | 2018-12-04 |  |  | 2018-11-02 | Approved for synchronization
27INR0146 | Larrea Solar | Greasewood IV LLC | Pecos | Solar | 231.6 | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | 2029-09-18 |  |  |  |  | In study
27INR0056 | Laurel Wind Energy Center | LAUREL ENERGY CENTER, LLC | Pecos | Wind | 306.6 | Tap Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 2 and Tap Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 1 | 2027-12-31 | 2024-10-25 | True |  |  | Signed; security posted
24INR0453 | Longfellow BESS I | CENTURY GAS PROCESSING, LLC | Pecos | Battery storage | 54.99 | 38432 TNCENTRY1_1 138 KV | 2028-03-30 | 2025-04-15 | True |  |  | Signed; security posted
24INR0455 | Longfellow BESS II | CENTURY GAS PROCESSING, LLC | Pecos | Battery storage | 105.75 | 38432 TNCENTRY2_1 138 KV | 2028-03-30 | 2025-04-15 | True |  |  | Signed; security posted
24INR0452 | Longfellow Solar I | CENTURY GAS PROCESSING, LLC | Pecos | Solar | 178.2 | 38431 TNCENTRY1_1 138 KV | 2028-12-31 | 2025-04-15 |  |  |  | Signed
24INR0454 | Longfellow Solar II | CENTURY GAS PROCESSING, LLC | Pecos | Solar | 207.36 | 38432 TNCENTRY2_1 138 KV | 2028-12-31 | 2025-04-15 |  |  |  | Signed
30INR0053 | MRR Solar | Antler Peak Solar, LLC | Pecos | Solar | 500 | Solstice Substation #60384 -AEP | 2030-07-01 | 2026-09-15 | True |  |  | Signed; security posted | In study -> Signed; security posted
22INR0365 | Mensa BESS | BRP Mensa BESS LLC | Pecos | Battery storage | 308.98 | 60718 Pecos Valley 138kV | 2028-06-01 |  |  |  |  | In study
29INR0181 | Pecos Flats Solar | Glass Mountain Solar, LLC | Pecos | Solar | 302.38 | 60404 SOLSTICE 345 kV | 2029-10-20 |  |  |  |  | In study
29INR0182 | Pecos Flats Solar II | Glass Mountain Solar, LLC | Pecos | Solar | 301.5 | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | 2029-02-05 |  |  |  |  | In study
29INR0183 | Pecos Flats Solar III | Glass Mountain Solar, LLC | Pecos | Solar | 301.5 | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | 2029-02-05 |  |  |  |  | In study
30INR0131 | Pecos Flats Wind I | Pecos Flats Wind, LLC | Pecos | Wind | 506.9 | Tap Bottlebrush (38441) to White Baker (38435) 345kV Line (TNMP) | 2030-06-29 |  |  |  |  | In study
30INR0132 | Pecos Flats Wind II | Pecos Flats Wind II, LLC | Pecos | Wind | 507.9 | Tap 345kV 38441 Bottlebrush to 38435 White Baker 345kV line (TNMP) | 2030-06-29 |  |  |  |  | In study
27INR0510 | Pecos Wind | Midnight Energy Center, LLC | Pecos | Wind | 193.8 | Tap 345 kV 60404 Solstice (SOLSTICE7A) – 76002 Bakersfield (L_BAKERS5_1Y) | 2028-05-30 | 2026-03-18 |  |  |  | Signed
30INR0100 | Pentarise BESS | Pentarise BESS, LLC | Pecos | Battery storage | 150.6 | 138 kV Pig Creek (#60393) | 2030-06-30 |  |  |  |  | In study
31INR0019 | Permian I Natural Gas | S&S Renewables, LLC | Pecos | Gas engines | 1246.95 | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | 2030-06-30 |  |  |  |  | In study
31INR0018 | Permian I Solar | S&S Renewables, LLC | Pecos | Solar | 1125.73 | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | 2030-06-30 |  |  |  |  | In study
30INR0086 | Permian I Wind | S&S Renewables, LLC | Pecos | Wind | 636.54 | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | 2030-06-30 |  |  |  |  | In study
28INR0260 | Rio Vista Solar | Rio Vista Solar, LLC | Pecos | Solar | 553.66 | Tap 138kV #60393 PigCreek4A – #60385 Solstice4A | 2030-09-02 |  |  |  |  | In study
28INR0261 | Rio Vista Storage | Rio Vista Storage, LLC | Pecos | Battery storage | 103.37 | Tap 138kV #60393 Pigcreek4A – #60385 Solstice4A | 2030-09-02 |  |  |  |  | In study
27INR0653 | Rock House Draw Gas | Longfellow Power LLC | Pecos | Gas engines | 523 | 38431 TNCENTRY1_1 138 KV | 2027-11-29 |  |  |  |  | In study
29INR0147 | Selenite Springs Solar | Selenite Springs Solar, LLC | Pecos | Solar | 253 | Tap 138kV 38355 Leon Creek Switching Station - 38308 Woodhouse Switching Station | 2028-08-30 | 2025-12-24 | True |  |  | Signed; security posted
26INR0296 | Sherbino II BESS SLF | Phoenix Battery Storage, LLC | Pecos | Battery storage | 77.37 | 38430 TNMP White baker Switching Station 138kV | 2027-04-19 | 2024-08-01 | True |  |  | Signed; security posted
19INR0120 | Sherbino II Wind repower | Sherbino II Wind Farm LLC | Pecos | Wind | -18 | 38430 TN White Baker 138kV | 2026-08-22 | 2008-02-28 | True |  | 2020-06-09 | Approved for synchronization
29INR0025 | Skyrider Wind | NextEra Energy Interconnection Holdings, LLC | Pecos | Wind | 370 | 138kV #38365 TNPINION | 2028-07-01 | 2025-12-23 | True |  |  | Signed; security posted
30INR0058 | Springfield Solar | BOULEVARD ASSOCIATES, LLC | Pecos | Solar | 400 | Tap Leon Creek (#38355) to Woodhouse Station (#38308) 138kV line | 2028-08-30 | 2025-12-24 | True |  |  | Signed; security posted
29INR0188 | Star Of Texas Solar | BOULEVARD ASSOCIATES, LLC | Pecos | Solar | 415 | 60152 Fort Stockton Switch 345kV | 2029-07-01 |  |  |  |  | In study
30INR0113 | The Giant Arc I | Powering Knowledge, LLC | Pecos | Gas engines | 1300 | Bus #60404 SOLSTICE CKT 01 | 2030-04-08 |  |  |  |  | In study
30INR0105 | The Giant Arc-II | Powering Knowledge, LLC | Pecos | Gas engines | 1300 | Bus #60404 SOLSTICE CKT 02 | 2030-04-11 |  |  |  |  | In study
26INR0715 | Tierra Bonita BESS SLF | Greasewood II BESS LLC | Pecos | Battery storage | 0 | 860 GIRVINSW 345kV | 2029-06-01 |  |  |  |  | In study
26INR0230 | Titus Sienta Solar | Sol Sienta Solar, LLC | Pecos | Solar | 501.93 | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | 2029-04-19 |  |  |  |  | In study | new
29INR0287 | Valentine Energy Center | Valentine Energy Center, LLC | Pecos | Gas engines | 162.3 | 60400 Lynx 138kV | 2031-02-28 |  |  |  |  | In study
29INR0263 | Whitethorn Solar Project | Greasewood III LLC | Pecos | Solar | 163.1 | 345KV 860 GIRVINSW | 2029-04-26 |  |  |  |  | In study | new
27INR0440 | Wisdom BESS SLF | Wisdom Green Energy LLC | Pecos | Battery storage | 102.88 | Tap 138 kV #38455 HOLIDAY SUB TNP - 138 kV #38450 SOAPTREE TNP | 2027-10-06 | 2026-03-18 |  |  |  | Signed | In study -> Signed
27INR0438 | Wisdom Solar SLF | Wisdom Green Energy LLC | Pecos | Solar | 299.37 | Tap 138 kV #38455 HOLIDAY SUB TNP - #38450 SOAPTREE TNP | 2027-10-06 | 2026-03-18 |  |  |  | Signed | In study -> Signed
18INR0080 | Woodward 2 repower | Nextera | Pecos | Wind | 0 | 60400 Lynx 138kV | 2026-12-31 | 2018-12-18 | True |  | 2018-12-19 | Approved for synchronization
18INR0079 | Woodward I repower | Nextera | Pecos | Wind | 0 | 60400 Lynx 138kV | 2026-12-31 | 2018-12-12 | True | 2019-11-07 | 2019-11-13 | Approved for synchronization
27INR0620 | st gall IIIA Storage | Tempus Power Management LLC | Pecos | Battery storage | 200.69 | 38355 LEON_CRK 138kV | 2028-06-01 |  |  |  |  | In study
27INR0621 | st gall IIIB Storage | Tempus Power Management LLC | Pecos | Battery storage | 200.69 | 38355 LEON_CRK 138kV | 2028-06-01 |  |  |  |  | In study
25INR0370 | Willis Storage | Majewski Storage LLC | Rains | Battery storage | 176.13 | tap 138kV Emory North 3171 to Liberty POD 1723 | 2028-05-31 | 2025-04-07 | True |  |  | Signed; security posted
22INR0383 | BRP Musca BESS | BRP Musca BESS LLC | Reagan | Battery storage | 100.51 | 60361 Santa Rita 138kV | 2027-12-01 |  |  |  |  | In study
27INR0315 | Old Roman Energy Center | Nova Clean Energy LLC | Reagan | Battery storage | 207.34 | 23868 STILES 138 KV | 2029-07-26 |  |  |  |  | In study
29INR0042 | Slager Lake Wind | NextEra Energy Resources Interconnection Holdings, LLC | Reagan | Wind | 310.2 | Tap 345kV 59903 Bearkat – 76000 NORTMC5_1Y; Badger 345 kV Station | 2029-07-01 | 2025-12-23 |  |  |  | Signed
23INR0548 | Leakey BESS | Regis Leaky LLC | Real | Battery storage | 9.9 | Station Name (TDSP Station Code): LEAKEY; Load/Load Transformer Name: L_LEAKEY9_1Y; PTI BUS Name: 7426; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 24.9kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | 2026-11-13 | 2023-01-18 | True | 2026-07-02 | 2026-07-10 | Approved for synchronization
27INR0292 | Donelson Solar SLF | Donelson Solar | Red River | Solar | 75.44 | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | 2028-10-17 |  |  |  |  | In study
27INR0293 | Donelson Storage SLF | Donelson Storage | Red River | Battery storage | 0 | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | 2028-10-17 |  |  |  |  | In study
28INR0125 | Silverbell Solar | Silverbell Energy Center, LLC | Red River | Solar | 125.59 | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | 2028-09-30 |  |  |  |  | In study
28INR0124 | Silverbell Storage | Silverbell Energy Center, LLC | Red River | Battery storage | 129.18 | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | 2028-09-30 |  |  |  |  | In study
26INR0389 | AGGIE STORAGE PROJECT SLF | reNRG TX 8 LLC | Reeves | Battery storage | 0 | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER: 38113 POI LOCATION: 31.396675, -103.6252777 COUNTY: REEVES | 2027-11-30 |  |  |  |  | In study
26INR0388 | Aggie Solar Project SLF | reNRG TX 8 LLC | Reeves | Solar | 103.7 | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER : 38113 COUNTY : REEVES POI LOCATION: 31.396675, -103.6252777 | 2027-11-30 |  |  |  |  | In study
28INR0499 | Alpha Digital Campus Combined-cycle and Co-located Load | PowerBridge LLC | Reeves | Gas combined cycle | 58.26 | 38044 TNCOWPEN__3 345kV | 2027-12-31 |  |  |  |  | In study
25INR0112 | August Draw Solar | August Draw Solar Holdings, LLC | Reeves | Solar | 250 | Tap 138kV 60207 Verhalen – 60808 Hoefs Road | 2028-06-27 | 2025-09-12 | True |  |  | Signed; security posted
25INR0146 | Blue Heron BESS | Blue Heron BESS, LLC | Reeves | Battery storage | 201.13 | Tap 138kV MANSON (1094) - Riverton (11083) | 2028-10-11 | 2026-07-27 | True |  |  | Signed; security posted | Signed -> Signed; security posted
26INR0034 | Bracero Pecan Storage | Bracero Pecan Storage LLC | Reeves | Battery storage | 238.21 | 60716 SARAGOSA 138kV | 2027-07-01 | 2024-06-27 | True |  |  | Signed; security posted
24INR0645 | COYOTE SPRINGS AGR1 | HEN INFRASTRUCTURE, LLC 1 | Reeves | Oil | 9.95 | Station Name: COYOTSPR Load Name: COYOTE_1 Bus#: 38113 Voltage: 138 kV DAC: COYOTSPR_LD8 COYOTSPR/COYOTE_1/38113/COYOTSPR_LD8 | 2026-06-23 | 2023-10-16 | True |  |  | Signed; security posted
23INR0116 | Cantaloupe Solar | Saragosa Del Sol Energy, LLC | Reeves | Solar | 307 | 60716 Saragosa 138kV | 2028-07-01 | 2024-04-23 | True |  |  | Signed; security posted
30INR0158 | Capshaw Solar | NextEra Energy Resources Interconnection Holding, LLC | Reeves | Solar | 450 | POIB: Tapping Drylake_5 (#18723) – TNFaulkner3 (#38125) 345 kV | 2030-07-01 |  |  |  |  | In study
26INR0685 | Exergy Energy West Texas Natural Gas Reciprocating Power I | August Partners LLC | Reeves | Gas engines | 400 | 38095 TNJACKRBT1 138kV | 2027-05-01 |  |  |  |  | In study
29INR0194 | Glass Mountain Wind 1 | Glass Mountain Wind, LLC | Reeves | Wind | 511.5 | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | 2028-12-31 |  |  |  |  | In study
28INR0468 | Glass Mountain Wind 2 | Glass Mountain Wind, LLC | Reeves | Wind | 519.2 | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | 2028-12-31 |  |  |  |  | In study
27INR0572 | Kilby1 Part 1 Small Block Simple Cycle | Energy Forge One LLC | Reeves | Gas turbine | 371 | #60404 Solstice Substation 345 kV | 2027-11-04 |  |  |  |  | In study
28INR0457 | Kilby1 Part 2 Tier1 BESS | Energy Forge One LLC | Reeves | Battery storage | 330 | #60404 Solstice Substation 345 kV | 2028-01-21 |  |  |  |  | In study
28INR0459 | Kilby1 Part 4 Large Block Simple Cycle | Energy Forge One LLC | Reeves | Gas turbine | 950 | #60404 Solstice Substation 345 kV | 2028-04-20 |  |  |  |  | In study
29INR0199 | Kilby1 Part 6 Large Block Combined Cycle | Energy Forge One LLC | Reeves | Gas turbine | 1056 | #60404 Solstice Substation 345 kV | 2029-07-19 |  |  |  |  | In study
26INR0396 | Kodiak AGR1 | Hunt Energy Network, LLC | Reeves | Oil | 132 | 38113 TNCOYOTSPG1 | 2029-06-08 |  |  |  |  | In study
26INR0385 | Nanulak BESS | Nanulak BESS, L.L.C. | Reeves | Battery storage | 181.54 | 38113 TNCOYOTSPG1 138kV | 2027-06-30 | 2025-11-19 |  |  |  | Signed
28INR0219 | Neptune Gas Generation Plant | BPX Production Company | Reeves | Gas engines | 113.77 | 11200 Longpast_T8 138kv | 2028-03-15 |  |  |  |  | In study
24INR0646 | SADDLEBACK AGR1 | HEN INFRASTRUCTURE, LLC 1 | Reeves | Oil | 9.95 | SADLBACK/SADLBK_1/38058/SADLBACK_LD8 | 2026-06-23 | 2023-10-16 | True |  |  | Signed; security posted
27INR0297 | Tolivar Power Plant (TEF- Due Diligence) | Pecos Power Plant, LLC | Reeves | Gas engines | 224.5 | Tap 138 KV 38045 IH20-38043 COWPEN | 2027-06-11 | 2025-07-01 | True |  |  | Signed; security posted
28INR0413 | Tolivar Power Plant Phase 2 | Pecos Power Plant, LLC | Reeves | Gas engines | 224.5 | Tap 138 KV 38055 Saltdraw-38043 COWPEN | 2027-09-29 | 2026-04-14 | True |  |  | Signed; security posted
29INR0360 | Trumpet Solar | NextEra Energy Resources Interconnection Holdings LLC | Reeves | Solar | 533 | tap 345kV 18723 Drylake_5 – 38125 TNFaulkner3 | 2029-07-01 |  |  |  |  | In study
29INR0354 | Wolf Bone North Energy Center | NRG Wolf Bone Energy Center LLC | Reeves | Gas combined cycle | 1174.4 | TNMP Cowpen 345kV Substation POIB 38044 (4 mile transmission line will connect POI at customer substation to POIB in the Cowpen substation) | 2031-02-28 |  |  |  |  | In study | new
23INR0047 | Charger Solar | AP Solar 4, LLC | Refugio | Solar | 397.15 | tap 345kV 8249 Angstrom – 5915 STP | 2026-09-18 | 2021-06-05 | True | 2026-06-30 | 2026-07-17 | Approved for synchronization
28INR0175 | Mobee Springs BESS | Mobee Springs, LLC | Refugio | Battery storage | 100.61 | #8805 BONIVIEW2A 69kV | 2028-03-31 |  |  |  |  | In study
26INR0155 | Ross Solar | S&S Renewables, LLC | Refugio | Solar | 1025.57 | tap 345kV 8249 Angstrom – 8676 Static | 2027-07-31 | 2024-06-27 |  |  |  | Signed
26INR0156 | Ross Storage | S&S Renewables, LLC | Refugio | Battery storage | 510.99 | tap the 345 kV Angstrom (#8249) – Static (#8676) line; AEP | 2027-07-31 | 2024-06-27 |  |  |  | Signed
29INR0341 | Pampa Natural Gas | IP Meitner Gas | Roberts | Gas engines | 250.7 | CTT Ghost Town (#79008) | 2030-01-01 |  |  |  |  | In study
24INR0135 | BRP Mekong BESS | BRP Mekong BESS LLC | Robertson | Battery storage | 409.88 | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | 2027-12-01 |  |  |  |  | In study
22INR0504 | Barton Branch IA | Barton Branch IA LLC | Robertson | Battery storage | 203.62 | Tap 345kV 3400 Twin Oak - 39950 TNP One | 2026-10-01 | 2025-06-18 | True |  |  | Signed; security posted
23INR0421 | Bee Branch IA | Bee Branch IA LLCBee Branch IA LLC | Robertson | Battery storage | 203.75 | Tap TNP ONE 39950 and Twin Oak 3400 | 2027-06-01 | 2026-03-13 | True |  |  | Signed; security posted
29INR0017 | Big Rooter East Solar | Big Rooter East, LLC | Robertson | Solar | 554.7 | 39950 TNP One Plant 345 kV | 2029-05-31 | 2025-06-01 |  |  |  | Signed
29INR0018 | Big Rooter East Storage | Big Rooter East, LLC | Robertson | Battery storage | 201.03 | 39950 TNP One Plant 345 kV | 2029-12-31 | 2025-06-01 |  |  |  | Signed
26INR0431 | Big Rooter West Solar | Big Rooter West, LLC | Robertson | Solar | 403.2 | 39950# TNTNP_ONE_3 345 KV | 2028-05-31 | 2025-02-18 |  |  |  | Signed
26INR0432 | Big Rooter West Storage | Big Rooter West, LLC | Robertson | Battery storage | 201.08 | 39950# TNTNP_ONE_3 345 KV | 2028-12-01 |  |  |  |  | In study
25INR0331 | Buffalo Meadow Solar | Buffalo Meadow Energy Center, LLC | Robertson | Solar | 251.27 | Tap Jack Creek (975) - Twin Oak (3400) 345kV line | 2028-09-30 |  |  |  |  | In study
25INR0288 | Buffalo Prairie Storage | Buffalo Meadow Energy Center, LLC | Robertson | Battery storage | 308.03 | Tap 345kV 975 Jack Creek - 3400 Twin Oak | 2028-09-30 |  |  |  |  | In study
27INR0418 | Pioneer Path Energy Storage 1 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0423 | Pioneer Path Energy Storage 2 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0424 | Pioneer Path Energy Storage 3 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0425 | Pioneer Path Energy Storage 4 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0426 | Prairie Horizon Energy Storage 1 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0427 | Prairie Horizon Energy Storage 2 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0428 | Prairie Horizon Energy Storage 3 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
27INR0429 | Prairie Horizon Energy Storage 4 | Tempus Power management LLC | Robertson | Battery storage | 102.14 | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | 2027-12-01 |  |  |  |  | In study
25INR0497 | Stegall Solar | BT Martin Solar, LLC | Robertson | Solar | 81.57 | Elliott (Bus #53) to Franklin (Bus #57) 69kV Transmission Line | 2027-05-30 |  |  |  |  | In study
25INR0498 | Stegall Storage | BT Martin Solar, LLC | Robertson | Battery storage | 50.47 | Tap connection to a new switching station on the Elliott (Bus #53) - Franklin (Bus #57) 69 kV Transmission Line | 2027-05-30 |  |  |  |  | In study
22INR0503 | Tidwell Prairie II Batt | Tidwell Prairie IIA LLC | Robertson | Battery storage | 203.62 | Tap 345kV 3400 Twin Oak - 39950 TNP One | 2026-12-03 | 2025-01-13 | True |  |  | Signed; security posted
26INR0418 | TE Smith Storage 2 | Smith II Battery Storage, LLC | Rockwall | Battery storage | 125.32 | 2478 Royse 345kV | 2029-02-07 |  |  |  |  | In study
30INR0088 | Mistflower Energy Center Solar | Mistflower Energy Center LLC | Runnels | Solar | 401.62 | Tap 345kV 60072 ODYSSEUS7A– 60040 BLF_CRK7A | 2030-06-01 |  |  |  |  | In study
30INR0089 | Mistflower Energy Center Storage | Mistflower Energy Center LLC | Runnels | Battery storage | 312.85 | Tap 345kV 60072 Odysseus – 60040 Bluff Creek | 2030-06-01 |  |  |  |  | In study
19INR0035 | Norton Solar | TAI Norton Solar, LLC | Runnels | Solar | 128.48 | 60451 Garnet 138kV | 2025-11-24 | 2019-06-20 | True | 2025-07-24 | 2025-08-06 | Approved for synchronization
24INR0485 | Rutile BESS | Rutile BESS, LLC | Runnels | Battery storage | 100.65 | Tap 138kV 6340 BALLINGER - 60399 WEISS | 2028-03-31 | 2025-07-17 | True |  |  | Signed; security posted
29INR0210 | Sawtooth Solar | Sawtooth Solar, LLC | Runnels | Solar | 201.36 | Tap to the 345kV Odysseus (Bus#60072) to Bluff Creek (Bus #60040) line | 2030-08-01 |  |  |  |  | In study
28INR0198 | Winters Glow Solar | Winters Glow Solar, LLC | Runnels | Solar | 301.6 | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | 2029-04-17 |  |  |  |  | In study
28INR0199 | Winters Glow Storage | Winters Glow Storage, LLC | Runnels | Battery storage | 155.2 | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | 2029-04-17 |  |  |  |  | In study
30INR0076 | Zuma Solar | Zuma Solar, LLC | Runnels | Solar | 201.37 | Tap 345kV 11263 Fisk Switch - 11406 Central Bluff Switch | 2030-09-09 |  |  |  |  | In study
22INR0332 | Brantley Branch Batt | Brantley Branch LLC | Rusk | Battery storage | 302.35 | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | 2029-02-01 |  |  |  |  | In study
23INR0286 | Dry Creek Solar I | OAK HILL SOLAR LLC | Rusk | Solar | 201.06 | tap 345kV 3100 Martin Lake - 3105 Elkton (Dorsett 345kV Switching Station) | 2026-01-31 | 2023-11-02 | True | 2025-05-08 | 2025-05-19 | Approved for synchronization
27INR0488 | Dry Creek Solar II | Oak Hill Solar II LLC | Rusk | Solar | 201.28 | Dorsett 345 kV Switching Station(tap 345 kV 3100 Martin Lake - 3105 Elkton) | 2028-02-01 |  |  |  |  | In study
25INR0591 | Zeus Rusk BESS | Rusk BESS, LLC | Rusk | Battery storage | 208.8 | Tap 345kV 3109 Stryker to 3100 Martin Lake | 2027-09-01 |  |  |  |  | In study
25INR0590 | Zeus Rusk Solar | Rusk Solar, LLC | Rusk | Solar | 26.8 | Tap 345kV 3109 Stryker to 3100 Martin Lake | 2027-09-01 |  |  |  |  | In study
29INR0207 | Alila BESS II | Electra Energy Project, LLC | San Patricio | Battery storage | 205.71 | 8249 Angstrom 345kV | 2029-01-25 |  |  |  |  | In study
28INR0223 | Bayou Creek Solar | Bayou Creek Solar LLC | San Patricio | Solar | 256.9 | 8606 Goddard 345kV | 2028-09-25 | 2026-06-02 | True |  |  | Signed; security posted
28INR0496 | Blue Kite | RWE Clean Energy Development, LLC | San Patricio | Gas turbine | 370.08 | <Bus#8956> <WHITEPOINT> <345KV> | 2030-08-29 |  |  |  |  | In study
22INR0443 | Bowstring BESS | Longbow Energy Storage, LLC | San Patricio | Battery storage | 155 | 138kV 8961 WHITEPT4A - 8418 RINCON4A | 2028-09-18 | 2025-09-09 | True |  |  | Signed; security posted
26INR0599 | Coda BESS | Coda BESS, LLC | San Patricio | Battery storage | 202 | (#80258) Mayo 138kV | 2028-07-31 |  |  |  |  | In study
26INR0428 | Diamond Cowboy Storage | Diamond B Storage, LLC | San Patricio | Battery storage | 103.5 | Tap 345kV 8249 Angstrom - 8624 Grissom | 2028-10-16 | 2026-05-26 | True |  |  | Signed; security posted
29INR0068 | Gregory Power Development SLF | Gregory Power Partners LLC | San Patricio | Gas combined cycle | 469.9 | 8580 Resnick 138kV | 2028-12-19 | 2026-07-01 |  |  |  | Signed | In study -> Signed
27INR0492 | Gulf Gateway Solar One | Gulf Gateway Solar, LLC | San Patricio | Solar | 301.4 | Tap 345 kV 8249 Angstrom - 8624 Grissom | 2029-12-01 |  |  |  |  | In study
27INR0556 | Gulf Gateway Storage One | Gulf Gateway Storage, LLC | San Patricio | Battery storage | 301.4 | Tap 345 kV 8249 Angstrom - 8624 Grissom | 2029-12-01 |  |  |  |  | In study
30INR0004 | Hecate Energy Arkansas Wind | Hecate Energy Gulf Wind LLC | San Patricio | Wind | 1029.39 | 8659 Naismith 345kV | 2030-06-01 |  |  |  |  | In study
28INR0305 | Iron Cowboy Solar | Vaquero II Solar LLC | San Patricio | Solar | 144.59 | Bus #8920 Haisley 4A 138 kV | 2029-07-10 | 2026-08-10 | True |  |  | Signed; security posted | Signed -> Signed; security posted
28INR0306 | Iron Cowboy Storage | Vaquero II Storage LLC | San Patricio | Battery storage | 63.27 | Bus #8920 Haisley 4A 138 kV | 2029-07-10 | 2026-08-10 | True |  |  | Signed; security posted | Signed -> Signed; security posted
23INR0180 | Jackalope Solar | Peacock Energy Project, LLC | San Patricio | Solar | 155.68 | 8173 Gibbs 138kV | 2026-02-05 | 2021-09-30 | True | 2024-07-30 | 2024-09-19 | Approved for synchronization
22INR0392 | Kalina Solar | Aurora Solar LLC | San Patricio | Solar | 120 | 8606 Goddard 345kV | 2029-05-31 |  |  |  |  | In study
29INR0106 | Kalina Storage | Aurora Solar LLC | San Patricio | Battery storage | 104.56 | 8606 GODDARD 345kV | 2029-12-01 |  |  |  |  | In study
26INR0306 | Nautilus Heavy Storage | Nautilus Heavy Storage, LLC | San Patricio | Battery storage | 256.24 | 8422 Dupont 138kV | 2030-01-30 |  |  |  |  | In study
27INR0227 | PALO VERDE BESS | RWE Clean Energy Development, LLC | San Patricio | Battery storage | 150 | Tap 345kV 8624 Grissom – 8455 Lon C Hill | 2029-07-22 |  |  |  |  | In study
27INR0132 | Palo Verde Wind | RWE Clean Energy Development, LLC | San Patricio | Wind | 297.5 | Tap 345kV 8624 Grissom – 8455 Lon C Hill | 2029-07-22 | 2025-12-19 |  |  |  | Signed
28INR0484 | Pathfinder Energy Storage, LLC | Pathfinder Energy Storage, LLC | San Patricio | Battery storage | 201.16 | 8437 Rincon 138kV | 2029-12-28 |  |  |  |  | In study
27INR0524 | Portland Storage SLF | Convergent Energy Solutions LLC | San Patricio | Battery storage | 0 | 8566 HOT IRON 4A 138 kV 8569 HOT IRON 4B 138 kV (2) POIs will be used for this project because there are (2) 138 kV lines supplying the ArcelorMittal plant. Project physical connection will be 13.8 kV bus at ArcelorMittal. | 2028-01-03 |  |  |  |  | In study
29INR0227 | San Patricio Energy Center BESS | Ferrovial Energy US 1 | San Patricio | Battery storage | 300.84 | 8606 Goddard 345kV | 2029-03-31 |  |  |  |  | In study
25INR0081 | SanPat Solar I | Padre Solar LLC | San Patricio | Solar | 308.88 | Tap 345kV 8249 Angstrom – 8659 Naismith | 2027-07-08 | 2023-10-18 | True |  |  | Signed; security posted
25INR0052 | SanPat Solar II | CGRP 04, LLC | San Patricio | Solar | 256.23 | Tap 345kV 8249 Angstrom – 8659 Naismith | 2027-07-22 | 2023-10-18 | True |  |  | Signed; security posted
28INR0181 | Sunburst BESS | Indigo Solar, LLC | San Patricio | Battery storage | 256.3 | KATOEN (Bus#8579) | 2029-03-16 |  |  |  |  | In study
28INR0179 | Sunburst Solar | Indigo Solar, LLC | San Patricio | Solar | 301.6 | KATOEN (Bus#8579) | 2029-03-16 |  |  |  |  | In study
26INR0211 | Titus Low Carbon Ventures Solar 1 | Vaquero Solar, LLC | San Patricio | Solar | 338.04 | Tap 345kV 8249 Angstrom - 8624 Grissom | 2028-10-16 | 2026-05-26 |  |  |  | Signed
27INR0364 | Cashel BESS | TIPPSOL LLC | Schleicher | Battery storage | 150.44 | 6500 Live Oak AEP 138kV | 2028-03-15 |  |  |  |  | In study
26INR0290 | Cold Creek Solar 2 | Cold Creek Solar and Storage LLC | Schleicher | Solar | 431.87 | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | 2028-05-28 | 2025-04-23 |  |  |  | Signed
26INR0291 | Cold Creek Storage 2 | Cold Creek Solar and Storage LLC | Schleicher | Battery storage | 171.75 | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | 2028-05-28 | 2025-04-23 |  |  |  | Signed
27INR0231 | Easy Battery Energy Storage Center | Easy Wind Energy Center, LLC | Schleicher | Battery storage | 200 | Tap 345 kV 76003 Big Hill to 76005 Schneeman Draw | 2029-06-15 |  |  |  |  | In study
27INR0246 | Easy Wind Energy Center | Easy Wind Energy Center, LLC | Schleicher | Wind | 241.13 | Tap 345kV #76003 Big Hill - #76005 Schneeman Draw circuit #1 | 2029-06-15 |  |  |  |  | In study
28INR0280 | Live Oak Wind II | ENGIE IR Holdings LLC | Schleicher | Wind | 302.63 | #76003 Big Hill 345kV | 2028-09-29 |  |  |  |  | In study
26INR0159 | Proving Ground BESS | Lantana Solar LLC | Schleicher | Battery storage | 51.4 | Tap 138kV 6500 Live Oak - 6490 Santiago | 2028-06-30 |  |  |  |  | In study
26INR0150 | Proving Ground Solar | Lantana Solar LLC | Schleicher | Solar | 82.1 | Tap 138 kV Live Oak (6500) - Santiago (6490) | 2028-06-30 |  |  |  |  | In study
22INR0239 | Rockefeller Storage | Mittel Rockefeller Storage LLC | Schleicher | Battery storage | 206.8 | 76003 Big Hill 345kV | 2027-06-01 | 2024-09-23 | True |  |  | Signed; security posted
27INR0261 | Tipperary Solar | Tippsol | Schleicher | Solar | 60.16 | 6498 Live Oak AEP 69kV | 2028-03-15 |  |  |  |  | In study
21INR0532 | Brazos Wind Repower | BRAZOS WIND VENTURES, LLC | Scurry | Wind | 22.4 | 1064 Sun 138kV | 2025-11-14 |  | True | 2023-04-25 | 2023-07-01 | Approved for synchronization
27INR0193 | Cedar Draw BESS | Cedar Draw Solar LLC | Scurry | Battery storage | 225.7 | 60011 Nebula7A 345kV | 2027-12-31 |  |  |  |  | In study
27INR0192 | Cedar Draw Solar | Cedar Draw Solar LLC | Scurry | Solar | 451.4 | 60011 Nebula7A 345kV | 2027-12-31 |  |  |  |  | In study
17INR0027b | Coyote Wind | Coyote Wind | Scurry | Wind | 242.6 | 11305 Dermott 345kV | 2026-08-28 | 2016-08-09 | True | 2020-08-24 | 2020-11-25 | Approved for synchronization
28INR0202 | Fluvanna Max BESS SLF | Fluvanna Max Solar LLC | Scurry | Battery storage | 51.8 | 11305 DERMOTT 345 kV | 2029-09-14 |  |  |  |  | In study
29INR0077 | Fluvanna Max Solar SLF | Fluvanna Max Solar LLC | Scurry | Solar | 152.7 | 11305 DERMOTT 345 kV | 2029-09-14 |  |  |  |  | In study
27INR0624 | Helion BESS | Helion BESS | Scurry | Battery storage | 100 | 59912 GALVANI 345 | 2027-09-16 |  |  |  |  | In study
27INR0623 | Helion Solar | Helion Solar LLC | Scurry | Solar | 100 | 59912 GALVANI 345 | 2027-10-22 |  |  |  |  | In study
25INR0287 | Hide Town Energy Storage | Hide Town Energy Storage LLC | Scurry | Battery storage | 102.76 | 18555 Union Switch 138 kV | 2029-10-11 |  |  |  |  | In study
25INR0197 | Inadale BESS | Inadale BESS, LLC | Scurry | Battery storage | 287.16 | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | 2029-03-02 |  |  |  |  | In study
25INR0196 | Inadale Solar | Inadale Solar, LLC | Scurry | Solar | 281.03 | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | 2029-03-02 |  |  |  |  | In study
25INR0747 | Knapp BESS | Knapp ESS Assets, LLC | Scurry | Battery storage | 9.95 | Station Name: KNAPP Station Code: KNAPP Station Bus Number: #1310 Station Transmission Voltage: 138 kV Load/Load Transformer Name: LDLXFMR2 Distribution Voltage: 12.47 kV | 2026-10-24 | 2025-03-13 | True | 2025-11-05 | 2025-11-24 | Approved for synchronization
25INR0400 | Maldives Solar | Maldives Solar LLC | Scurry | Solar | 181.3 | Galvani 345 kV station (Bus #59912) | 2028-09-25 | 2023-12-01 | True |  |  | Signed; security posted
24INR0519 | Roost Energy Storage | Bluff Creek Energy Storage LLC | Scurry | Battery storage | 102.36 | the Knapp Sub (bus# 1310) – Union Switch (bus# 18555) | 2028-09-30 |  |  |  |  | In study
28INR0486 | Spectra Solar | SE DC Devco | Scurry | Solar | 1200 | 59912 Galvani 345KV | 2028-11-16 | 2025-12-29 | True |  |  | Signed; security posted
27INR0535 | Zeus Scurry BESS | Zeus Scurry BESS | Scurry | Battery storage | 1043.07 | MHOS 345 kV Substation (#59911) | 2028-10-01 |  |  |  |  | In study
27INR0529 | Zeus Scurry Solar | Scurry Solar, LLC | Scurry | Solar | 503.54 | MHOS 345 kV Substation (#59911) | 2028-10-01 |  |  |  |  | In study
28INR0151 | Chimney Creek Solar | Chimney Creek Energy, LLC | Shackelford | Solar | 203.88 | Tap 345 kV 68000 West Shackelford – 60515 Clear Crossing Ckt 1 | 2030-05-30 |  |  |  |  | In study
26INR0500 | Shackleford BESS | Shackelford County BESS LLC | Shackelford | Battery storage | 206.5 | 1442 CFRSW 345kV | 2028-09-23 |  |  |  |  | In study
27INR0354 | Cebocell BESS | Cebocell, LLC | Smith | Battery storage | 200.87 | 3137 BlackFork 138 KV | 2028-10-31 |  |  |  |  | In study
27INR0497 | Black Mountain Somervell Gas Combined | Fort Worth Power Core LLC | Somervell | Gas combined cycle | 495.3 | Dinosaur Switch (#15208) | 2029-09-28 |  |  |  |  | In study
21INR0520 | Yellow Viking Solar | Yellow Viking Development One, LLC | Somervell | Solar | 171.13 | Tap 345kV 1900 Comanche Peak - 11886 Timberview Switch | 2027-07-13 | 2022-10-25 | True |  |  | Signed; security posted
23INR0455 | Bessie Storage | Bessie Energy Storage, LLC | Starr | Battery storage | 210.8 | Charly Egner Substation Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | 2029-09-28 |  |  |  |  | In study
23INR0354 | Bordertown BESS | Bordertown BESS LLC | Starr | Battery storage | 100 | 8796 Roma 138kV | 2028-12-01 | 2022-10-12 | True |  |  | Signed; security posted
28INR0037 | Bullring Wind 1 | Halcon Wind, LLC | Starr | Wind | 303.5 | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | 2028-06-30 | 2025-11-03 | True |  |  | Signed; security posted
28INR0038 | Bullring Wind 2 | Halcon Wind, LLC | Starr | Wind | 303.8 | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | 2028-06-30 | 2025-11-03 | True |  |  | Signed; security posted
28INR0039 | Bullring Wind 3 | Halcon Wind, LLC | Starr | Wind | 190.4 | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | 2028-06-30 | 2025-11-03 | True |  |  | Signed; security posted
20INR0162 | Diamondback solar | Diamondback Solar, LLC | Starr | Solar | 200.5 | 80355 Del Sol 345kV | 2028-04-29 | 2024-06-14 | True |  |  | Signed; security posted
27INR0222 | Fierce River BESS | Rio Grande Solar LLC | Starr | Battery storage | 284.49 | Tapping the 345 kV Line from Del Sol (Bus# 80355) to Frontera (Bus# 80119) ckt 1 | 2029-02-22 |  |  |  |  | In study
25INR0241 | Halcon Storage | TX BESS A LLC | Starr | Battery storage | 132.65 | Tap 138kV 8957 Central Lopeno - 80106 Falcon Dam | 2028-05-15 |  |  |  |  | In study
28INR0127 | Half Moon Solar | NextEra Energy Interconnection Holdings, LLC | Starr | Solar | 512.5 | #80231 Pronto 345kV | 2029-07-01 | 2025-09-08 | True |  |  | Signed; security posted
29INR0223 | Mandolin Solar II SLF | Mandolin Energy Center II, LLC | Starr | Solar | 304.4 | Tap 345kV 80355 Del Sol - 80227 Rapido | 2029-06-15 |  |  |  |  | In study
29INR0224 | Mandolin Solar III SLF | Mandolin Energy Center I, LLC | Starr | Solar | 250 | Tap 345kV 80355 Del Sol - 80227 Rapido | 2029-06-15 |  |  |  |  | In study | new
26INR0527 | Mandolin Solar SLF | Mandolin Energy Center I, LLC | Starr | Solar | 300 | Tap 345kV 80355 Del Sol - 80227 Rapido | 2029-06-15 |  |  |  |  | In study
26INR0528 | Mandolin Storage SLF | Mandolin Energy Center I, LLC | Starr | Battery storage | 0 | Tap 345kV 80355 Del Sol - 80227 Rapido | 2029-06-15 |  |  |  |  | In study
16INR0081 | Mesteno Wind | Mesteno Windpower, LLC | Starr | Wind | 201.6 | 80355 Del Sol 345kV | 2027-03-01 | 2018-04-25 | True | 2019-11-26 | 2019-12-12 | Approved for synchronization
24INR0445 | PSE Flores TX Storage | PureSky Development Inc | Starr | Battery storage | 200 | TAP 138KV 8793 RIO GRANDE CITY - 8798 LAGRULLA | 2028-06-30 |  |  |  |  | In study
24INR0446 | PSE Gongora Hill TX Storage | PureSky Development Inc | Starr | Battery storage | 200 | Tap 138kV 8796 Roma – 7870 Escobares | 2028-06-30 |  |  |  |  | In study
28INR0043 | Sendero Solar | ACE DevCo NC, LLC | Starr | Solar | 502.69 | Tap 345kV 80079 Cruce - 80355 Del Sol | 2029-05-15 |  |  |  |  | In study
20INR0216 | Starr Solar Ranch | Starr Solar Ranch 1 LLC | Starr | Solar | 136.73 | 8795 Roma 138kV | 2025-08-14 | 2020-10-01 | True | 2024-10-09 | 2024-10-30 | Approved for synchronization
25INR0379 | Starr Storage | Falcon Lake Storage, LLC | Starr | Battery storage | 0 | 8795 Roma 138kV | 2028-03-29 |  |  |  |  | In study
26INR0446 | Sword BESS | Hidalgo Solar LLC | Starr | Battery storage | 40.1 | Tap 138 kV 8394 Liston - 8392 Bates | 2029-02-22 |  |  |  |  | In study
26INR0445 | Sword Solar | Hidalgo Solar LLC | Starr | Solar | 137.18 | Tap 138 kV 8394 Liston - 8392 Bates | 2029-02-22 |  |  |  |  | In study
26INR0600 | Crocus Solar | Crocus Solar, LLC | Stephens | Solar | 102 | Tap 138 kV Gunsolas Creek Sub (1660) – Breckenridge Tap (1613) | 2028-07-01 | 2026-08-04 |  |  |  | Signed
26INR0601 | Crocus Storage | Crocus Solar, LLC | Stephens | Battery storage | 51 | Tap 138 kV Gunsolas Creek Sub (1660) – Breckenridge Tap (1613) | 2028-07-01 | 2026-08-04 |  |  |  | Signed
21INR0240 | La Casa Wind | LA CASA WIND, LLC | Stephens | Wind | 148.4 | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | 2026-11-30 | 2023-09-07 | True | 2025-10-31 | 2025-11-14 | Approved for synchronization
27INR0076 | Bob Creek Wind | NextEra Energy Interconnection Holdings, LLC | Sterling | Wind | 239.47 | 59902 Sand Bluff 345kV | 2028-07-01 | 2025-06-06 | True |  |  | Signed; security posted
17INR0054 | Capricorn I & III repower | Nextera | Sterling | Wind | 32 | 180757 Capricorn Ridge 3 138kV | 2026-06-30 | 2006-11-14 |  |  | 2021-03-04 | Approved for synchronization
26INR0589 | Goat Mountain BESS | Clearway Energy Group LLC | Sterling | Battery storage | 201.1 | 76030-Gasconades Creek 345 kV | 2028-06-01 |  |  |  |  | In study
26INR0611 | Goat Mountain BESS 2 | Clearway Energy Group LLC | Sterling | Battery storage | 100.7 | 76030-Gasconades Creek 345 kV | 2028-06-01 |  |  |  |  | In study
27INR0367 | Goat Mountain Wind-Repower | Goat Wind LLC | Sterling | Wind | 303.2 | 76030 Gasconades Creek 345kV | 2027-03-01 | 2026-02-20 | True |  |  | Signed; security posted
29INR0185 | Roan Solar Phase 1 | Roan Solar, LLC | Sterling | Solar | 205.9 | Divide (#76090) to Sand Bluff Wind Farm (#59902) 345 kV | 2029-04-30 |  |  |  |  | In study
29INR0187 | Roan Solar Phase 2 | Roan Solar, LLC | Sterling | Solar | 205.9 | Divide (#76090) to Sand Bluff Wind Farm (#59902) 345 kV | 2029-12-15 |  |  |  |  | In study
26INR0269 | Moccasin Solar | Swenson Solar LLC | Stonewall | Solar | 603.59 | Tapping the 345 kV Line from Kirchhoff (Bus# 60707) to Clear Crossing (Bus# 60515) | 2027-07-06 | 2024-09-04 | True |  |  | Signed; security posted
28INR0253 | Stonewall BESS | Stonewall ESS, LLC | Stonewall | Battery storage | 135 | tap 138kV 6150 SPUR4A - 6158 ASPM4A | 2028-12-29 |  |  |  |  | In study
27INR0242 | Stonewall Solar | Stonewall PV, LLC | Stonewall | Solar | 60.2 | Tap 69kV #755 BEPC Aspermont - #6156 AEP Aspermont | 2029-01-15 |  |  |  |  | In study
27INR0236 | Atticus Energy Storage | Atticus Energy Storage | Sutton | Battery storage | 102.98 | Tap 69 KV 6570 Bond Road - 6513 Sonora | 2030-01-26 |  |  |  |  | In study
28INR0148 | Sonora High Noon BESS | Sonora High Noon, LLC | Sutton | Battery storage | 204.08 | 60412 CARVER 138kV | 2028-07-01 |  |  |  |  | In study
29INR0032 | Commodus 2 Solar | IP Blackwell II, LLC | Swisher | Solar | 502.1 | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | 2029-07-30 |  |  |  |  | In study
29INR0033 | Commodus 2 Wind | IP Blackwell II, LLC | Swisher | Wind | 641.48 | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | 2029-07-30 |  |  |  |  | In study
22INR0402 | Frye Storage | Hecate Energy Frye Storage LLC | Swisher | Battery storage | 503.85 | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | 2028-12-01 |  |  |  |  | In study
27INR0625 | Hornet Energy Storage SLF | Hornet Energy Storage LLC | Swisher | Battery storage | 0 | 23901 OZARKTRAIL_5 345kV | 2029-09-30 |  |  |  |  | In study
25INR0282 | Hornet Solar II SLF | Hornet Solar II LLC | Swisher | Solar | 201.49 | Ozark Trail Switch 345kV substation (Bus #23901) | 2028-07-31 | 2024-08-21 | True |  |  | Signed; security posted
25INR0283 | Hornet Storage II SLF | Hornet Storage II LLC | Swisher | Battery storage | 0 | Ozark Trail Switch 345kV substation (Bus # 23901) | 2028-07-31 | 2024-08-21 | True |  |  | Signed; security posted
24INR0003 | Stem Solar | Innovative Solar 134, LLC | Swisher | Solar | 200 | tap 345kV 23914 Tule Canyon - 23912 Ogallala | 2025-08-26 |  |  |  |  | In study
26INR0487 | Anglin BESS | Fort Worth BESS LLC | Tarrant | Battery storage | 206 | 1883 EVRSW 138kV | 2028-09-30 |  |  |  |  | In study
28INR0116 | Salazar BESS | Salazar Energy Storage LLC | Tarrant | Battery storage | 127.82 | 2068 Rosen Heights 138kV | 2028-07-11 |  |  |  |  | In study
21INR0492 | Stockyard Grid Batt | Stockyard Grid, LLC | Tarrant | Battery storage | 150.6 | 2082 Hicks 138kV | 2028-12-14 | 2022-10-26 | True |  |  | Signed; security posted
24INR0763 | Team Ranch Storage | BAF Storage, LLC | Tarrant | Battery storage | 307.2 | 1869 Benbrook Switch 345kV | 2027-03-01 |  |  |  |  | In study
26INR0622 | Buffalo Gap 1 Wind Repower | Buffalo Gap Wind Farm, LLC | Taylor | Wind | 120.23 | 6216 Bluff Creek Substation 138kV | 2027-02-01 | 2005-02-28 | True |  |  | Signed; security posted
26INR0626 | Buffalo Gap 3 Wind Repower | Buffalo Gap Wind Farm 3, LLC | Taylor | Wind | 168.45 | 6216 Bluff_Creek 138kV | 2027-02-01 | 2005-02-28 | True |  |  | Signed; security posted
28INR0156 | Chimney Rock BESS | Taylor ESS, LLC | Taylor | Battery storage | 156 | Tap 138kV 76317 MOORE - 76318 BUTMAN | 2028-04-10 |  |  |  |  | In study
27INR0503 | Dog Star Solar I | Dog Star Solar LLC | Taylor | Solar | 499.01 | Bluff Creek (Bus #60040) to Mulberry Creek (Bus #6235) 345 kV | 2027-12-31 |  |  |  |  | In study
27INR0504 | Dog Star Solar II | Dog Star Solar LLC | Taylor | Solar | 499.01 | Bluff Creek (Bus #60040) to Mulberry Creek (Bus #6235) 345 kV | 2027-12-31 |  |  |  |  | In study
24INR0341 | Forts Trail BESS | JC Central Bluff, LLC | Taylor | Battery storage | 208.82 | 11406 Central Bluff Switch 345kV | 2029-03-02 |  |  |  |  | In study
24INR0488 | Forts Trail BESS 2 | JC Central Bluff, LLC | Taylor | Battery storage | 205.54 | 11406 Central Bluff Switch 345 kV | 2029-03-02 |  |  |  |  | In study
24INR0308 | Forts Trail Solar | JC Central Bluff, LLC | Taylor | Solar | 200.81 | 11406 Central Bluff Switch 345kV | 2029-03-02 |  |  |  |  | In study
17INR0053 | HHGT repower Horse13+CallD | Nextera | Taylor | Wind | 44 | 7046 Kendal 345kV | 2027-03-31 | 2009-06-26 |  |  | 2021-09-10 | Approved for synchronization
17INR0052 | Horse13 CallD repower | Nextera | Taylor | Wind | 44 | 6216 Bluff Creek 138kV | 2027-03-31 | 2019-05-22 | True |  | 2021-03-16 | Approved for synchronization
26INR0700 | Key City Battery Storage SLF | Key City Battery Storage LLC | Taylor | Battery storage | 1.9 | 6235 Abilene Mulberry Creek 345 | 2029-03-31 |  |  |  |  | In study
26INR0701 | Key City Solar SLF | Key City Solar LLC | Taylor | Solar | 989.1 | 6235 Abilene Mulberry Creek 345 | 2029-03-31 |  |  |  |  | In study
28INR0254 | Summerhill BESS | Taylor ESS, LLC | Taylor | Battery storage | 143 | Tap 138kv 6228 ABNTHWST4A - 6288 MULBERRY4D | 2028-12-15 |  |  |  |  | In study
26INR0618 | Taylor County Paul Storage | DM-TCP, LLC | Taylor | Battery storage | 204.9 | 6260 Abilene South Substation 138kV | 2029-12-30 |  |  |  |  | In study
25INR0558 | Ayass BESS | Harvick BESS, LLC | Throckmorton | Battery storage | 51.28 | 6206 Bush Knob 69kV | 2028-12-30 |  |  |  |  | In study
21INR0263 | Monarch Creek Wind | MONARCH CREEK WIND, LLC | Throckmorton | Wind | 283.4 | 11419 Coody Crossing Switch 345kV | 2027-09-17 | 2020-08-24 | True |  |  | Signed; security posted
30INR0123 | Sideoats Solar 1 | Bush Knob Solar, LLC | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345 kV | 2031-03-31 |  |  |  |  | In study | new
30INR0124 | Sideoats Solar 2 | Bush Knob Solar, LLC | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV | 2031-03-31 |  |  |  |  | In study | new
30INR0125 | Sideoats Solar 3 | Bush Knob Solar, LLC | Throckmorton | Solar | 167.6 | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV | 2031-03-31 |  |  |  |  | In study | new
26INR0327 | Sleepy Hollow BESS | Sleepy Hollow BESS, LLC | Throckmorton | Battery storage | 123.1 | Tap 138 kV 792 Murray - 6169 Paint Creek | 2028-02-22 |  |  |  |  | In study
26INR0454 | Dove Creek Solar | Dove Creek Solar, LLC | Tom Green | Solar | 163.6 | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | 2028-07-01 |  |  |  |  | In study
26INR0455 | Dove Creek Storage | Dove Creek Solar, LLC | Tom Green | Battery storage | 162.5 | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | 2028-07-01 |  |  |  |  | In study
25INR0339 | Fort Concho Energy storage | Rocky Mountain Energy Development, LLC | Tom Green | Battery storage | 251.15 | Tap 138 kV #76320 Schkade - #76011 Twin Buttes Line; LCRA | 2028-12-31 |  |  |  |  | In study
23INR0312 | Hofbrau BESS | Momentum Hofbrau LLC | Tom Green | Battery storage | 180.72 | 6442 Redcreek 138kV | 2028-07-01 |  |  |  |  | In study
29INR0328 | Moon Chapel Solar | Orsted Onshore Development North America, LLC | Tom Green | Solar | 402.01 | Tap 345kV 76090 Divide – 76009 Twin Buttes Ckt 1 | 2029-12-31 |  |  |  |  | In study
27INR0445 | Moon Chapel Wind | Orsted Onshore Development North America, LLC | Tom Green | Wind | 379.2 | Tap 345kV 76090 Divide - 76009 Twin Buttes Ckt 1 | 2028-10-01 |  |  |  |  | In study
23INR0224 | Morning Glory Solar | Armadillo Solar, LLC | Tom Green | Solar | 122.4 | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | 2028-11-30 |  |  |  |  | In study
29INR0376 | Silver Sky BESS | Lightsource Renewable Energy Development LLC | Tom Green | Battery storage | 201.1 | 6444 Red Creek 345kV | 2029-12-13 |  |  |  |  | In study
29INR0365 | Silver Sky Solar | Lightsource Renewable Energy Development LLC | Tom Green | Solar | 401.9 | 6444 Red Creek 345kV | 2029-12-13 |  |  |  |  | In study
25INR0853 | Tango Lily BESS | Lightsource Renewable Energy Development LLC | Tom Green | Battery storage | 200.95 | Tap 138kV 60008 TRIBUTE4A - 6442 REDCREEK4A | 2029-12-22 |  |  |  |  | In study
29INR0231 | Tango Lily Solar | Lightsource Renewable Energy Development LLC | Tom Green | Solar | 200.95 | Tap 138kV 60008 TRIBUTE4A - 6442 REDCREEK4A | 2029-12-21 |  |  |  |  | In study
20INR0247 | Water Valley Wind Energy | Water Valley Wind Energy, LLC | Tom Green | Wind | 180 | 345 kV 76009 Twin Buttes to 76090 Divide Double Circuit | 2027-12-15 | 2025-03-17 | True |  |  | Signed; security posted
26INR0083 | Zeppelin Energy Storage | ZEPPELIN ENERGY STORAGE LLC | Tom Green | Battery storage | 163.93 | 6464 San Angelo North | 2028-05-31 |  |  |  |  | In study
23INR0474 | AP Greenport | AP Greenport | Travis | Battery storage | 100.45 | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | 2027-11-19 |  |  |  |  | In study
27INR0485 | Blackland Prairie 1 Energy Storage | Balcones Ridge Resiliency LLC | Travis | Battery storage | 102.1 | 9328 Austrop 138kV | 2027-12-01 | 2026-04-10 |  |  |  | Signed
27INR0486 | Blackland Prairie 2 Energy Storage | Balcones Ridge Resiliency II LLC | Travis | Battery storage | 102.1 | 9328 Austrop 138kV | 2030-12-01 |  |  |  |  | In study
27INR0487 | Blackland Prairie 3 Energy Storage | Balcones Ridge Resiliency II LLC | Travis | Battery storage | 102.1 | 9328 Austrop 138kV | 2030-12-01 |  |  |  |  | In study
25INR0266 | East Blackland Battery Storage SLF | DERIVA ENERGY STORAGE, LLC | Travis | Battery storage | 75 | 7337 Kimbro 138kV | 2028-05-27 |  |  |  |  | In study
24INR0372 | GIGA AUSTIN SOLAR | GIGA TEXAS ENERGY LLC | Travis | Solar | -53.3 | 7047 HORNSBY Substation 138kV | 2027-03-14 |  |  |  |  | In study
25INR0688 | Giga Texas Data Center | Giga Texas Energy, LLC | Travis | Battery storage | 133 | HORNSBY Substation POIB# 7047 Site will be connected behind the meter at Medium Voltage 24.9 kV with non export controls GSU TRANSFORMER 80/106/133MVA 345kV DELTA PRIMARY 24.9kV WYE-G SECONDARY Z=XX%, 65DEG C RISE | 2025-12-15 | 2025-04-30 |  |  |  | Signed
22INR0488 | Venture Hill Storage | KCE TX 24, LLC | Travis | Battery storage | 70.44 | 7336 Gilleland Creek 138kV | 2026-12-01 |  |  |  |  | In study
24INR0238 | Appaloosa Run BESS | APPALOOSA RUN STORAGE, LLC | Upton | Battery storage | 103 | New Palouse 138kV (#60278) | 2026-08-30 |  |  |  |  | In study
28INR0213 | Badger BESS | Greasewood BESS, LLC | Upton | Battery storage | 138.57 | Tap 345kV 59903 Bearkat - 76000 L_NORTMC5_1Y | 2029-05-25 |  |  |  |  | In study
28INR0212 | Badger Solar | 174 Power Global Properties, LLC | Upton | Solar | 280.46 | Tap 345kV 59903 Bearkat - 76000 L_NORTMC5_1Y | 2029-05-25 |  |  |  |  | In study
24INR0394 | CATHODE BESS | CED Development Inc. | Upton | Battery storage | 150 | 76635 King Mountain 138kV | 2027-12-31 |  |  |  |  | In study
24INR0393 | ELECTRODE BESS | CED Development Inc. | Upton | Battery storage | 150 | 76040 Castillo 138kV | 2027-12-31 |  |  |  |  | In study
21INR0006 | Giddings Wind | Pioneer Natural Resources | Upton | Wind | 240 | 71212 Upton 138kV | 2030-09-09 |  |  |  |  | In study
19INR0002 | Grandfalls Solar | King Mountain Solar, LLC | Upton | Solar | 175.6 | 842 King Mountain Station 345kV | 2026-11-25 | 2025-01-23 | True | 2026-06-24 | 2026-07-15 | Approved for synchronization
21INR0262 | Grandfalls Storage SLF | King Mountain Storage LLC | Upton | Battery storage | 175.6 | tap 345kV 11028 Odessa - 76000 North McCamey | 2028-07-01 |  |  |  |  | In study
25INR0557 | McCamey's Castle Battery | Castle Storage, LLC | Upton | Battery storage | 409.6 | 76597 Robbins Switch 138 kV | 2028-03-30 | 2025-03-20 | True |  |  | Signed; security posted
25INR0417 | Mesa View Storage | Mesa View Storage, LLC | Upton | Battery storage | 254.88 | Tap 345 kV KINGMTSW (#842) to NORTMC (#76000) | 2027-07-15 | 2024-09-09 | True |  |  | Signed; security posted
19INR0189 | SP TX-12B Phase III | ConEd Development | Upton | Solar | 40 | 76040 Castillo 138kV | 2025-12-02 |  |  |  |  | In study
25INR0207 | Shadow Ranch Solar | LectricWind LLC | Upton | Solar | 807.61 | 842 King Mountain 345kV | 2030-06-01 |  |  |  |  | In study
25INR0451 | Tres Rios Ranch BESS | LectricWind LLC | Upton | Battery storage | 290 | 76008 Twelvemile 345kV | 2027-12-31 | 2025-12-30 |  |  |  | Signed
24INR0404 | Tres Rios Ranch Solar | LectricWind LLC | Upton | Solar | 508 | 76008 Twelvemile 345kV | 2027-12-31 | 2025-12-30 |  |  |  | Signed
28INR0446 | Vista Bluff Wind I "Alternate POI" | Vista Bluff Windpower, LLC | Upton | Wind | 290.4 | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | 2029-12-31 |  |  |  |  | In study
28INR0447 | Vista Bluff Wind II "Alternate POI" | Vista Bluff Windpower, LLC | Upton | Wind | 290.4 | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | 2029-12-31 |  |  |  |  | In study
28INR0086 | West Royal Natural Gas (TEF-Due Diligence) | Invenergy Energy Transition Development LLC | Upton | Gas turbine | 888 | Tap 345kV 76000 L_NORTMC5_1Y - 18668 ROCKDRAW_5 | 2030-06-01 |  |  |  |  | In study
28INR0057 | Windecker | Windecker Energy LLC | Upton | Wind | 419.7 | 10058 Catclaw Switch 138kV | 2028-04-17 |  |  |  |  | In study
28INR0188 | Ashra Solar SLF | Ashra Solar, LLC | Uvalde | Solar | 40.25 | Tap 69kV bus#5823 UVALDE Switch (UVALDESW9) to bus#5820 UVALDE SUB (UVALDESUB9) | 2028-06-14 |  |  |  |  | In study
28INR0190 | Ashra Storage SLF | Ashra Solar, LLC | Uvalde | Battery storage | 1.62 | Tap 69kV 5823 UVALDE Switch - 5820 UVALDE SUB | 2028-06-14 |  |  |  |  | In study
21INR0334 | Nightfall Solar | BDPU SOLAR NIGHTFALL, LLC | Uvalde | Solar | 180.87 | 138 kV Tap 8707 Dryfrio - 8234 Uvalde (new 138 kV Meil station) | 2026-12-31 | 2023-10-26 | True | 2026-09-22 |  | Approved for energization | Signed; security posted -> Energized
26INR0260 | Evans Creek Energy Storage | Evans Creek Energy Storage LLC | Val Verde | Battery storage | 102.96 | Comstock 138kV Substation (PSSE Bus #8683) | 2028-04-01 |  |  |  |  | In study
26INR0419 | Lone Bow Solar | Greenalia Solar Power Lone Bow LLC | Val Verde | Solar | 277.46 | Tap 138 kV 8683 Comstock - 60389 Corral | 2030-06-15 |  |  |  |  | In study
25INR0546 | VISOL 1 SOLAR | VISOL 1 SOLAR, LLC | Val Verde | Solar | 94.78 | Tap 138kV 8683 Comstock - 60389 Corral | 2028-06-30 |  |  |  |  | In study
24INR0472 | Amador Storage | BT Amador Storage, LLC | Van Zandt | Battery storage | 102.41 | 6833 Explorer Switching Station 138kV | 2027-04-08 | 2023-11-02 | True |  |  | Signed; security posted
23INR0045 | Caney Creek Solar | HEP Aquamarine Holdings LLC | Van Zandt | Solar | 121.04 | Tap 138kV 6829 Glen Pine - 6833 Explorer | 2027-06-21 | 2021-12-29 | True |  |  | Signed; security posted
27INR0317 | Edgewood BESS 1 | Tempus Power management LLC | Van Zandt | Battery storage | 102.1 | Tap Edgewood 138kV bus(3181) to CANTNSW_8 (3174) | 2028-03-01 |  |  |  |  | In study
27INR0413 | Edgewood BESS 2 | Tempus Power management LLC | Van Zandt | Battery storage | 102.1 | Tap Edgewood 138kV bus(3181) to 3174 | 2028-03-01 |  |  |  |  | In study
26INR0253 | Goldfinch Solar | BT DJ4M Solar, LLC | Van Zandt | Solar | 150.77 | Tap Connection Bus 2485 Poetry Switch to 3103 Shamburger Switch | 2029-03-31 |  |  |  |  | In study
26INR0254 | Goldfinch Storage | BT DJ4M Solar, LLC | Van Zandt | Battery storage | 100.44 | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | 2030-03-31 |  |  |  |  | In study
25INR0253 | Whiskey BESS | Whiskey BESS LLC | Van Zandt | Battery storage | 153.72 | 6828 Canton Tap 138 kV | 2027-07-31 | 2025-03-28 |  |  |  | Signed
25INR0384 | Zorro BESS | ZORRO BESS LLC | Van Zandt | Battery storage | 153.69 | 138 kV Ben Wheeler (Bus# 6852) | 2027-08-31 | 2025-03-28 |  |  |  | Signed
28INR0356 | Arpeggio BESS | Arpeggio BESS, LLC | Victoria | Battery storage | 200.71 | #80064 Chocolate Bayou 138kV | 2029-09-30 |  |  |  |  | In study
29INR0248 | Blue Energy Center - Phase 1b – Steam | Brother 1, LLC | Victoria | Gas combined cycle | 330 | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | 2031-10-17 |  |  |  |  | In study
33INR0007 | Blue Energy Center - Phase 3 – Steam Stage 2 | Sister 1, LLC | Victoria | Nuclear | 1320 | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | 2033-06-15 |  |  |  |  | In study | new
30INR0150 | Blue Energy Center- Phase 1a - Gas | Brother 1, LLC | Victoria | Gas turbine | 780 | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | 2030-05-02 |  |  |  |  | In study | new
23INR0342 | Brizo BESS | BRP Brizo BESS LLC | Victoria | Battery storage | 144.22 | 138 kV Loop 463 Substation (#5680) | 2027-09-01 | 2025-03-27 |  |  |  | Signed
27INR0382 | Calico BESS | Nova Clean Energy LLC | Victoria | Battery storage | 204.9 | Tap 138 kV 8723 CANGREJO4A - 8721 BEECHER4A | 2028-06-01 |  |  |  |  | In study
26INR0021 | Crossroads Wind | HyFuels Green Lake Wind LLC | Victoria | Wind | 277.38 | 80090 Dokmai 138 KV | 2028-02-28 | 2024-07-24 | True |  |  | Signed; security posted
26INR0559 | Georgia-Lynn BESS | Georgia Lynn BESS LLC | Victoria | Battery storage | 108.7 | 80064 CHOCBAYU4A 138 kV | 2028-02-20 |  |  |  |  | In study
26INR0505 | Goldhill Energy Storage | Goldhill Energy Storage LLC | Victoria | Battery storage | 200.58 | Tap 138kV 8154 VISTRON4B – 8189 TUNGSTEN4A | 2028-09-30 |  |  |  |  | In study
26INR0028 | HyFuels Calhoun Solar | HyFuels Green Lake Solar LLC | Victoria | Solar | 301.82 | Tap 345kV 8715 RADIANT7A - 8728 COBRA7A | 2028-10-07 |  |  |  |  | In study
23INR0090 | Iguala Solar | Iguala Solar LLC | Victoria | Solar | 250 | AEP South Texas Project (#5915) to Static (#8676) 345kV line | 2029-02-01 | 2025-07-29 |  |  |  | Signed
27INR0224 | Leopard BESS | Bobcat Energy Center, LLC | Victoria | Battery storage | 264.24 | 8721 Beecher 138 kV | 2029-02-28 | 2025-06-09 | True |  |  | Signed; security posted
27INR0170 | Marcos BESS | GRS BESS Texas Eight LLC | Victoria | Battery storage | 115.88 | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | 2027-08-15 |  |  |  |  | In study
27INR0169 | Marcos Solar SLF | GRS BESS Texas Eight | Victoria | Solar | 216.11 | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | 2028-08-15 |  |  |  |  | In study
29INR0243 | Oak Belt Solar | Oak Belt Solar, LLC | Victoria | Solar | 181 | Tap 138 kV (Bus #5506) FURHMANSB8 - (Bus #5584) VANDERBLTSW8 | 2030-03-31 |  |  |  |  | In study
29INR0244 | Oak Belt Storage | Oak Belt Storage, LLC | Victoria | Battery storage | 209.7 | Tap 138 kV (Bus #5506) FURHMANSB8 - (Bus #5584) VANDERBLTSW8 | 2030-03-31 |  |  |  |  | In study
24INR0168 | Tejano Storage | Tejano Storage, LLC | Victoria | Battery storage | 152.31 | Tap 138kV 8125 Lolita - 8172 Victoria | 2029-07-01 |  |  |  |  | In study
24INR0425 | Two Brothers ESS | BRP Blue Topaz 2, LLC | Victoria | Battery storage | 154.65 | 8911 BLKBYU4A 138kV | 2028-02-29 | 2024-04-22 | True |  |  | Signed; security posted
24INR0461 | Augie BESS | BRP Blue Topaz 5, LLC | Waller | Battery storage | 200.81 | 46560 Waller 138kV | 2027-12-17 |  |  |  |  | In study
26INR0243 | Caladium BESS | Caladium Storage, LLC | Waller | Battery storage | 201.28 | 57664 Sunnyside 69kV | 2027-11-30 |  |  |  |  | In study
26INR0426 | Maderagemela BESS1 | Twinwood ES1, LLC | Waller | Battery storage | 153.96 | Tap 138kV 44750 FULSHR_S25_8 to 44860 TWINWD_S25_8 | 2029-02-01 | 2025-11-07 | True |  |  | Signed; security posted
26INR0773 | Seaway BESS | Mount Whitney Energy Storage LLC | Waller | Battery storage | 9.9 | TSP Substation Name - Seaway TSP Substation Code - Seaway Load Name/Load Transformer Name - LOAD_T-4 Bus # / PTI Bus Number: 57670 Voltage (Transmission level Kv) - 138kV Node (associated w/ load/load XFMR in NMMS) - 0009 | 2027-02-22 | 2024-12-11 | True |  |  | Signed; security posted
26INR0425 | Twinwood Solar 1 | Twinwood PV1, LLC | Waller | Solar | 358.06 | Tap 138kV 44750 FULSHR_S25_8 - 44860 TWINWD_S25_8 | 2029-02-01 | 2025-11-07 | True |  |  | Signed; security posted
23INR0094 | BRP Pyxis BESS | BRP Pyxis BESS LLC | Ward | Battery storage | 206.87 | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | 2028-12-01 |  |  |  |  | In study
23INR0075 | BRP Rhine BESS | BRP Rhine BESS LLC | Ward | Battery storage | 206.89 | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | 2028-12-01 |  |  |  |  | In study
25INR0008 | BasRanch (TEF - Due Diligence) | CPV Basin Ranch, LLC | Ward | Gas combined cycle | 1350 | tap 345kV Riverton Switch - Sand Lake Switch | 2028-12-01 | 2025-07-16 | True |  |  | Signed; security posted
24INR0538 | FLIFER Solar I | FLIFER LLC | Ward | Solar | 84 | Tap 138 kV Yucca Drive Switch (bus# 1009) – Sand Tank (bus# 11197) | 2027-04-15 |  |  |  |  | In study
27INR0562 | Frizzle BESS | Frizzle BESS, L.L.C. | Ward | Battery storage | 180.9 | #38143, TNSLVRLEAF1, 138kV | 2027-10-18 |  |  |  |  | In study
26INR0724 | Monahans Power Gas | Liberty Power Innovations LLC | Ward | Gas engines | 18.2 | Tap #1107 Monahans Tap 2 to #11117 Pecos Trail 138kV | 2030-04-16 |  |  |  |  | In study
27INR0255 | New Minglewood Energy Center | Nova Clean Energy LLC | Ward | Battery storage | 208.3 | #11098 Sand Lake Switch Station (SANDLAKE_5) 345kV | 2029-09-29 |  |  |  |  | In study
25INR0606 | Proteus Thornton Ranch Solar SLF | Thornton Ranch Solar, LLC | Ward | Solar | 180 | 37990 TNSTAGHORN1 138kV | 2028-11-20 |  |  |  |  | In study
25INR0607 | Proteus Thornton Ranch Storage SLF | Thornton Ranch Solar, LLC | Ward | Battery storage | 0 | 37990 TNSTAGHORN1 138kV | 2028-11-20 |  |  |  |  | In study
27INR0202 | Shallow Valley Storage | Shallow Valley Storage, LLC | Ward | Battery storage | 103.39 | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | 2029-04-19 |  |  |  |  | In study | new
26INR0698 | Staghorn Gas | RPC Merchant LLC | Ward | Gas engines | 9.99 | STATION NAME: STAGHORN LOAD NAME: STGHRN_3 TNMP TRANSFORMER NAME: T3 BUS #: 37990 TRANSMISSION VOLTAGE: 138KV NODE: 9984 | 2026-10-29 | 2025-05-30 | True | 2026-09-02 | 2026-09-18 | Approved for synchronization | Signed; security posted -> Approved to connect
28INR0105 | Vast Sands Power I (TEF -Due Diligence) | Permian Power I LLC | Ward | Gas turbine | 440 | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | 2028-05-01 | 2025-10-31 | True |  |  | Signed; security posted
28INR0109 | Vast Sands Power II (TEF-Due Diligence) | Permian Power I LLC | Ward | Gas turbine | 440 | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | 2028-06-30 | 2025-10-31 | True |  |  | Signed; security posted
26INR0024 | Becerra Creek Storage 1 | Bordas Renewable Energy, LLC | Webb | Battery storage | 125.62 | 345 kV Cenizo Substation (#80220) | 2027-12-01 |  |  |  |  | In study
27INR0003 | Becerra Creek Storage 2 | Bordas Renewable Energy, LLC | Webb | Battery storage | 125.62 | 345 kV Cenizo Substation (#80220) | 2027-12-01 |  |  |  |  | In study
27INR0398 | Bravo BESS | Bravo BESS LLC | Webb | Battery storage | 207.38 | Tap 345kV 80220 CENIZO7A - 80224 TIEMPO7A | 2027-12-12 |  |  |  |  | In study
29INR0219 | Cenizo Solar | Cenizo Energy Center LLC | Webb | Solar | 301.39 | Tap 345 kV 80220 Cenizo - 80079 Cruce Ckt 2 | 2029-12-31 | 2026-09-28 |  |  |  | Signed | In study -> Signed
22INR0257 | Corazon Solar Phase II | BAYWA R.E. SOLAR PROJECTS | Webb | Solar | 203.9 | 80219 Lobo 345kV | 2028-06-01 | 2020-08-04 |  |  |  | Signed
27INR0126 | Corvus Solar | Corvus Solar, LLC | Webb | Solar | 201.5 | Tap 345kV Cenzio (#80219) - Lobo (#80220) | 2028-11-12 | 2025-07-31 | True |  |  | Signed; security posted
27INR0077 | Cuchillas BESS | Gransolar Texas Two | Webb | Battery storage | 306.94 | 80219 Lobo 345kV | 2028-12-15 |  |  |  |  | In study
24INR0059 | Cuchillas Solar | Gransolar Texas Two, LLC | Webb | Solar | 305.6 | 80219 Lobo 345kV | 2028-12-15 | 2023-06-20 | True |  |  | Signed; security posted
27INR0414 | Diamond Sage BESS 1 | DGC Renewables, LLC | Webb | Battery storage | 103.5 | tap 345kV 80219 LOBO7A - 5709 FOWLERTONSW5 CKT2 | 2028-10-01 |  |  |  |  | In study
27INR0444 | Diamond Sage BESS 2 | DGC Renewables, LLC | Webb | Battery storage | 103.5 | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | 2028-10-01 |  |  |  |  | In study
27INR0390 | Diamond Sage Solar 1 | DGC Renewables, LLC | Webb | Solar | 213.96 | tap 345kV 80219 LOBO7A - 5709 FOWLER TONSW5 CKT2 | 2028-10-01 |  |  |  |  | In study
27INR0395 | Diamond Sage Solar 2 | DGC Renewables, LLC | Webb | Solar | 213.96 | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | 2028-10-01 |  |  |  |  | In study
25INR0321 | El Molino Solar SLF | El Molino Solar, LLC | Webb | Solar | 201.32 | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | 2029-09-01 |  |  |  |  | In study
25INR0322 | El Molino Storage SLF | El Molino Solar, LLC | Webb | Battery storage | 0 | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | 2029-09-01 |  |  |  |  | In study
23INR0209 | Outpost Storage | Hecate Energy Outpost Storage LLC | Webb | Battery storage | 508.1 | 345kv Avanzada7A (80235) | 2028-03-01 |  |  |  |  | In study
23INR0183 | Pradera Storage | Pradera Storage, LLC | Webb | Battery storage | 153.11 | tap 345 kV Lobo 80219 - Fowlerton 5709 ckt #2 | 2029-06-23 |  |  |  |  | In study
20INR0047 | Siete | Apex Clean Energy | Webb | Wind | 492.8 | 345kV 8718 Triada | 2029-03-31 | 2022-06-30 | True |  |  | Signed; security posted
27INR0536 | Siete Wind | Siete Wind, LLC | Webb | Wind | 492.8 | 345kV 8718 Triada | 2028-01-03 |  |  |  |  | In study
23INR0529 | Torrecillas BESS | Torrecillas Interconnect, LLC | Webb | Battery storage | 9.9 | 161257 Torrecillas 345kV Station code: TORR | 2026-12-31 | 2015-01-30 | True | 2025-06-25 | 2025-07-01 | Approved for synchronization
28INR0068 | Alpujarra Solar | Greening USA Corp. | Wharton | Solar | 112.5 | 5521 GALOW 138 KV | 2028-05-01 |  |  |  |  | In study
25INR0545 | Blue Creek Energy Storage | Blue Creek Energy Storage, LLC | Wharton | Battery storage | 101.2 | Tap 138kV 42985 DYANN_POI8 - 43190 S_LANE_B138 Ckt 60 | 2028-12-31 |  |  |  |  | In study
24INR0576 | Boling Generation (TEF-Due Diligience) | Boling Generation | Wharton | Gas turbine | 400 | 43340 Gulftie 138kV | 2028-12-16 |  |  |  |  | In study
28INR0030 | Brela BESS LLC | Brela BESS LLC | Wharton | Battery storage | 251.3 | 44040 Bailey SW 345 kV | 2028-05-29 |  |  |  |  | In study
27INR0392 | Cernan BESS | Cernan BESS LLC | Wharton | Battery storage | 10.04 | Hillje 345kV (#44200) | 2028-10-02 | 2025-12-30 |  |  |  | Signed
27INR0102 | Cottonseed Energy Storage | Cottonseed Energy Storage LLC | Wharton | Battery storage | 207.6 | South Lane City and PSEE # is 43190 | 2027-04-20 |  |  |  |  | In study
20INR0069 | Danish Fields Solar | Danish Fields Solar, LLC | Wharton | Solar | 602.8 | 44200 Hillje 345kV | 2026-08-29 | 2020-02-24 | True | 2023-03-27 | 2023-05-04 | Approved for synchronization
23INR0137 | Diran BESS | BRP Diran BESS LLC | Wharton | Battery storage | 103 | 43190 South Lane City 138kV | 2028-01-31 | 2025-01-07 | True |  |  | Signed; security posted
25INR0601 | East Bernard BESS | Regis East Bernard LLC | Wharton | Battery storage | 9.5 | Station Name: East Bernard Station Code: EB ERCOT Load Name: TR2 ERCOT BUS #: 44190 Voltage (Transmission level kV): 138 Node associated with load XFMR: 8045 CNP 5-Digit Code: E_BERN Short Code: EB TR2 Feeder: EB-81 CNP XFMR #: EB TR2 | 2026-11-04 | 2024-04-29 | True |  |  | Signed; security posted
28INR0090 | EmberGreen | EmberGreen Energy Center | Wharton | Gas turbine | 1036 | Tap 138kV 48050 Caney - 44150 Hungerford | 2028-01-01 | 2026-08-04 |  |  |  | Signed
23INR0058 | Erin Solar | Erin Solar LLC | Wharton | Solar | 208.34 | 44040 Bailey 345 kV | 2029-12-31 | 2023-03-22 |  |  |  | Signed
24INR0569 | Hadrian Energy Storage | Hadrian Energy Storage, LLC | Wharton | Battery storage | 101.2 | Line Tap 138kV #43012 NEWGLF60T3_8 - #43190 S_LANE_B138 | 2028-12-31 |  |  |  |  | In study
25INR0741 | Hollywood Solar Repower | RED TAILED HAWK SOLAR LLC | Wharton | Solar | 9.9 | 44060 BLU 345kV | 2026-09-30 | 2025-10-21 | True |  |  | Signed; security posted
25INR0542 | Hynes Bay Energy Storage | Hynes Bay Energy Storage, LLC | Wharton | Battery storage | 101.2 | Tap 138kV 5546 DANEVANG SW - 8121 BLESSING | 2027-12-31 |  |  |  |  | In study
22INR0517 | Lane City Wind | RWE Clean Energy, LLC | Wharton | Wind | 199.5 | 44040 Bailey 345kV | 2026-12-31 | 2022-05-13 | True | 2025-06-12 | 2025-07-28 | Approved for synchronization
27INR0112 | Malachite BESS | Malachite Storage LLC | Wharton | Battery storage | 191.12 | Tap 345 kV 44200 Hillje – 9073 Holman | 2032-04-30 | 2025-12-26 |  |  |  | Signed
27INR0111 | Malachite Solar | Malachite Solar LLC | Wharton | Solar | 184.55 | The 345 kV Hillje (#44200) – Holman (#9073) Line; AEN. | 2032-04-30 | 2025-12-26 |  |  |  | Signed
21INR0220 | Maleza Solar | Brush Solar LLC | Wharton | Solar | 254.94 | tap Blue – Hillje 345 kv Ckt.#27 | 2028-12-31 | 2021-01-13 | True |  |  | Signed; security posted
23INR0227 | Maleza Solar II | Brush Solar, LLC | Wharton | Solar | 254.94 | tap Blue – Hillje 345 kv Ckt.#27 | 2028-12-31 |  |  |  |  | In study
21INR0456 | Maleza Storage | Brush Storage, LLC | Wharton | Battery storage | 150.83 | tap Blue – Hillje 345 kv Ckt.#27 | 2028-12-31 |  |  |  |  | In study
25INR0582 | Maleza Storage II | Brush Storage, LLC | Wharton | Battery storage | 256.1 | 44220 Julia 345kV | 2028-12-31 |  |  |  |  | In study
28INR0452 | Neal Battery | CH Neal Battery LLC | Wharton | Battery storage | 120.52 | tap of 138kV 8750 Chalmers - 8127 Lane City | 2029-04-03 |  |  |  |  | In study
28INR0160 | Neal Solar | CH Neal Solar LLC | Wharton | Solar | 146.6 | tap of 138kV 8750 Chalmers - 8127 Lane City | 2029-04-03 |  |  |  |  | In study
25INR0319 | Northington Solar | Northington Solar, LLC | Wharton | Solar | 125.9 | The 138 kV El Campo (#8102) - Pulsar (#8192) Line; AEP. | 2028-03-14 | 2024-10-02 | True |  |  | Signed; security posted
24INR0167 | OCI SunRoper | OCI SunRoper LLC | Wharton | Solar | 265.1 | tap138kV #43190 South Lane City to #42985 Dyann CKT#60 | 2027-10-01 | 2025-07-10 | True |  |  | Signed; security posted
26INR0725 | PHOTON BESS REPOWERING | GulfStar Power, LLC | Wharton | Battery storage | 305.48 | 44880 Waterh_POI_5 345kV | 2027-08-17 |  |  |  |  | In study
25INR0493 | PHOTON SOLAR 1 2 SLF | GulfStar Power, LLC | Wharton | Solar | 235.66 | 44880 Waterh_POI_5 345kV | 2026-05-11 | 2021-10-01 | True | 2024-10-15 | 2024-10-31 | Approved for synchronization
23INR0111 | PHOTON SOLAR 3 SLF | GulfStar Power, LLC | Wharton | Solar | 109.99 | 44880 Waterh_POI_5 345kV | 2026-05-11 | 2021-10-01 | True | 2024-05-17 | 2024-10-02 | Approved for synchronization
25INR0673 | PHOTON SOLAR 4 SLF | GulfStar Power, LLC | Wharton | Solar | 105.98 | 44880 Waterh_POI_5 345kV | 2026-05-11 |  | True | 2024-06-25 | 2024-11-04 | Approved for synchronization
26INR0718 | PHOTON SOLAR REPOWERING | GulfStar Power, LLC | Wharton | Solar | 0 | 44880 Waterh_POI_5 345kV | 2027-08-17 | 2021-02-25 |  |  |  | Signed
29INR0082 | Peach Creek Solar | AEUG Peach Creek Solar LLC | Wharton | Solar | 300 | 44040 Bailey 345 kV | 2029-09-30 |  |  |  |  | In study
21INR0505 | Ramsey Storage | Hecate Energy Ramsey Storage LLC | Wharton | Battery storage | 500 | 44200 Hillje 345kV | 2028-06-30 | 2022-08-11 | True |  |  | Signed; security posted
24INR0210 | Raven Storage | Raven Storage, LLC | Wharton | Battery storage | 103.53 | Tap 138kV 44740 Wallis - 44190 East Bernard CKT#65 | 2027-02-01 | 2024-06-04 | True |  |  | Signed; security posted
22INR0205 | Sbranch Solar | Bernard Creek Solar, LLC | Wharton | Solar | 233.52 | Tap 138kV 44190 East Bernard - 44130 Caney | 2026-10-31 | 2020-07-26 | True | 2022-09-12 | 2023-11-21 | Approved for synchronization
26INR0474 | Sorghum BESS | Blue Creek BESS, LLC | Wharton | Battery storage | 208.9 | #44060 Blue Substation 345kV | 2027-12-01 | 2025-01-08 |  |  |  | Signed
21INR0341 | Space City Solar | Apollo Solar Ranch, LLC | Wharton | Solar | 366 | 44200 Hillje 345kV | 2027-06-01 | 2025-12-11 | True |  |  | Signed; security posted
30INR0133 | Starfield Energy Storage | Starfield Energy Storage, LLC | Wharton | Battery storage | 122.2 | Tap 138kV 44150 Hungerford - 44190 East Bernard | 2030-12-31 |  |  |  |  | In study | new
24INR0605 | TEXAS GULF SULPHUR REPOWER | Wharton County Generation, LLC | Wharton | Gas turbine | 16.1 | 43340 Gulftie 138 kV | 2025-03-27 | 2022-03-01 | True |  | 2025-02-17 | Approved for synchronization
25INR0293 | TOCE BESS 1 | TOCE BESS 1, LLC | Wharton | Battery storage | 205.2 | 138 kV Danevang Switching Station (Bus# 5546) | 2028-12-31 | 2024-12-30 |  |  |  | Signed
20INR0238 | Voyager Storage | EDF Renewables Development, Inc. | Wharton | Battery storage | 50.14 | 44200 Hillje 345kV | 2028-04-08 |  |  |  |  | In study
26INR0144 | Wittig Solar | Greenalia Solar Power Wittig LLC | Wharton | Solar | 106.9 | 138 kV Gulftie (#43340) – San Bernard (#43110) | 2028-10-30 |  |  |  |  | In study
29INR0197 | Zora Solar | Zora Solar, LLC | Wharton | Solar | 250.8 | 46650 Athena 138 kV | 2029-10-15 |  |  |  |  | In study
30INR0077 | Moon Hammer | Moon Hammer LLC | Wheeler | Gas turbine | 1300 | tap 345 kV line between Tesla & Grey | 2030-11-30 | 2025-12-19 |  |  |  | Signed
26INR0472 | Bologna BESS | MALONEY BESS LLC | Wichita | Battery storage | 202.56 | Tap 138kV #1450 Pleasant Valley Switch - #1492 Wichita Falls Riverbend | 2028-04-19 |  |  |  |  | In study
28INR0118 | Copperleaf Energy Storage | Copperleaf Energy Storage, LLC | Wichita | Battery storage | 305.63 | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) | 2029-09-25 |  |  |  |  | In study
25INR0154 | Nymphaea Solar | Nymphaea Solar, LLC | Wichita | Solar | 120.9 | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | 2028-07-01 | 2026-05-18 | True |  |  | Signed; security posted
25INR0155 | Nymphaea Storage | Nymphaea Solar, LLC | Wichita | Battery storage | 61 | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | 2028-07-01 | 2026-05-18 | True |  |  | Signed; security posted
26INR0280 | Pethrus BESS | Pethrus BESS, LLC | Wichita | Battery storage | 174.08 | Tap Wichita Falls Switch (#1464) – North Star (#1467) 138 kV Line | 2029-03-03 |  |  |  |  | In study
28INR0221 | Rio Star Energy Storage | Rio Star Energy Storage, LLC | Wichita | Battery storage | 142.58 | Tap 1464 Wichita Falls South Switch – 1474 Scotland 138 kV | 2029-04-20 |  |  |  |  | In study
27INR0029 | Short Creek BESS | Wichita Solar I, LLC | Wichita | Battery storage | 155.66 | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | 2028-07-01 |  | True |  |  | Signed; security posted
24INR0201 | Short Creek Solar | Wichita Solar I, LLC | Wichita | Solar | 627.81 | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | 2027-12-17 | 2024-10-02 | True |  |  | Signed; security posted
27INR0412 | Spinosa BESS | Spinosa Energy Center, LLC | Wichita | Battery storage | 201.2 | Tap 138 kV Wichita Falls Cogen (#1498) – Pleasant Valley Switch (#1450) | 2030-05-08 |  |  |  |  | In study
26INR0613 | Wichita County Mawson Storage | DM-WCM, LLC | Wichita | Battery storage | 153.62 | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) Line | 2029-04-16 |  |  |  |  | In study
28INR0377 | Wichita Creek Solar | Wichita Solar II, LLC | Wichita | Solar | 3.43 | Tap 345 kV 6111 RILEY - 1730 KRUM WEST Ckt 1 | 2030-04-15 |  |  |  |  | In study
28INR0378 | Wichita Creek Storage | Wichita Solar II, LLC | Wichita | Battery storage | 300 | Tap 345 kV 6111 RILEY - 1730 KRUM WEST Ckt 1 | 2030-04-15 |  |  |  |  | In study
21INR0210 | Adamstown Solar | Adams Creek Solar Project, LLC | Wilbarger | Solar | 250.88 | tap 345kV 1730 West Krum - 6111 Riley Ckt 2 | 2027-08-31 | 2024-12-04 | True |  |  | Signed; security posted
25INR0492 | Blue Summit Energy Storage | NextEra Energy Interconnection Holdings, LLC | Wilbarger | Battery storage | 100 | 61001 JIM TREECE 345kV | 2026-07-31 | 2012-02-22 | True | 2025-12-17 | 2026-02-03 | Approved for synchronization
27INR0004 | Dundee West Wind | Felix 2, LLC | Wilbarger | Wind | 146.49 | 345 kV Riley Substation (#6101); AEP | 2027-12-31 | 2025-02-21 | True |  |  | Signed; security posted
27INR0007 | Felix East Solar | Felix 1, LLC | Wilbarger | Solar | 200.92 | The 345 kV Riley Substation (#6101); AEP | 2028-12-31 | 2025-02-21 | True |  |  | Signed; security posted
22INR0209 | Felix North Solar | Crescent Solar, LLC | Wilbarger | Solar | 200.98 | 6101 Riley 345kV | 2028-12-31 | 2025-02-21 | True |  |  | Signed; security posted
27INR0009 | Felix Storage | Felix 1, LLC | Wilbarger | Battery storage | 100.54 | The 345 kV Riley Substation (#6101); AEP | 2027-07-31 |  |  |  |  | In study
27INR0012 | Felix West Solar | Felix 1, LLC | Wilbarger | Solar | 200.95 | 6101 Riley 345 kV | 2028-12-31 | 2025-02-21 | True |  |  | Signed; security posted
28INR0464 | Grayback Solar | Grayback Solar, LLC | Wilbarger | Solar | 221.81 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2029-09-01 |  |  |  |  | In study
32INR0006 | H&C WILBARGER POWER I | H&C WILBARGER POWER I | Wilbarger | Gas combined cycle | 1025.55 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2032-02-27 |  |  |  |  | In study
32INR0008 | H&C WILBARGER POWER II | H&C WILBARGER POWER I | Wilbarger | Gas combined cycle | 1025.55 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | 2032-02-27 |  |  |  |  | In study
27INR0581 | Limitless Energy Hub I | Limitless Energy Hub I LLC | Wilbarger | Gas combined cycle | 1238.25 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B. | 2028-12-01 | 2025-12-31 |  |  |  | Signed
27INR0582 | Limitless Energy Hub II | Limitless Energy Hub II LLC | Wilbarger | Gas combined cycle | 1238.25 | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B. | 2028-12-01 | 2025-12-31 | True |  |  | Signed; security posted
23INR0273 | Poco Trail Solar | Eastern Trail Solar Center, LLC | Wilbarger | Solar | 438.75 | Tap 345kV 6101 Riley - 1422 Bowman Byrd Road Switch | 2029-04-02 |  |  |  |  | In study
25INR0377 | Proteus Vernon Solar SLF | Vernon Solar and Storage LLC (a Delaware LLC) | Wilbarger | Solar | 75 | 6060 Vernon 138kV | 2029-02-18 |  |  |  |  | In study
25INR0416 | Proteus Vernon Storage SLF | Vernon Solar and Storage LLC (a Delaware LLC) | Wilbarger | Battery storage | 0 | 6060 Vernon 138kV | 2029-02-18 |  |  |  |  | In study
28INR0332 | Reunion Solar | Reunion Solar, LLC | Wilbarger | Solar | 600.9 | Tap 345kV #60504 Tesla Road to #6111 Riley | 2028-07-01 |  |  |  |  | In study
28INR0333 | Reunion Storage | Reunion Solar, LLC | Wilbarger | Battery storage | 200.3 | Tap 345kV #60504 Tesla Road to #6111 Riley | 2028-07-01 |  |  |  |  | In study
22INR0497 | TEXPO | Oklaunion Power Station, LLC | Wilbarger | Gas steam turbine | 680 | 6101 Riley 345 kV | 2027-10-31 |  |  |  |  | In study
27INR0207 | Wander Waters BESS | Wander Waters BESS LLC | Wilbarger | Battery storage | 303.5 | 61001 JIMTREEC7A 345kV | 2027-10-31 |  |  |  |  | In study
27INR0332 | White Wing Solar | White Wing Solar, LLC | Wilbarger | Solar | 127.4 | Tap 345 kV (#60504) Tesla - (#6111) Riley | 2028-07-01 |  |  |  |  | In study
27INR0333 | White Wing Storage | White Wing Solar, LLC | Wilbarger | Battery storage | 130.4 | Tap 345 kV (#60504) Tesla - (#6111) Riley | 2028-07-01 |  |  |  |  | In study
20INR0097 | El Sauz Ranch | El Sauz Ranch Wind, LLC | Willacy | Wind | 301.5 | 8663 EL SAUZ POI 345kV | 2026-12-01 | 2021-01-27 | True | 2022-09-28 | 2023-02-28 | Approved for synchronization
26INR0507 | Los Vientos IB Repower | Los Vientos Windpower IB, LLC | Willacy | Wind | 184.8 | #8319 RIOHONDO 138 kV | 2029-03-01 |  |  |  |  | In study
24INR0534 | Lyford Energy | Lyford Energy, LLC | Willacy | Battery storage | 101.2 | 5745 E Raymondville 138kV | 2027-09-02 |  |  |  |  | In study
19INR0023 | Monte Alto 2 Wind | Monte Alto Windpower, LLC | Willacy | Wind | 199.2 | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | 2028-12-31 | 2022-03-22 | True |  |  | Signed; security posted
27INR0606 | Big Watt Mustang Power | Big Watt Power Mustang LLC | Williamson | Gas combined cycle | 448.98 | Tapping the 138 kV line from Taylor (Bus#3658) to Thorndale North (Bus#3659) | 2028-12-15 |  |  |  |  | In study
26INR0077 | Anila BESS | Alina Energy LLC | Wilson | Battery storage | 209 | Tap of 345 kV Elm Creek (Bus# 5133) - San Miguel Gen (Bus# 5901) Transmission Line Ckt 1 | 2028-09-30 | 2025-03-06 | True |  |  | Signed; security posted
26INR0074 | Anila Solar | Alina Energy LLC | Wilson | Solar | 200.8 | Tap 345kV 5133 Elm Creek - 5901 San Miguel Gen Ckt 1 | 2028-09-30 | 2025-03-06 | True |  |  | Signed; security posted
23INR0077 | Cachena Storage SLF | Clear Fork Creek Solar LLC | Wilson | Battery storage | 0 | Tap 345KV 5133 Elmcreek - 5323 Old Hickory | 2027-04-29 |  |  |  |  | In study
23INR0027 | Clear Fork Creek Solar | Clear Fork Creek Solar LLC | Wilson | Solar | 602.02 | Tap 345KV 5133 Elm Creek - 5323 Old Hickory | 2027-04-29 | 2021-11-23 | True |  |  | Signed; security posted
24INR0376 | Huisache BESS | Huisache Solar, LLC | Wilson | Battery storage | 100.67 | Tapping the Elm Creek to Shaula circuit 1 | 2029-06-30 | 2025-08-12 | True |  |  | Signed; security posted | Signed -> Signed; security posted
24INR0160 | Huisache Solar | Huisache Solar, LLC | Wilson | Solar | 125.59 | Tapping the Elm Creek to Shaula circuit 1 | 2029-06-30 | 2025-08-12 | True |  |  | Signed; security posted | Signed -> Signed; security posted
23INR0318 | Marcelina Storage | Marcelina Solar, LLC | Wilson | Battery storage | 203.21 | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | 2026-12-18 |  |  |  |  | In study
28INR0250 | Mojo Solar | Power Synergy | Wilson | Solar | 527.94 | Tap 345 kV 5133 Elm Creek - 5901 San Miguel CKT 1 & 2 | 2028-06-30 |  |  |  |  | In study
28INR0299 | Moon Stone BESS | Moon Stone Battery Facility LLC | Wilson | Battery storage | 200.8 | Tap 138kV Eagle Creek (5132) to Floresville (5155) | 2029-03-31 |  |  |  |  | In study
24INR0156 | Moonstone Solar Project | Moon Stone Solar Farm, LLC | Wilson | Solar | 174.97 | Tap 138kV Eagle Creek (5132) to Floresville (5155) | 2029-03-31 | 2025-02-17 |  |  |  | Signed
29INR0318 | Nockenut Springs Storage 1 | Pecan Springs Energy, LLC | Wilson | Battery storage | 209.36 | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | 2029-06-05 |  |  |  |  | In study
29INR0319 | Nockenut Springs Storage 2 | Pecan Springs Energy, LLC | Wilson | Battery storage | 209.38 | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | 2029-06-05 |  |  |  |  | In study
29INR0320 | Nockenut Springs Storage 3 | Pecan Springs Energy, LLC | Wilson | Battery storage | 209.38 | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | 2029-06-05 |  |  |  |  | In study
25INR0248 | Strawberry Acres Storage | Strawberry Acres Energy Center, LLC | Wilson | Battery storage | 156.73 | 5132 Eagle Creek Substation 138kV | 2028-09-30 |  |  |  |  | In study
28INR0494 | Wilson Gas Plant | Misae Gas Power | Wilson | Gas engines | 402.88 | Tap 345 kV 5133 ELMCREEK - 5901 MIGUEL5 CKT 1 Tap 345 kV 5133 ELMCREEK - 5901 MIGUEL5 CKT 2 | 2028-06-30 |  |  |  |  | In study
23INR0071 | BRP Volans BESS | BRP Volans BESS LLC | Winkler | Battery storage | 206.88 | 11189 Quarry Field SW - 1074 Wink 138kV | 2027-12-01 |  |  |  |  | In study
25INR0711 | Coyanosa Gas | RPC Merchant, LLC | Winkler | Gas engines | 9.9 | Station Name: COYANOSA Load Name: COYAN_2 TNMP Transformer Name: Xfmr T-2 (25kV) Bus#: 38380 Transmission Voltage: 138kV Node: 0033 | 2026-12-17 | 2025-03-13 | True |  |  | Signed; security posted
30INR0128 | Horizon Ridge Wind | CPV Horizon Ridge Wind, LLC | Winkler | Wind | 406.55 | POIB is 131853 NOTSW_1_8 - the Notrees SW Substation - Project includes property in Ector, Andrews, and Winkler counties. | 2030-04-23 |  |  |  |  | In study | new
25INR0656 | Gilleys Energy Storage | Gilleys Energy Storage, LLC | Wise | Battery storage | 306.4 | Tap 345 kV 1730 West Krum - 6111 Riley CKT 2 | 2028-04-21 |  |  |  |  | In study
25INR0184 | Legato BESS | Legato Storage, LLC | Wise | Battery storage | 202.65 | 138kV #608 Crafton Substation - #620 Bowie Substation | 2028-04-24 |  |  |  |  | In study
26INR0329 | Pianissimo BESS II | Pianissimo Storage, LLC | Wise | Battery storage | 202 | Tap 138kV 685 LEO - 587 GREENWOOD | 2027-12-31 |  |  |  |  | In study
27INR0618 | Prairie Point Energy Storage I | Prairie Point LLC | Wise | Battery storage | 1000 | RAMHORNH 5 - 31875 | 2027-12-31 |  |  |  |  | In study
27INR0619 | Prairie Point Energy Storage II | Prairie Point LLC | Wise | Battery storage | 1000 | RAMHORNH 5 - 31875 | 2027-12-31 |  |  |  |  | In study
26INR0318 | Sandford Solar | BT Sandford Solar, LLC | Wise | Solar | 126.18 | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | 2029-01-30 |  |  |  |  | In study
26INR0319 | Sandford Storage | BT Sandford Solar, LLC | Wise | Battery storage | 100.93 | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | 2029-01-30 |  |  |  |  | In study
27INR0040 | Solar Star Rhome Storage | Solar Star Rhome Storage | Wise | Battery storage | 226.24 | 576 RHOME 138kV | 2029-09-27 |  |  |  |  | In study
28INR0278 | Spur Energy Storage | Spur Energy Storage, LLC | Wise | Battery storage | 612.62 | Tap 345kV (1429) JACKSBRO_5 - (11736) BIRDDOG_5 | 2029-09-15 |  |  |  |  | In study
20INR0286 | Wise County Power Repower (CT1, CT2) | Wise County Power Company LLC | Wise | Gas combined cycle | 21 | 1421 Willow Creek 345kV | 2026-12-19 | 2001-03-19 | True |  |  | Signed; security posted
25INR0466 | Yooperlite Storage | BT Yooperlite Storage, LLC | Wise | Battery storage | 175.65 | Tap 138 kV 580 Westbrook Switch - 588 Willow | 2028-05-31 |  |  |  |  | In study
29INR0084 | Jolly Rock Storage Center | Jolly Rock Storage Center LLC | Young | Battery storage | 208.57 | Tap 138kV 1431 GRAHAM Plant Switch - 11525 Short Grass Circuit 1. | 2029-05-16 |  |  |  |  | In study
29INR0204 | Miller Bend Energy BESS | Miller Bend Energy , LLC | Young | Battery storage | 547.65 | Tap 345kV (Bus1#1430) Graham SES to (Bus2#11050) Dusty Road | 2029-12-01 |  |  |  |  | In study
29INR0203 | Miller Bend Energy Solar | Miller Bend Energy, LLC | Young | Solar | 531.84 | Tap 345kV (Bus1#1430) Graham SES to (Bus2#11050) Dusty Road | 2029-12-01 |  |  |  |  | In study
25INR0306 | Red Top Solar I | Cat Red Top Solar, LLC | Young | Solar | 200.59 | Tap 138kV 1431 Graham SES - Short Grass 11525 | 2029-04-20 |  |  |  |  | In study
29INR0172 | Sweetheart BESS | Sweetheart Energy, LLC | Young | Battery storage | 310.16 | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | 2029-12-01 |  |  |  |  | In study
29INR0171 | Sweetheart Solar | Sweetheart Energy, LLC | Young | Solar | 301.14 | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | 2029-12-01 |  |  |  |  | In study
20INR0019 | Trinity Hills Wind repower | Trinity Hills Wind Farm LLC | Young | Wind | -27 | 17002 Garvey Rd 345kV | 2026-12-31 | 2018-10-17 |  |  | 2020-05-22 | Approved for synchronization
26INR0302 | Young County Energy Storage | Young County Energy Storage LLC | Young | Battery storage | 104.5 | TAP 138 KV BUS AND CREAT NEW BUS BETWEEN MURRAY (792) AND GRAHAM SES (1431) COUNTY : YOUNG | 2028-08-01 |  |  |  |  | In study
28INR0337 | Barrosos Creek Wind 3 | Cascabel Wind Energy, LLC | Zapata | Wind | 197.75 | #80227 Rapido 345 kV | 2028-05-31 |  |  |  |  | In study
28INR0338 | Barrosos Creek Wind 4 | Cascabel Wind Energy, LLC | Zapata | Wind | 197.75 | #80227 Rapido 345 kV | 2028-05-31 |  |  |  |  | In study
23INR0237 | Big River BESS | Rio Grande River Solar LLC | Zapata | Battery storage | 51.26 | tap 138kV 8299 Zapata - 8957 Lopeno4A | 2028-12-31 |  |  |  |  | In study
23INR0215 | Big River Solar | Rio Grande River Solar LLC | Zapata | Solar | 104.35 | tap 138kV 8299 Zapata - 8957 Lopeno4A | 2028-12-31 |  |  |  |  | In study
24INR0424 | Cascabel Wind 1 | Vaquero Wind Energy, LLC | Zapata | Wind | 197.75 | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307) | 2027-12-01 | 2025-05-23 | True |  |  | Signed; security posted
23INR0561 | Cascabel Wind 2 | Vaquero Wind Energy, LLC | Zapata | Wind | 197.75 | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307). | 2027-12-01 | 2025-05-23 | True |  |  | Signed; security posted
24INR0505 | Corralitos Wind 1 | Vaquero Wind Energy, LLC | Zapata | Wind | 196.1 | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | 2027-12-01 | 2025-06-19 | True |  |  | Signed; security posted
24INR0506 | Corralitos Wind 2 | Vaquero Wind Energy, LLC | Zapata | Wind | 195.4 | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | 2027-12-31 | 2025-06-19 | True |  |  | Signed; security posted
28INR0339 | Corralitos Wind 3 | Las Crestas Wind Energy, LLC | Zapata | Wind | 196.1 | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | 2028-05-31 |  |  |  |  | In study
28INR0340 | Corralitos Wind 4 | Las Crestas Wind Energy, LLC | Zapata | Wind | 195.4 | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | 2028-05-31 |  |  |  |  | In study
29INR0169 | Falcon BESS | Falcon Energy Project, LLC | Zapata | Battery storage | 516.72 | Tap 345kV #80225 CENIZO to #80307 DEL SOL | 2029-12-01 |  |  |  |  | In study
28INR0483 | Falcon II BESS | Falcon Energy Project | Zapata | Battery storage | 103.3 | 8004 Revilla 138 kV | 2032-02-16 |  |  |  |  | In study
28INR0482 | Falcon II Solar | Falcon Energy Project | Zapata | Solar | 100.32 | 8004 Revilla 138 kV | 2032-02-16 |  |  |  |  | In study
28INR0317 | Falcon Solar | Falcon Energy Project, LLC | Zapata | Solar | 501.96 | Tap 345kV #80225 Cenizo7C to #80307 Del Sol7C | 2029-12-01 |  |  |  |  | In study
26INR0116 | Falcon Zapata Storage 138 | Falcon BESS, LLC | Zapata | Battery storage | 200.79 | Tap 138kV 8299 Zapata - 8957 Lopeno | 2028-03-11 | 2026-02-03 | True |  |  | Signed; security posted
26INR0107 | Freedom Falcon BESS | Falcon BESS, LLC | Zapata | Battery storage | 501.9 | Tap 345kV #80224 Tiempo - #80227 Rapido | 2028-08-11 |  |  |  |  | In study
30INR0042 | La Morena Energy Center BESS | Adapture Solar Development | Zapata | Battery storage | 250 | Tap 345 kV 80225 CENIZO7C - 80307 DELSOL7C | 2029-05-07 |  |  |  |  | In study
30INR0043 | La Morena Energy Center Solar | Adapture Solar Development | Zapata | Solar | 250 | Tap 345 kV (80225) CENIZO7C - (80307) DELSOL7C | 2029-05-07 |  |  |  |  | In study
24INR0077 | Quarter Ranch Solar | Gransolar Texas Three LLC | Zapata | Solar | 154.12 | 80223 Cenizo Substation 345kV | 2028-10-15 |  |  |  |  | In study
28INR0503 | Rancho Grande Solar | Bordas Renewable Energy, LLC | Zapata | Solar | 251.58 | 345 kV Tiempo Substation #80224 | 2028-05-09 |  |  |  |  | In study
23INR0006 | Sierra Madre Solar | Sierra Madre Solar LLC | Zapata | Solar | 255.15 | tap 345kV 80307 Del Sol - 80225 Cenizo | 2027-12-01 |  |  |  |  | In study
24INR0184 | Slate Solar Project | Ignis TX Solar Three LLC | Zapata | Solar | 104.89 | Tap 138kV 8646 Rio Bravo - 8985 San Ygancio | 2030-01-15 |  |  |  |  | In study
28INR0005 | Tetris Solar | NextEra Energy Interconnection Holdings LLC | Zapata | Solar | 359 | TAP 345kV 80307 Del Sol 7C - 80225 Cenizo 7C | 2029-07-01 |  |  |  |  | In study
17INR0043 | Vaquero 1 Wind | Enerverse | Zapata | Wind | 400 | tap 345kV 8905 N Edinb - 8455 Lon Hill | 2027-01-15 |  |  |  |  | In study
30INR0093 | Wallflower Energy Storage | Wallflower Energy Storage | Zapata | Battery storage | 209.16 | Tap the 345 kV Cenizo (#80225) - Del Sol (#80307) line | 2029-12-30 |  |  |  |  | In study
30INR0092 | Wallflower Solar | Wallflower Solar, LLC | Zapata | Solar | 201.15 | Tap the 345 kV Cenizo (#80225) - Del Sol (#80307) line. | 2029-12-30 |  |  |  |  | In study
24INR0131 | Zelus BESS | BRP Zelus BESS LLC | Zapata | Battery storage | 201.03 | the 138 kV Zapata Substation (#8299; AEP) | 2027-12-01 |  |  |  |  | In study
26INR0120 | Bramble Energy Center | Bramble Energy Center, LLC | Zavala | Battery storage | 225.1 | 8236 West Batesville 138kV | 2028-12-22 |  |  |  |  | In study
27INR0274 | Flying Kite Bess | Flying Kite BESS, LLC | Zavala | Battery storage | 104.93 | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | 2027-12-30 |  |  |  |  | In study
25INR0304 | Flying Kite Solar | FLYING KITE SOLAR LLC | Zavala | Solar | 80.38 | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | 2027-12-30 | 2024-10-02 |  |  |  | Signed
27INR0380 | La Mancha Solar SLF | La Mancha Solar, LLC | Zavala | Solar | 40.9 | Tap 69kV 5836 NBatesville - 5822 Leona | 2028-10-10 |  |  |  |  | In study
27INR0381 | La Mancha Storage SLF | La Mancha Storage, LLC | Zavala | Battery storage | 40.9 | Tap 69kV 5836 NBatesville - 5822 Leona | 2028-10-10 |  |  |  |  | In study
26INR0179 | SunShiner ESS | SunShiner ESS LLC | Zavala | Battery storage | 200 | 8008 La Pryor4A | 2029-05-11 |  |  |  |  | In study